## Slide 1: PMP® Exam Preparation PMP 250
Session # 11
Project Integration Management
Project Management Professional, (PMP), is a registered mark of the Project Management Institute , Inc.

## Slide 2
The contents of this lesson are based on:
A Guide to Project Management Body of Knowledge (PMBOK® Guide) Sixth Edition
Published and Owned by
Project Management Institute, PMI®
PMBOK, PMP, CAPM and PMI are registered trade marks of Project Management Institute, Inc.

## Slide 3: LEARNING OBJECTIVES
Understand:
  How project integration management processes relate to the 5 project management process groups in a project phase
  The inputs, tools and techniques and outputs for managing project integration processes as outlined in PMBOK® 6th Edition Guide

## Slide 4: Introduction to Project Integration
What is Project Integration?
  The knowledge area includes the processes and activities needed to identify, define, combine, unify and coordinate the various processes and project management activities within the Project Management Process Groups.
  Project Integration includes unification, consolidation, communication and interrelationship characteristics throughout the project, applicable to:
  Resource Allocation
  Assessing Alternative Approaches
  Adapting The Processes to the Project Objectives
  Managing Interdependencies Among Knowledge Areas
Notes: PM managerial approach P 221

## Slide 5: Introduction to Project Integration
CONCEPT
DELIVERABLES (OUTPUTS)
Scope
Cost
Quality
Time
Communications
Resources
Procurement
Risk
WORK
(INPUTS)
Stakeholders

## Slide 6: Key Concepts of Integration Management
The Project Manager combines the results of all other knowledge areas and is ultimately responsible for the project as a whole
Projects and Project Mgmt. are integrative in nature. The links among process groups are often iterative.
Project Integration involves:
Aligning Time & Benefits of Results
Using Appropriate Project Knowledge
Planning Project to Achieve Objectives
Managing Activities & Integrating Changes
Processing Data to Report Progress
Monitoring & Controlling Progress
Making Integrated Decisions re. Changes
Managing Phase Transitions
Completing & Closing Project or Phase
Sophisticated integration is necessary for more complex projects with more variations of stakeholder expectations

## Slide 7: Trends & Emerging Practices in Project Integration Management
Project Integration Management
Use of Automated Tools (PMIS)
Use of Visual Management Tools
Project Knowledge Mgmt.
Expanding PM’s Responsibilities; Initiate & manage Benefits
Combining Results from All Other Knowledge Areas
Hybrid Methodologies: Agile, Business Analysis
eg. white-board, sticky notes
PM software

## Slide 8: Integration Management Tailoring
CONSIDERATION | NEEDED TAILORING
Project Life Cycle | What phases are appropriate for the Project life cycle?
Development Life Cycle | What is the appropriate cycle for the project? Predictive or adaptive? If adaptive, should the product be developed by Iterative, Incremental or Hybrid approach? In Iterative & Agile approaches, the control of the detailed product planning and delivery is delegated to the Team. The PM’s focus is on building collaborative decision-making environment and the team has the ability to respond to changes
Management Approach | Based on Org. culture, and Project Complexity, which approach would be more effective?
Change | How will change be managed in the project?
Governance | What Control Boards, Committees, and other Stakeholders are involved? Status Reporting Needs?
Lessons Learned | What information and historical information should be collected? How will these be made available for future projects?
Knowledge Mgmt. | How will knowledge be managed to foster collaborative working environment?
Benefits | How and when to report Benefits? At the end? Each iteration?

## Slide 9: Project Integration Management

## Slide 10: Project Integration Management

## Slide 11: 4.1 Develop the Project Charter
The Project charter
  Is a document that (1) formally recognizes the existence of a project (2) assigns a project manager and (3)provides the project manager with the authority to apply organizational resources to project activities.
  Includes (or refers to documents containing):
    project justification - Business Case for the project to address
    product description
  Provides direct link between the project and the strategic objectives of the organization, creates a formal record of the project, and shows the organizational commitment to the project.

## Slide 12: 4.1 Develop the Project Charter
The project charter either directly or by reference to other documents should address the following information:
  Requirements to satisfy stakeholders needs
  Business needs, high-level description of the requirements that the project is to satisfy
  Project purpose or justification
  Assigned Project Manager and authority level
  Summary milestone schedule
  Stakeholder influences
  Functional organizations and their participation
  Organizational, environmental, and external assumptions
  Organizational, environmental, and external constraints
  Business Case justifying the project, including return on investment
  Summary budget

## Slide 13: 4.1 Develop the Project Charter
Develop the Project Charter is the process by which the project or project phase is authorized. The authorization typically comes from someone external to the project team.
Roles that can authorize projects are sponsors, PMO, and portfolio steering committee.
A project or phase exists, as the result of the development and signoff of the project charter.
*stakeholders must all agree

## Slide 14: 4.1 Develop Project Charter
1. Project Charter
2. Assumption Log
Expert Judgment
Data Gathering
  Brainstorming
  Focus Groups
  Interviews
Interpersonal & Team
Skills
Conflict Mgmt.
Facilitation
Meeting Mgmt.
4. Meetings
Business Documents
Business Case
Benefits Mgmt. Plan
Agreements
Enterprise Env. Factors
Org. Process Assets
Inputs
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 15: 4.1.1 Develop Project Charter: Inputs
.1 Business Case
  Creates the justification for senior mgmt. decision-making to undertake the project, by providing a benefit-cost analysis. The business case is typically created as a result of:
    Market demand for a product or service
    Organizational needs
    Customer request
    Technological advance to develop faster, better, cheaper or more economical solutions to a problem.
    Legal requirements that must be compiled with
    Ecological impacts; i.e., to lessen environmental impact, a company causes
    Social need; i.e., to provide potable water, sanitation education, etc.
  The business case may be periodically reviewed to ensure that the project is delivering the expected business benefits. The PM does not update or modify the Business Case.
.2 Agreement
  Provides input regarding an external customer’s requirements. It could be in the form of a contract, MOU, SLA, Letters of Intend etc.

## Slide 16: 4.1.1 Develop Project Charter: Inputs
.2 Agreement – Cont’d
  A written definition of the sum of all the products and services that the project is to accomplish
  For internal projects, the sponsor provides the business needs or product/service requirements
  For external projects the customer provides the agreement as part of the RFP, or contract.
  The Agreement provides information regarding:
    Business need – Project justification
    Product Scope Definition - a brief summary of the product description
    Strategic Plan (all projects should support the organization’s goals)

## Slide 17: 4.1.1 Develop Project Charter: Inputs
.3 Enterprise Environmental Factors
  Factors and systems that surround and influence project’s success, including:
    Government or industry standards
    Legal or regulatory Requirements and/or Constraints
    Marketplace Conditions
    Organizational culture and Political Climate
    Organizational Governance Framework
    Stakeholders’ Expectations and Risk Tolerances

## Slide 18: 4.1.1 Develop Project Charter: Inputs
.4 Organizational Process Assets
  Organizational Formal/informal policies, procedures, plans and guidelines whose effect must be considered.
  Organizational standard policies, processes, and procedures
  Portfolio, Program and Project Governance Framework,
  Monitoring and reporting methods
  Templates
  Historical Information and Lessons Learned Repository.

## Slide 19: 4.1.2 Develop Project Charter: Tools & Techniques
.1 Expert Judgment
  Judgement provided based upon expertise in an application area, knowledge area, discipline, industry for the activity being performed. Expertise may be provided by any group or individual with specialized education, knowledge, skill or training, in the following topics:
  Organizational strategy
  Benefits Management
  Technical Knowledge of the industry and the project
  Time and Cost estimates
  Risk Identification

## Slide 20: 4.1.2 Develop Project Charter: Tools & Techniques
.2 Data Gathering
Key techniques used for this process could include:
    Brainstorming used to identify a list of ideas and solutions from stakeholders, SME’s, and Team members, when developing the project charter. The techniques comprises idea generation, and analysis.
    Focus Groups Bring together stakeholders and SME’s to discuss the perceived project risk, success criteria, and other relevant topics in a conversational mode.
    Interviews Talking one-to-one to stakeholders to obtain specific hi-level information, assumptions or constraints.

## Slide 21: 4.1.2 Develop Project Charter: Tools & Techniques
.3 Interpersonal and Team Skills
Conflict Management helps reconcile differences in stakeholders’ opinion on the objectives, success criteria, high-level requirements, milestones, and other elements of the charter.
Facilitation Guiding a group event where participants reach a conclusion or make a successful decision.
Meeting Management includes preparing the agenda, inviting representatives from key stakeholder groups, and sending the follow up minutes and action.
.4 Meetings
Held with key stakeholders to identify project objectives, success criteria, key deliverables, hi-level requirements, etc.

## Slide 22: 4.1.3 Develop Project Charter: Outputs
.1 Project Charter
  A document that (1)formally recognizes the existence of a project (2) assigns a project manager and (3)provides the project manager with the authority to apply organizational resources to project activities. includes (or refers to documents containing):
    Project purpose
    Measureable project objectives and success criteria
    High-level Requirements, project Description, and key Deliverables.
    Overall Project Risk
    Summary Milestone Schedule
    Preapproved Financial Resources
    Key Stakeholders’ list
    Product Approval Requirements
    Project Exit Criteria
    Name and authority of project sponsor and Project Manager
.2 Assumption Log
Hi-level strategic and operational assumptions, as identified in the Business Case

## Slide 23: Develop Project Management Plan

## Slide 24: 4.2 DEVELOP PROJECT MANAGEMENT PLAN
Project Management plan development is the process of creating an integrated project management plan. This integrated document becomes the baseline to measure any performance against. Developing the project management plan is an iterative process. As things change (and they always do), various updates could be added to the plan as a result of change control processes.
The project integration management knowledge area pulls many factors together. Falling short in one area can greatly impact other areas

## Slide 25: 4.2 Develop Project Management Plan
1 Project
Management Plan
1 Expert Judgment
2 Data Gathering
Brainstorming
Checklists
Focus Groups
Interviews
.3 Interpersonal & Team
Skills
Conflict Mgmt.
Facilitation
Meeting Mgmt.
.4 Meetings
1 Project Charter
2 Outputs from other
processes
3 Enterprise Env. Factors
4 Organizational Process
Assets
Inputs
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 26: 4.2.1 Develop Project Management Plan: Inputs
.1 Project Charter
  A document that formally recognizes the existence of a project, designates and provides the project manager with the authority to apply organizational resources to project activities.
.2 Outputs from Other Processes
  As other planning processes are completed their outputs are integrated into the overall project Management Plan. The plan should comprise the following auxiliary plans:
    Scope Management Plan x Resources Management Plan
    Time Management Plan x Communications Management Plan
    Cost Management Plan x Risk Management Plan
    Quality Management Plan x Procurement Management Plan
    x Stakeholder Management Plan

## Slide 27: 4.2.1 Develop Project Management Plan: Inputs
.3 Enterprise Environmental Factors
  Factors that could influence development of the project plan may include:
    Government or industry standards
    Legal or regulatory Requirements and/or Constraints
    PMBOK® relevant to the focus area; i.e., construction, Agile, Risk etc.
    Organizational structure, culture, mgmt. policies, and sustainability
    Organizational Governance Framework
    Infrastructure; i.e., facilities, capital equipment
  .4 Organizational Process Assets
  Org. assets that could influence development of the project management plan may include:
  Organizational standard policies, processes, and procedures
  Project Management templates:
    Guidelines and criteria for tailoring organization’s standard processes to her specific project
    Project closure guidelines for validation and acceptance of project outcome.
  Change control procedures, detailing how any change will be approved and validated
  Monitoring and reporting methods
  Project information from previous similar projects
  Historical Information and Lessons Learned Repository.

## Slide 28: 4.2.2 Develop Project Management Plan: Tools & Techniques
.1 Expert Judgment
  Considered for developing project plan development to:
  Tailoring PMBOK® processes to meet the project needs
  Developing additional components of the plan if needed.
  Determining the tools and techniques to be used for the processes
  Developing technical and management details to include in the plan
  Determining resources and skills levels needed for the project
  Defining the configuration management level to apply on the project
  Determining which project documents will be subject to formal change control process
  Prioritizing work on the project to optimize resource allocation

## Slide 29: 4.2.2 Develop Project Management Plan: Tools & Techniques
.2 Data Gathering
Key techniques used for this process could include:
    Brainstorming used to gather ideas and solutions about the project approach. Attendees include Team members, SME’s, stakeholders.
    Checklists to guide the PM develop the plan or verify that all needed information is included in the plan.
    Focus Groups Bring together stakeholders and SME’s to discuss the project management approach and the integration of different components into the plan.
    Interviews Talking one-to-one to stakeholders to obtain specific from stakeholders to develop the project plan

## Slide 30: 4.2.2 Develop Project Management Plan: Tools & Techniques
.3 Interpersonal and Team Skills
Conflict Management helps reconcile differences in stakeholders’ opinion on all aspects of the project management plan.
Facilitation Guiding a group participants to achieve a mutual understanding, that all contributions are considered and that conclusions or results have the buy-in according to established decision process.
Meeting Management necessary to ensure that the numerous meetings that are held to develop, unify and agree on the project plan are well run.

## Slide 31: 4.2.2 Develop Project Management Plan: Tools & Techniques
.4 Meetings
Meetings are held to discuss the project approach, and establish how the work needed to accomplish project objectives, will be performed monitored and controlled.
The project kick-off meeting, usually held at the end of the planning period, is for communicating the objectives of the project, gain the team’s commitment and explain the roles and responsibilities of each stakeholder.
The kick-off meeting takes place along with the Executing Process Group.

## Slide 32: 4.2.3 Develop Project Management Plan: Outputs
.1 Project Management Plan
  The project management plan is the overarching document that describes how the project will be executed, monitored, controlled and closed.
  The Project Mgmt. Plan integrates and consolidates all of the Subsidiary Management Plans, Baselines, and Additional Component formation as needed to manage the project.
Baselines
1. Scope Baseline
Scope Statement
WBS
WBS Dictionary
2. Schedule Baseline
3. Cost Baseline
The Time-Phased Budget
Additional Components
Change Management Plan
Configuration Management Plan
Performance Measurement Baseline
Project Life-Cycle
Development Approach
Management Reviews

## Slide 33: Subsidiary Plans Included in Project Management Plan
Adopted from PMI’s PMBOK® Guide
Scope
Management
Plan
Cost
Management
Plan
Schedule
Management
Plan
Project
Management
Plans
Quality
Management
Plan
Resource
Management
Plan
Communications
Management
Plan
Procurement
Management
Plan
Risk
Management
Plan
Stakeholder
Management
Plan
Requirements
Management
Plan

## Slide 34
PMBOK® Guide, Table 4-1

## Slide 35: 4.3 Direct & Manage Project Work

## Slide 36: 4.3 Direct & Manage Project Work
This process is for leading and performing the work defined in the Project Mgmt. plan, and implementing approved changes, to achieve project objectives and complete the deliverables.
The PM and the Project Mgmt. Team direct planned activities, manage various organizational interfaces, review the impact of project changes, implement approved changes, and manage corrective, preventive and repair work.

## Slide 37: 4.3 Direct & Manage Project Work
1 Deliverables
2 Work Performance Data
3 Issue Log
4 Change Requests
5 Project Management Plan
Updates
.6 Project Documents
Updates
.7 Org. Process Assets
Updates
1 Expert Judgment
2 Project Management
Information System
. 3 Meetings
Inputs
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)
.1 Project Management Plan
Any Component
.2 Project Documents
Change Log
Lessons Learned Register
Milestone List
Project Communications
Project Schedule
Requirements Traceability Matrix
Risk Register
Risk Report
.3 Approved Change
Requests
.4 Enterprise Env, Factors
.5 Org. Process Assets

## Slide 38: 4.3.1 Direct & Manage Project Work: Inputs
.1 Project Management Plan
  Any component of this formal, approved document used to manage and control project execution, is an input to this process
.2 Project Documents
    Change Log contains the status of all change requests
    Lessons Learned Register Used to improve performance and to avoid repeating mistakes
    Milestone List Shows milestone dates
    Project Communication Includes performance reports, deliverable status, other information generated by the project
    Project Schedule Shows list of activities, their duration and resources and planned dates
    Requirement Traceability Matrix links product requirements to the deliverables that satisfy them
    Risk Register for information on threats and opportunities that may impact the project
    Risk Report identifies sources for overall project risks along with a summary information on individual project risks.

## Slide 39: 4.3.1 Direct & Manage Project Work: Inputs
.3 Approved Change Requests
  Adjustments, such as Scope changes, modifications to plans, procedures, costs, or schedules. Change requests are reviewed, and implemented if approved to bring expected future project performance in line with the project plan
  Approved change requests are an output of Perform Integrated Change Control.
  Approved changes may include
    Approved Preventive Actions To reduce probability of negative consequences
    Approved Defect Repair
    Validated Defect Repair: Notification that re-inspected items have been accepted or rejected

## Slide 40: 4.3.1 Direct & Manage Project Work: Inputs
.4 Enterprise Environmental Factors
  The following factor may influence directing and managing project work:
    Organizational structure, culture, management practices and sustainability
    Existing facilities and capital resources
    HR administrative guidelines
    Stakeholders’ risk tolerance
.5 Organizational Process Assets
  The following org. assets may influence directing and managing project work:
  Organizational standard processes, procedures and policies
  Issue and defect management procedures, including defining, identification, controlling, resolution and tracking of issues and defects
  Issue management databases providing historical information.
  Performance measurement databases
  Change and risk control procedures
  Project information from previous projects

## Slide 41: 4.3.2 Direct & Manage Project Work: Tools & Techniques
.1 Expert Judgment
  Expertise that could be provided by any group or individuals with specialized knowledge or training, including:
  Technical knowledge on the industry and focus area of the project
  Cost, budget and procurement management
  Legal, legislative, regulatory and governance information
.2 Project Management Information Systems (PMIS)
IT Systems and Software tools such as: scheduling, work authorization, configuration management, information collection and distribution systems.
Corporate knowledge base repositories.
Automated gathering and reporting on Key Performance Indicators (KPI)

## Slide 42: 4.3.2 Direct & Manage Project Work: Tools & Techniques
.3 Meetings
Meetings are held to discuss and address topics related to project directing and managing work. Participants include the project manager, the project team and other stakeholders as appropriate.
These meetings should be well prepared with a well-defined agenda purpose and objectives. Meetings could be held for the purpose of:
Information exchange
Brainstorming, options evaluation, or design
Decision making

## Slide 43: 4.3.3 Direct & Manage Project Work: OUTPUTS
.1 Deliverables
  A unique and verifiable outcome/result of the project or a phase, capable of performing the required functions or fulfilling specified needs, as per the project plan or a component of the plan.
  Change control should be applied once the first version of the deliverable is completed. The control of multiple versions or editions of a deliverable is supported by configuration management tools and procedures.
.2 Work Performance Data
  Raw performance data identified during activities performed to carry out the project work. Performance data when processed, creates information to be derived by other processes. Such data includes: percentage of work completed, KPI, technical performance measures, actual dates of activities, story pints completed, deliverable status, schedule progress, number of change requests, actual costs incurred, actual duration, etc.

## Slide 44: 4.3.3 Direct & Manage Project Work: OUTPUTS
.3 Issue Log
This project document keeps records of issues and problems encountered throughout the project life-cycle, to track and resolve them.
Log records may include information about: type, source, description, priority, responsibility, resolution target date, status, and resolution.

## Slide 45: 4.3.3 Direct & Manage Project Work: OUTPUTS
. 4 Change Requests
  Identified while the work is being done. Could be triggered by internal or external sources. May be required to expand project scope, modify cost or schedule estimates, etc.
  Change requests could involve
    Corrective action
    Preventive action
    Defect Repair
    Documentation updates

## Slide 46: 4.3.3 Direct & Manage Project Work: OUTPUTS
.5 Project Management Plan Updates
  Changes requested, approved and implemented during the project implementation would require updating the project plan and its baselines in areas such as:
    Requirement Management Plan x Resources Management Plan
    Schedule Management Plan x Communication Mgmt Plan
    Cost Management Plan x Risk Management Plan
    Quality Management Plan x Procurement Mgmt Plan
.6 Project Document Updates
  Updates may be required to the following Project Documents
    Requirements Documents x Lessons learned register
    Issues and Assumption Logs x Activity lists
    Risk Register x Stakeholder Register
.7 Organizational Process Assets
Might need to be updated as a result of this process

## Slide 47: 4.4 Manage Project Knowledge

## Slide 48: 4.4 Manage Project Knowledge
This process allows the PM Team to leverage existing organizational knowledge and create new knowledge to achieve project’s objectives and contribute to organizational learning, to be available for future projects, and support operations.
Adopted from PMI’s (PMBOK® Guide)

## Slide 49: 4.4 Direct & Manage Project Work
1Lessons Learned Register
2 Project Mgmt. Plan Updates
Any component
3 Organizational Process
Assets Updates
1 Expert Judgment
2 Knowledge Management
.3 Information Mgmt.
. 4 Interpersonal & Team
Skills
Active Listening
Facilitation
Leadership
Networking
Political Awareness
Inputs
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)
.1 Project Management Plan
All Components
.2 Project Documents
Lessons Learned Register
Project Team Assignments
Resource Breakdown Structure
Source Selection Criteria
Stakeholder Register
Risk Register
.3 Deliverables
.4 Enterprise Env, Factors
.5 Org. Process Assets

## Slide 50: Types of Knowledge
EXPLICIT KNOWLEDGE
Can be codified using words, pictures numbers
TACIT KNOWLEDGE
Personal insights, believes, experience “know-how”
Knowledge Management
KNOWLEDGE SHARING & INTEGRATION
1. Reusing
Existing
Knowledge
2. Creating
New
Knowledge

## Slide 51: 4.4.1 Manage Project Knowledge: Inputs
.1 Project Management Plan (all components)
.2 Project Documents
Lessons Learned Register - provides information on effective practices in knowledge management
Project Team Assignments – provides information on available competencies in the project and knowledge that may be missing
Resource Breakdown Structure - provides information of composition of the team and may help understand what knowledge is available as a group and what knowledge is missing
Stakeholder Register – helps understand the knowledge stakeholders have
.3 Deliverables (completed tangible components)
Provides information about the product required to complete.

## Slide 52: 4.4.1 Manage Project Knowledge: Inputs
.4 Enterprise Environmental Factors
    The following factors can influence the process
    Organizational, Stakeholder and Customer Culture; A culture of trusting working relationships, no-blame, valuing leaning and social behavioral norms, is important in managing knowledge.
    Geographic Distribution of Facilities and Resources – Helps determine methods of gaining and sharing knowledge
    Organizational Knowledge Experts; i.e. Specialized Knowledge Mgrs.
    Legal and Regulatory Requirements and/or Constraints; Confidentiality of project information

## Slide 53: 4.4.1 Manage Project Knowledge: Inputs
.5 Organizational Process Assets
The factors that can influence the process include
Organizational Standards Policies, Processes, & Procedures; i.e.,
confidentiality and access to information, security, data protection, record retention polices, use of copyrighted information, destruction of confidential information, registry data and metadata, authorized communication technology.
Personnel Administration; e.g., development and training records, competency in knowledge sharing behavior
Organizational Communication Requirements; formal requirements are necessary for sharing information. Informal communication is more effective in creating new knowledge and integrating knowledge across diverse groups.
Formal Knowledge Sharing & Information Sharing Procedures; e.g., learning reviews during and post-project periods. Identifying, capturing and sharing lessons learned.

## Slide 54: 4.4.2 Manage Project Knowledge: Tools & Techniques
.1 Expert Judgement - Expertise to be considered:
- Info from other projects
- Knowledge Management - Information Management
- Organizational Learning - Knowledge & Info Mgmt. Tools
.2 Knowledge Management
- Communities of practice - Meetings (including online)
- Work Shadowing - Discussion groups (focus groups)
- Seminars & Conferences - Workshops for lessons learned
- Storytelling - Creativity & idea Mgmt. techniques
- Knowledge fairs - Interactive training
.3 Information Management- to create and connect people to information, & share knowledge
- Codifying explicit knowledge
- Lessons learned Register
- Library services
- Information gathering
- PMIS

## Slide 55: 4.4.2 Manage Project Knowledge: Tools & Techniques
.4 Interpersonal and Team Skills
- Active listening: reduces misunderstanding, improves communication
- Facilitation: guides a group to reach decision, solution or conclusion
- Leadership: to communicate the vision, inspire to focus on knowledge
- Networking: allows informal connections and relations among project stakeholders to be established and creates conditions to share tacit knowledge
- Political Awareness: helps project manager to plan communications based on project environment & organizational politics

## Slide 56: 4.4.3 Manage Project Knowledge: Outputs
.1 Lessons Learned Register
The register includes the following about the situation:
  Category & description
  The impact, recommendations and actions
  Challenges, problems, realized risks and opportunities
The Register, besides being an output of this process, is an input to many processes and updated throughout the project.
The Team start capturing the Lessons Learned early in the project, and document the knowledge using videos, pictures, audios, or other suitable means to ensure the efficiency of the lessons captured.
At the end of the project the information is transferred to the Organizational Process Assets called the Lessons Learned Repository
.2 Project Management Plan Updates
Any associated component(s) of the plan are updated for approved change requests.
.3 Organizational Process Assets Updates
All new knowledge created by projects are codified, or embedded in the deliverables, or integrated into the processes and procedures as a result of this process.
Existing knowledge can also be codified for the first time by this process.

## Slide 57: 4.5 Monitor and Control Project Work

## Slide 58: 4.5 Monitor and Control Project Work
This Process is for ensuring project work is carried out in accordance with the performance objectives defined in the project management plan. By tracking, reviewing and reporting the overall progress the stakeholders understand the current state, recognize corrections made to resolve performance issues, and have visibility into the future project status with cost and schedule forecasts.
Performed throughout the project, monitoring and control includes collecting, measuring and assessing measurements and trends to effect performance improvements. Control includes determining corrective or preventive actions or re-planning and following up to ensure the resolution of performance issues.

## Slide 59: 4.5 Monitor and Control Project Work
Monitoring and control is concerned with:
Comparing actual performance against project mgmt. plan.
Assessing performance periodically to determine the need for and then recommend appropriate corrective action
Identifying new risks and checking the status of existing risks
Maintaining accurate information base concerning the project’s deliverables and their documentation.
Providing reporting information
Providing forecasts to update current cost and schedule information
Monitoring implementation of approved changes
Providing appropriate reporting on project progress and status.
Ensuring that the project stays aligned with the business needs of the organization.

## Slide 60: 4.5 Monitor & Control Project Work Data Flow Diagram

## Slide 61: 4.5 Monitor and Control Project Work
1 Work performance
2 Change Requests
3 Project Mgmt Plan
Updates (any component)
4 Project Document
Updates
Cost Forecasts
Issue Log
Lessons Learned Rgstr
Risk Register
Schedule Forecasts
1 Expert Judgment
2 Data Analysis
Alternative Analysis
Cost-Benefit Analysis
EVA
Root Cause Analysis
Trend Analysis
Variance Analysis
3 Decision Making
4 Meetings
1 Project Mgt. Plan
2 Project Documents
Assumptions Log
Basis of Estimates
Cost Forecasts
Issues Log
Lessons Learned Register
Milestone List
Quality Reports
Risk Register
Risk Report
Schedule Forecasts
3 Work Performance Info
4 Agreements
5 Enterprise Env. Factors
6 Org. Process Assets
Inputs
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 62: 4.5.1 Monitor and Control Project Work: Inputs
.1 Project Management Plan
  The process involves looking at all components of the Project Mgmt. Plan and determine which should be an input to this process.
.2 Project Documents
Assumption Log provides information about project constraints
Basis of Estimates helps determine how to respond to variances
Cost Forecasts to determine the project is within budget tolerance range
Issue Log to document and monitor issue resolution by target date
Lessons Learned Register for info on variances and corrective action
Milestone List to check if specific milestones have been met
Quality Reports provides recommendations for processes, project,
product improvements, and corrective actions.
Risk Register for info on encountered risks and opportunities
Risk Report for info on specified and overall project risks
Schedule Forecasts help determine if the project is within defined
schedule ranges & identify necessary change requests

## Slide 63: 4.5.1 Monitor and Control Project Work: Inputs
.3 Work Performance Information
EXAMPLE: Work performance data includes cost actually expended to do work. The data has to be compared to the budget, the percentage of the work completed, the resources used to accomplish the work, and the funding schedule. The Performance Information provides the context to determine if the project is on budget or not. If there is a variance, the information also indicates the degree of variance from the plan, and determines if corrective action is required.

## Slide 64: 4.5.1 Monitor and Control Project Work: Inputs
.4 Agreements
When project work is totally or partially outsourced in accordance with a procurement agreement, the PM needs to oversee the contractor’s work to make sure that the agreements meet the specific needs of the project in accordance with the organizational procurement policies.
.5 Enterprise Environmental Factors
The following factor may influence the monitoring and control of the project work:
PMIS such as scheduling, cost, resourcing tools, performance indicators, databases, product records and financials.
Existing facilities and equipment, organization’s telecommunication channels
Stakeholders expectations and risk tolerance levels
Government or industry standards, regulations, product standards, quality standards, workmanship standards

## Slide 65: 4.5.1 Monitor and Control Project Work: Inputs
.6 Organizational Process Assets
  Organizational assets that could influence monitoring and control of project work:
  Organizational standards, policies and procedures
  Financial control procedures,
  Monitoring and reporting methods
  Issue and defect management procedures defining issue controls, identification, resolution and action item tracking.
  Organizational knowledge base, process measurement and lessons learned repository.

## Slide 66: 4.5.2 Monitor and Control Project Work: Tools & Techniques
.1 Expert Judgment
  Expertise from individuals or groups should be considered for:
  - Earned Value Analysis - Interpretation & contextualization of data
  - Duration & Cost Estimation Techniques - Trend Analysis
  - Technical Knowledge on the project industry - Risk Management; Contract Management
.2 Data Analysis
      Examples of such techniques:
      - Alternative Analysis - Earned Value Analysis
      - Cost/Benefit Analysis - Root cause analysis
      - Trend analysis - Variance analysis
      .3 Decision Making- includes unanimity, majority or plurality voting
      .4 Meetings – Includes face-to-face, virtual, or formal meetings, held to review
      project performance.

## Slide 67: 4.5.3 Monitor and Control Project Work: Outputs
.1 Work Performance Reports
Performance information compiled in project documents intended to generate awareness, help making decisions or taking actions. Specific work performance metrics may be defined at the start of the project and included in the normal work performance reports provided to the stakeholders.
Examples:
Status and Progress Reports,
Earned Value Graphs and Information
Trend lines and forecasts
Reserve burn-down charts
Defect histograms
Contract performance information
Risk Summaries

## Slide 68
.2 Change Requests
  Comparison of actual results with planned results, may require changes to be requested, to adjust, expand, or reduce project or product scope. The collection and documentation of new requirements may be necessary the review and disposition of changes.
  Change requests could involve
    Corrective action to realign project work with the Project Mgmt. Plan
    Preventive action to ensure future work is aligned with the Plan
    Defect Repairs to modify nonconforming product or component
4.5.3 Monitor and Control Project Work: Outputs

## Slide 69: 4.5.3 Monitor and Control Project Work: Outputs
.3 Project Management Plan Updates
  Changes identified, approved and implemented during monitoring and controlling project work might require updating the project plan and its baselines in areas such as:
    Schedule Management Plan x Scope Baseline
    Cost Management Plan x Schedule Baseline
    Quality Management Plan x Cost Performance Baseline
.4 Project Document Updates
  Updates may be required to the following Project Documents
    Cost Forecasts x Issue Log
    Lessons Learned Register x Risk Register
    Schedule Forecast

## Slide 70: 4.6 Perform Integrated Change Control

## Slide 71: 4.6 Perform Integrated Change Control
This process reviews all requests for changes to project documents, deliverables, or the project management plan, and depending on the application area and complexity of the project, determines whether to accept or reject them.
Change requests go through this process, after the project is baselined,
Whenever a change request may impact any of the project baselines, or involves an artifact is placed under configuration control, a formal integrated change control process is always required.
Every formal change request needs to be either approved, differed or rejected by a responsible person, identified by the Project Management Plan, or organizational policies. A Change Control Board (CCB) may also be chartered for the process.
Change requests, may require new or revised cost & time estimates, activity sequencing, resource requirements, or alternative risk responses.
Approved changes can require adjustments to the project mgmt. plan, and other documents.
The customer’s or the sponsor’s acceptance is required for approved changes that involve changes to the baselines.

## Slide 72: 4.6 Perform Integrated Change Control Data Flow Diagram

## Slide 73: 4.6 Perform Integrated Change Control
Perform Integrated Change Control may include any or all of the following actions, as appropriate:
  Determine that changes have occurred or need to occur
  Influencing change requests so that only needed changes can occur
  Reviewing and approving change requests
  Adjusting and monitoring impacted baselines as needed
  Implementing needed corrective action and/or preventive action
  Communicating changes to the project regarding implemented changes

## Slide 74: 4.6 Perform Integrated Change Control Flow - Chart
Adopted from PMI’s PMBOK® Guide

## Slide 75: 4.6 Perform Integrated Change Control
1 Approved Change Requests
2 Project Mgt. Plan Updates
3 Project Documents Updates
Change Log
1 Expert Judgment
2 Change Control Tools
3 Data Analysis
Alternative Analysis
Cost/Benefit Analysis
.4 Decision Making
Voting
Autocratic Decision
Multicriteria Analysis
5 Meetings
1 Project Mgmt Plan
Change Mgmt. Plan
Config Mgmt. Plan
Scope Baseline
Schedule Baseline
Cost Baseline
2 Project Documents
Basis of Estimates
Requiremts Traceability
Matrix
Risk Report
3 Work Performance
Reports
4 Change Requests
5 Enterprise Env Factors
6 Org Process Assets
Inputs
Tools &
Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 76: 4.6.1 Perform Integrated Change Control: Inputs
.1 Project Management Plan
  Components of the project mgmt. plan that may be included in the input:
  Change Management Plan provides direction for the change process
  Configuration Management Plan describes configurable items of the project that will be recorded and updated so that the project outcome remains operable
  Scope Baseline defines the project
  Schedule Baseline required to assess the impact of the changes on the schedule
  Cost Baseline required to assess the impact of the changes on the project cost
.2 Project Documents
Project documents that may be included in the input:
Basis of Estimates information on how to calculate the impact of the change
Requirements Traceability Matrix helps assess the change’s impact on scope
Risk Report provides information on the sources of risks involved in the change
  .3 Work Performance Reports
  Provides information about resource availability, schedule and cost data, burn-up or
  burn-down charts.

## Slide 77: 4.6.1 Perform Integrated Change Control: Inputs
.4 Change Requests
The requested changes may or may not impact the baselines
If the change only affects the performance against the baseline, the Project Manager reviews the request and may decide either to reject it or take corrective, preventive, or repair action, as appropriate.
Change requests that have an impact on the project baselines, must provide information about the (1) cost of implementing the change, (2) modifications to the scheduled dates, (3) resource requirements (4) risks. These changes are reviewed by the CCB.
Approved changes should be incorporated into a revised baseline.

## Slide 78: 4.6.1 Perform Integrated Change Control: Inputs
.5 Enterprise Environmental Factors The factors that may influence integrated change control include:
  Legal restrictions, requirements, and/or regulations
  Government or Industry Standards
  Organizational Governance framework (control, direction, policies etc.)
  Contractual constraints
.6 Organizational Process Assets
  Organizational assets that could influence integrated change control:
  change control procedures,
  approval procedures,
  performance measurement databases,
  previous project files, historical data, lessons learned,
  configuration management knowledge base, etc.

## Slide 79: 4.6.2 Perform Integrated Change Control: Tools & Techniques
.1 Expert Judgment
  The areas of expertise may include:
    Technical knowledge of the industry and focus area of the project
    Legislations and regulations relevant to the project
    Legal aspects of Procurement
    Configuration Management
    Risk Management
.2 Change Control Tools
  Tools are needed to facilitate the appropriate review and approval (or rejection) of change requests; i.e., Identification, recording and reporting status, verification and auditing of the configuration item. These tools should support the process activities to:
    Identify Changes
    Document Changes
    Decide on the Changes
    Track changes

## Slide 80: 4.6.2 Perform Integrated Change Control: Tools & Techniques
.3 Data Analysis
Analysis techniques that can be used for this process include:
Alternatives Analysis, to assess changes and decide which can be accepted, rejected, or modified for subsequent acceptance.
Cost Benefit Analysis, compares the benefits of the change with the associated costs
.4 Decision Making
Techniques include:
Voting
Autocratic Decision Making, made by an individual
Multicriteria Decision Making uses a decision matrix to evaluate the requested change on the basis of predefined criteria.
.5 Meetings
Held by CCB to assess the impact of the requested change and decide whether to accept, reject or consider alternatives.
The CCB also reviews configuration management activities.

## Slide 81: 4.6.3 Perform Integrated Change Control: Outputs
.1 Approved Change Request
  Approved change requests require a baseline update. Rejected change requests are usually sent back to requester for additional information
  Change requests are processed according to established change control systems.
  The status of all requested changes, are updated in the change request log, as part of project document updates.
.2 Project Management Plan Updates
  All impacted components of the plans, and relevant baselines need to be updated as a result of an approved change.
  Changes to the baselines should only show changes from the current time forward, to preserve the integrity of the baselines and the historical data of past performance.
.3 Project Document Updates
  Mainly the Change Request Log would need updating

## Slide 82: 4.7 Close Project or Phase

## Slide 83: 4.7 CLOSE PROJECT OR PHASE
Adopted from PMI’s (PMBOK® Guide)
This is the process for finalizing all activities and closing of the project or a phase. At the conclusion of this process, all project information are achieved, the planned project work completed and accepted by the customer, and resources released. The activities necessary for the administrative closure of the project or phase include: (refer PMBOK® 6th Ed Page 123 for details)
Actions & Activities necessary to satisfy completion or exit criteria for the phase or the project, confirming the formal delivery and customer acceptance of deliverables.
Activities related to the completion of the contractual agreements applicable to the project, and confirming the formal acceptance of the seller’s work
Activities needed to collect project records, audit project performance, identify and archive lessons learned.
Activities necessary to transfer the project products or services, to production or operation
Collecting any suggestions for improving or updating organizational policies or procedures and sending them to the appropriate organizational unit
Measuring stakeholder satisfaction

## Slide 84: 4.7 CLOSE PROJECT OR PHASE Data Flow

## Slide 85: 4.7 CLOSE PROJECT OR PHASE
Outputs
1 Project Docs Updates
Lessons learned Rgstr.
2 Final product, service or
results transition
.3 Final Report
.4 Org. Process Assets
Updates
1 Project Charter
2 Project Mgmt. Plan
3 Project Documents
Assumptions log
Basis of estimates
Change log
Issue log
Lessons Learned Rgstr.
Milestone List
Project Communications
Quality Cntrl. Measure’nts
Quality Reports
Req. Documentation
Risk register
Risk Reports
4 Accepted Deliverables
5 Business Documents
Business Case
Agreements
6 Procurement Docs
7 Org. Process Assets
Tools and
Techniques
1 Expert Judgment
2 Data Analysis
Document Analysis
Regression Analysis
Trend Analysis
Variance Analysis
3 Meetings
Adopted from PMI’s (PMBOK® Guide)
Inputs

## Slide 86: 4.7.1 CLOSE PROJECT OR PHASE: INPUTS
.1 Project Charter
  Defines the project success criteria, approval requirements and sign-off signatories.
.2 Project Management Plan
  All components of the project management plan are inputs to this process
.3 Project Documents
  The process requires information from the following Project Documents:
  - Assumptions Log - Basis of estimates
  - Change log - Issue log
  - Lessons Learned Register - Milestone List
  - Project Communications - Quality Control Documents
  - Quality Reports - Requirements Documentation
  - Risk Register - Risk Report

## Slide 87: 4.7.1 CLOSE PROJECT OR PHASE: INPUTS
.4 Accepted Deliverables
  Includes approved product specifications, delivery receipts, work performance documents.
.5 Business Documents
  Business Case justifies business needs and project cost/benefit analysis
  Business Management Plan outlines target benefits and their mgmt.
.6 Agreements
  Provide information plus terms and conditions for formal contract closure requirements.
  .7 Procurement Documents
  These documents are indexed and achieved to be used as lessons learned on
  future projects, providing information on contract details & performance, “as-build” drawings, manuals, trouble-shooting and other technical documentation.
  .8 Organizational Process Assets
  Organizational Process Assets influence the process by providing:
    Guidance in project or phase closure activities such as final product audits, evaluations, acceptance criteria, team performance appraisal, knowledge transfer
    Configuration Management knowledge base.

## Slide 88: 4.7.2 CLOSE PROJECT OR PHASE: TOOLS & TECHNIQUES
.1 Expert Judgment
  Expertise needed may include:
  - Management Control - Auditing
  - Legal and Procurement - Legislation & Regulations
.2 Data Analysis
The process may require analytical the following techniques:
- Document Analysis - Regression Analysis
- Trend Analysis - Variance Analysis
.3 Meetings
- Used to confirm deliverables have been accepted; exit criteria met
- formalize completion of contracts
- Evaluate stakeholder satisfaction
- Gather lessons learned

## Slide 89: 4.7.3 CLOSE PROJECT OR PHASE : OUTPUTS
.1 Project Documents Update
  On closure, the particular document that requires updating is:
    - Lessons Learned Register to include information on benefits management, accuracy of the Business Case, project and development life-cycles, risk and issue management, stakeholder engagement, etc.
.2 Final Product, Service, or Results Transition
The final product, service or result that the project was authorized to produce may be handed over to a different group or organization that will operate, maintain and support throughout its life.
.3 The Final Report
  Provides a summary level description of:
  The project or phase; Scope objectives, evaluation criteria and evidence that completion criteria were met.
  Quality objectives, evaluation criteria, for the project and product, the verification, actual delivery dates, and reasons for any variances.
  Validation information for the final product, service or result
  Schedule objectives and the degree the benefits were met
  The achievement of the business needs identified.
  Risks od issues encountered and how they were addressed

## Slide 90: 4.7.3 CLOSE PROJECT OR PHASE : OUTPUTS
.4 Organizational Process Assets Updates
Organizational Process Assets that may require updates:
Project Documents resulting from project activities; e.g., Project Management Plan, scope, cost, schedule, project calendars and change management documentation.
Operational and Support Documents required for the organization to maintain, operate, and support the product or service delivered by the project.
Project or Phase Closure Documents consisting of formal documentation that indicates completion of the project or phase and the transfer of the completed deliverables to others.
Lessons Learned Repository Lessons learned and knowledge gained throughout the project are transferred to the repository for future projects.