## Slide 1: PMP® Exam Preparation PMP 250 Session # 4 Project Schedule Management
Project Management Professional, (PMP), is a registered mark of the Project Management Institute , Inc.

## Slide 2
The contents of this lesson are based on:
A Guide to Project Management Body of Knowledge (PMBOK® Guide) Sixth Edition
Published and Owned by
Project Management Institute, PMI®
PMBOK, PMP, CAPM and PMI are registered trade marks of Project Management Institute, Inc.

## Slide 3: Objectives
By the end of this session you should understand:
  How Project Time Management processes relate to the 5 project management process groups in a project phase
  The inputs, tools and techniques and outputs for managing Project Time processes as outlined in PMBOK® Guide

## Slide 4
Project Schedule Management
6.2
Define
Activities
6.4
Estimate
Activity
Duration
6.6
Control
Schedule
6.5
Develop
Schedule
6.0
Project Schedule Management
6.1
Plan Schedule
Management
6.3
Sequence
Activities
Adopted from PMI’s (PMBOK® Guide)

## Slide 5
Project SCHEDULE Management
Adopted from PMI’s PMBOK® Guide

## Slide 6: Project Schedule Management
“Project Schedule Management includes the processes required to ensure timely completion of the project”
        PMBOK® Guide
        The project schedule is one of the most important documents a project manager develops. The schedule has to be accurate and relevant. The phrase “Garbage in, garbage out” applies to schedule development! Taking the time to gather the information necessary to develop a realistic schedule will pay off high dividends throughout the project.

## Slide 7: KEY CONCEPTS FOR PROJECT SCHEDULE MANAGEMENT
The Project Schedule is one the most important tools for the project team, for the following reasons:
  Determines when and how the project scope deliverables will be completed
  Serves as a tool for communication, managing stakeholders’ expectations
  Is the basis for performance tracking and reporting
Once the scheduling method, appropriate for the project, is selected; i.e., CPM or Agile, the project team enters the project-specific data into the schedule tool, (such as MS Project) to create schedule model.

## Slide 8: Scheduling Overview
PMBOK® 6th Edition Fig 6-2 page 176

## Slide 9: TRENDS & EMERGING PRACTICES IN PROJECT SCHEDULE MANAGEMENT
The emerging trend of high uncertainty and unpredictability of project scope, has given rise to the practice of adaptive scheduling, to respond to changing needs

## Slide 10: TAILORING CONSIDERATIONS
What is the most appropriate detailed approach?
Life Cycle Approach
What are the factors impacting duration?
Resource Availability
How will project complexity, uncertainty, impact project control?
Project Dimensions
Is technology to develop, record, transit and store schedule accessible?
Technology Support

## Slide 11: CONSIDERATIONS FOR AGILE/ADAPTIVE ENVIRONMENTS
Adaptive Approaches
  Use short cycle (iterations) to undertake work
  Review results of an iteration and adapt as necessary
  Provide rapid feedback on the approach and suitability of deliverables
Hybrid Approach
  Large projects require long-term planning to manage the development of the deliverables.
  For larger, enterprise-wide projects, Scaling factors (e.g. team size, geographical distribution, organizational and technological complexities) can be used.
  A Hybrid Approach, combining both predictive and adaptive can be adapted.

## Slide 12
6.1- Plan Schedule Management
Adopted from PMI’s (PMBOK® Guide)
6.2
Define
Activities
6.4
Estimate
Activity
Duration
6.6
Control
Schedule
6.5
Develop
Schedule
6.0
Project Schedule Management
6.1
Plan Schedule
Management
6.3
Sequence
Activities

## Slide 13: 6.1 PLAN SCHEDULE MANAGEMENT
This process provides guidance and direction on how the project schedule will be managed throughout its life-cycle.

## Slide 14: 6.1 PLAN SCHEDULE MANAGEMENT
Outputs
.1 Schedule Mgt. Plan
Inputs
.1 Project Charter
.2 Project Mgmt. Plan
Scope Mgmt. Plan
Development
Approach
.3 Enterprise
Environmental
factors
.4 Org. Process
Assets
Tools &
Techniques
.1 Expert Judgment
.2 Data Analysis
.3 Meetings

## Slide 15: 6.1.1 PLAN SCHEDULE MANAGEMENT - INPUTS
.1 Project Charter
Contains summary information about milestones, and project approval requirements, relevant to the schedule management plan.
.2 Project Management Plan
Contains information used to develop the schedule management plan, such as, but not limited to:
Scope Management Plan contains information about how the schedule will be developed
Development Approach provides information about the scheduling approach, estimating and controlling techniques, scheduling tools.

## Slide 16: 6.1.1 PLAN SCHEDULE MANAGEMENT - INPUTS
.3 Enterprise Environmental Factors
Environmental factors that influence developing a schedule management plan, include but are not limited to:
Organizational culture & Structure
Availability of skills and physical resources
Scheduling Software
Commercial databases providing standardized estimating data
Organizational standard processes and procedures to satisfy specific project needs
.4 Organizational Process Assets:
Influencing factors include, but are not limited to:
Monitoring/reporting tools •Templates and forms
Historical info • Existing relevant development, management and control policies, procedures and guidelines

## Slide 17: 6.1.2 PLAN SCHEDULE MANAGEMENT – TOOLS & TECHNIQUES
.1 Expert Judgment
Experts provide valuable inputs about the environment and information from prior similar projects, relevant planning schedule management process.
.2 Data Analysis
Alternative Analysis to choose among strategic options regarding: scheduling methodology, tools and techniques, estimating approaches, formats and project management software. The schedule management plan may also provide details on how to crash or fast track activities to compress project time.
.3 Meetings
Planning meetings held with the sponsor, selected stakeholders and the project team to develop the schedule management plan.

## Slide 18: 6.1.3 PLAN SCHEDULE MANAGEMENT – OUTPUTS
.1 Schedule Management Plan
A component of the project management plan, establishes how to develop, monitor and control the schedule. Helps determine how to establish the following:
Project Schedule development model
Release and iteration length
Level of schedule accuracy
Units of measure to be used in the schedule
Organizational procedures links; the WBS provides the framework for the schedule plan to ensure consistency
Project schedule model maintenance.
Control thresholds; i.e., thresholds for schedule variances allowed before taking corrective action
Rules for performance measurement - EVM rules set to measure
  Rules to establish Percentage complete
  EVM Techniques
Reporting formats

## Slide 19: 6.2 DEFINE ACTIVITIES
Activity Definition involves
  identifying and documenting the specific activities that must be performed to produce the deliverables and sub-deliverables identified in the work breakdown structure.
Implicit in the process is the need to define the activities such that the project objectives are met.
Adopted from PMI’s (PMBOK® Guide)

## Slide 20
Outputs
.1 Activity List
.2 Activity Attributes
.3 Milestone List
.4 Change Requests
.5 Project Mgmt. Plan
updates
Schedule Baseline
Cost Baseline
Inputs
.1 Project Mgmt. Plan
Schedule Mgmt. Plan
Scope Baseline
.2 Enterprise
Environmental
factors
.3 Org. Process
Assets
Tools &
Techniques
.1 Expert Judgment
.2 Decomposition
.3 Rolling Wave
Planning
.4 Meetings
Adopted from PMI’s (PMBOK® Guide)
6.2 DEFINE ACTIVITIES

## Slide 21: 6.2.1 - DEFINE ACTIVITIES: INPUTS
.1 Project Management Plan
The components include:
Schedule Management Plan Provides details about the methodology, duration, rolling wave planning and the level of detail to manage work.
Scope Baseline
  Provides details about deliverables, constraints, and assumptions.
    Assumptions
      must be documented
      are considered true, real, or certain for planning purposes
2 Enterprise Environmental Factors
- Org. Culture & Structure - Commercial Databases - PMIS
.3 Organizational Process Assets
Lessons Learned Repository (historical data)
Standardized Procedures
Templates
Activity planning related policies, procedures, and guidelines

## Slide 22
.1 Expert Judgment
  Project team members or other individuals can provide expertise in defining activities, from their past experience in similar projects.
.2 Decomposition
  Involves subdividing the project work packages into smaller components called activities, i.e., the effort needed to complete the work package.
  Decomposition is also used in creating the WBS
  The activity list, WBS, and WBS Dictionary can be created simultaneously or sequentially, while using the WBS as the foundation for creation of the activity list.
.3 Rolling wave planning
  Progressive elaboration planning; i.e. work in the near term is planned in detail, while work in the future is planned at higher levels of WBS
.4 Meetings
Held face-to-face or virtual format with team members to define project activities needed to complete the work
6.2.2 - Define ACTIVITIES: TOOLS & TECHNIQUES

## Slide 23: 6.2.3 - DEFINE ACTIVITIES: OUTPUTS
.1 Activity List
  A comprehensive list including all of the activities that need to be performed to complete the project.
  The Activity list is an extension of the WBS
  For Rolling Wave planning or Agile techniques, the activity list will be updated periodically as the project progresses.
. 2 Activity Attributes
Provide details about the project activities; i.e., Activity identifier (ID), WBS ID, activity label or name, activity description, predecessors/successors, leads/lags, resource requirements, constraints and assumptions.
. 3 Milestone List
  A milestone is a significant point in time or event in the project schedule.
  A component of project management plan
  Identifies whether a milestone is mandatory (contractual) or optional
.4 Change Requests
Change requests are needed when the progressive elaboration of the deliverables into activities may reveal work that may not have been in the initial project baseline.

## Slide 24: 6.2.3 - DEFINE ACTIVITIES: OUTPUTS
.5 Project Management Plan Updates
  Components of the Project Management Plan that may require updates, whenever changes are approved, include
    Schedule Baseline updating of the baseline with new delivery dates and other significant schedule milestones, is necessary for activities impacted by approved change requests.
    Cost Baseline updated whenever approved changes in schedule activities involve cost changes.

## Slide 25: SITUATIONAL QUESTIONS & REAL WORLD APPLICATION
Issues you might expect to encounter include work taking longer than expected, or not having an idea how long an activity should take.
The introduction of out-of-scope items into the project could pose
problems, depending upon how much “research” was done during
planning.
Time and cost estimates could be out-of-line, also if there were a
great number of items not identified originally, but needed to
complete the project
It is useful to develop a schedule management plan to know how to:
  Decompose work packages into activities and milestone
  Establish the network diagram
  Determine needed resources
  Integrate activities into the schedule
  Deal with schedule changes and updates

## Slide 26: 6.3 SEQUENCE ACTIVITIES
Adopted from PMI’s (PMBOK® Guide)
6.2
Define
Activities
6.4
Estimate
Activity
Duration
6.6
Control
Schedule
6.5
Develop
Schedule
6.0
Project Schedule Management
6.1
Plan Schedule
Management
6.3
Sequence
Activities

## Slide 27: 6.3 SEQUENCE ACTIVITIES
Involves identifying and documenting dependencies amongst project activities
Activities must be sequenced accurately in order to support later development of a realistic, achievable and efficient schedule.
Manual sequencing can be used on small projects
Computers are more effective on large projects in the later phases
Adopted from PMI’s (PMBOK® Guide)

## Slide 28: 6.3 SEQUENCE ACTIVITIES
Outputs
.1 Project Schedule
Network Diagrams
.2 Project Documents
updates
Activity attributes
Activity lists
Assumption log
Milestone list
Tools &
Techniques
.1 Precedence
Diagramming
Method (PDM)
.2 Dependency
Determination and
Integration
.3 Leads & Lags
.4 PMIS
Inputs
.1 Project Mgmt. Plan
Schedule Mgmt Plan
Scope Baseline
.2 Project Documents
Activity Attributes
Activity List
Assumptions log
Milestone list
.3 Enterprise Env.
Factors
.4 Organizational
Process Assets
Adopted from PMI’s (PMBOK® Guide)

## Slide 29: 6.3.1 SEQUENCE ACTIVITIES: INPUT
.1 Project Management Plan
Schedule Management Plan defines the method, the level of
accuracy, and the sequencing criteria required.
Scope Baseline the information documented is the baseline is considered for sequencing activities.
.2 Project Documents are the basis for what and how work will be done on the project.
Activity Attributes define sequence, dependencies, leads and lags between activities
Activity Lists
Assumption Log
Milestone List

## Slide 30: 6.3.1 SEQUENCE ACTIVITIES: INPUT
.3 Enterprise Environmental Factors
Government & Industry Standards
PMIS
Scheduling Tools
Organizational Work Authorization Systems
.2 Organizational Process Assets
Project dependencies of Portfolio and Program Plans
Policies, guidelines, methodologies related to activity planning
Templates
Lessons Learned repository

## Slide 31: 6.3.2 SEQUENCE ACTIVITIES: TOOLS & TECHNIQUES
.1 Precedence Diagramming Method (PDM)
  PDM is a diagramming technique in which activities are represented by boxes (nodes) and linked lines to show the sequence in which the activities are to be performed
  also known as Activity-on-Node (AON)
  AON does not allow for loops
  PDM supports four (4) types of dependency relationships:
    Finish to Start (FS)
    Finish to Finish (FF)
    Start to Start (SS)
    Start to Finish (SF)

## Slide 32: Relationship Types

## Slide 33: 6.3.2 SEQUENCE ACTIVITIES: TOOLS & TECHNIQUES
.2 Dependency Determination & Integration
  Mandatory Dependencies
    also known as “Hard Logic”
    are inherent in the work that is being performed i.e. the concrete must cure before putting up the superstructure
    often involve physical limitations
    must be taken into consideration when developing the schedule

## Slide 34: 6.3.2 SEQUENCE ACTIVITIES: TOOLS & TECHNIQUES
  Discretionary Dependencies
    also known as “Soft”, Preferred or Preferential Logic
    are defined by the project team and must be handled with care since they may limit later scheduling options
    are usually based on “best practices” within a particular application area
    can be used where a specific sequence is required…even though there are other acceptable sequences

## Slide 35: 6.3.2 SEQUENCE ACTIVITIES: TOOLS & TECHNIQUES
  External Dependencies
    Involve a relationship between project activities and non project activities i.e. testing software may depend on the delivery of hardware from an outside vendor
    Internal Dependencies
    Are within the control of the project team and involve a precedence relationship between project activities. Example: the team cannot test a machine before installing it.
.3 Leads & Lags
  leads allow for a modification of a logical relationship which allows an acceleration of the successor task.
    e.g. in a finish to start to dependency with a 10 day lead, the successor activity can start 10 days before the predecessor has finished
  lags provide for a modification of a logical relationship which causes a delay in the successor task.
    e.g. in a finish-to-start dependency with a 10 day lag, the successor activity cannot start until 10 days after the predecessor has finished

## Slide 36: Lags and Leads (cont’d)

## Slide 37: 6.3.2 SEQUENCE ACTIVITIES: TOOLS & TECHNIQUES
4. PMIS
Includes scheduling software, capable of planning, organizing and adjusting the sequence of activities; insert leads and lags are required, and allow the selection of different types of dependencies.
Example: Microsoft Project 2016

## Slide 38: 6.3.3 SEQUENCE ACTIVITIES: OUTPUTS
.1 Project Schedule Network Diagrams: are completed to show the sequencing of the activities on the project.
PMBOK® 6th Edition Fig 6-11 page 193

## Slide 39: 6.3.3 SEQUENCE ACTIVITIES: OUTPUTS
.2 Project Document Updates
Sequence Activities may require updates to the project document. These may include:
  Activity Attributes the sequencing information in this document may require updating
  Activity List may need to be updated if impacted by the change in activity relationships
  Assumption Log assumptions and constraints may need to be updated based on the sequencing relationship, leads and lags.
  Milestone List milestones dates may be changed due to changes in sequencing

## Slide 40: Situational questions & real world application
Sequencing issues may cause problems, such as being ready to start work but not having the necessary predecessor completed, or performing work that does not make logical sense in relation to the overall output of the project.

## Slide 41
6.4 ESTIMATE ACTIVITY RESOURCES
Adopted from PMI’s (PMBOK® Guide)
6.2
Define
Activities
6.4
Estimate
Activity
Duration
6.6
Control
Schedule
6.5
Develop
Schedule
6.0
Project Schedule Management
6.1
Plan Schedule
Management
6.3
Sequence
Activities

## Slide 42: 6.4 ESTIMATE ACTIVITY DURATION
In this process the key is to estimate the number of work periods to complete each activity. That estimation then rolls up to create summary estimates.
The process uses information from SOW, resource type and quantity estimates, resource calendars, constraints, estimated efforts required.
Other factors taken into consideration are:
  Law of diminishing returns for factors used to determine the required effort
  Number of resources
  Advances in technology
  Motivation of staff.
Adopted from PMI’s (PMBOK® Guide)

## Slide 43: 6.4 ESTIMATE ACTIVITY DURATION- DATA FLOW
Project Docs Input
Activity Attributes
Activity List, Milestone List
Assumption Log
Lessons Learned Register
Team Assignments
Resource Breakdown Structure
Resource Calendars
Resource Requirements
Risk Register
Project Docs Updates
Activity Attributes
Assumption Log
Lessons Learned Register

## Slide 44: 6.4 ESTIMATE ACTIVITY DURATION
Outputs
1 Duration Estimates
2 Basis of Estimates
3 Project Doc Updates
Activity Attributes
Assumption Log
Lessons Learned
Registry
Tools &
Techniques
1 Expert Judgment
2 Analogous Estimating
3 Parametric Estimating
4 Three-Point Estimate
5 Bottom-up Estimating
6 Data Analysis
Alternative Analysis
Reserve Analysis
7 Decision Making
8 Meetings
1 Project Mgmt. Plan
Schedule Mgmt. Plan
Scope Baseline
2 Project Documents
Activity Attributes
Activity List
Assumption Log
Lessons Learned Reg.
Milestone List
Project Team Asgmt.
RBS
Resource Calendar
Resource Requirements
Risk Register
3 Enterprise Org Factors
4 Org Process Assets
Adopted from PMI’s (PMBOK® Guide)
Inputs

## Slide 45: 6.4.1 ESTIMATE ACTIVITY DURATION: INPUTS
.1 Project Management Plan
Schedule Management Plan defines the method, accuracy level and other relevant criteria
Scope Baseline provides technical details for estimating duration
.2 Project Documents
Activity Attributes defines activity relationships
Activity List defines activities required and their dependencies
Assumption Log identifies sources of potential risks
Lessons Learned Register records of activity efforts and durations
Milestone List provides dates that may impact duration estimates
Project Team Assignment
Resources Breakdown Structure provides hierarchical structure for HR
Resource Calendar specifies availability of resources
Resource Requirements provides estimates of required resources.
Risk Register identified risks may impact resource selection

## Slide 46
SAMPLE REsource BREAKDOWN STRUCTURE
Adopted from PMI’s PMBOK® Guide

## Slide 47: 6.4.1 ESTIMATE ACTIVITY DURATION: INPUTS
.3 Enterprise Environmental Factors
can influence duration estimations by inputs from estimating databases, reference data, productivity metrics, published commercial info, etc.
.4 Organizational Process Assets
Historical duration information
Project Calendars
Estimating Policies
Scheduling methodology
Lessons Learned Repository

## Slide 48: 6.4.2 ESTIMATE ACTIVITY DURATION: TOOLS & TECHNIQUES
.1 Expert Judgment
  Expertise to be considered:
  Schedule development, management and control
  Estimating techniques
  Discipline or application knowledge.
.2 Analogous Estimating
  Top down approach using previous estimates based on similar project activities
  Used when there is a limited amount of information available about the project or segment of the project.
  Less costly and less accurate.
  .3 Parametric Estimating
  Multiplying the quantity of work to be performed by the productivity rate. Example: number of drawings to be produced x labor hours per drawing; or, if a resource can install 25m of cable per hour, then to install 1,000m of cable will require 40 hours of work.

## Slide 49: 6.4.2 ESTIMATE ACTIVITY DURATION: TOOLS & TECHNIQUES
.4 Three-Point Estimates
  The Weighted Average of: Most Likely (M ), Optimistic (O) Pessimistic estimates (P):
    Beta Distribution: Expected Time
Triangular Distribution Expected Time
.5 Bottom-Up Estimating
This is a method of estimating project duration or cost by aggregating the lower level components of the WBS, starting with the work packages.
Dependencies of estimated activities can effect the application and use of resources.

## Slide 50: ESTIMATING METHODS
Method | Description | Example
Analogous | A total estimate of time or cost that lacks details. Main advantage is speed of creation. Main disadvantage is lack of details on each constituent piece. | A high level estimate, created by a subject matter expert, based on experience in a past similar project.
Bottom-up | An estimate based on aggregating time and cost of constituent pieces. Main advantage is detail and accuracy. Disadvantage is that it is time consuming and expensive to create | The team creates a complete estimate from the bottom (activity level) and roll it up to a total estimate.
Parametric | Estimate based on an existing parameter. Usually created by industry standards or experience. Advantage is speed and accuracy. | A house builder estimates the total cost to build a house at $200 per square foot multiplied by the area of the house.
Computerized/ Monte Carlo | Estimate created by a computer program that simulates project outcome, to determine time, cost and resource factors. It is quick, accurate and allows “what if” scenarios. | Variables simulated could include overall time and cost estimates, as well as number of people needed to achieve project outcomes.
Adopted from PMI’s (PMBOK® Guide)

## Slide 51: 6.4.2 ESTIMATE ACTIVITY DURATION: TOOLS & TECHNIQUES
.6 Data Analysis
Alternative Analysis used to compare various scenarios to determine the optimal approach for accomplishing project work. The analysis could be applied to various levels of resource skills, or schedule compression techniques, or make/buy decisions.
Reserve Analysis used to determine the amount of contingency and management reserve needed for the project. Duration estimates may include schedule reserves.
Management reserves of schedule, are specified amount of the project budget that are withheld and controlled by management to be used for unforeseen work that is within project scope.
.7 Decision Making
Previously described.
.8 Meetings
Held by the project team to estimate activity durations. In Agile methodology, meetings are held to conduct sprint or iteration planning and discuss prioritized backlog.

## Slide 52: 6.4.3 ESTIMATE ACTIVITY DURATION: OUTPUTS
.1 Duration Estimates
  Quantitative assessments of the likely number of work periods that will be required to complete an activity
  Duration estimates should always include an indication of the range of possible results; i.E. 2 weeks +/- 2 days to indicate an activity will take at least 8 days and no more than 12 days to complete
.2 Basis of Estimates
Supporting details for duration estimates:
  Documentation of the basis
  Assumptions made
  Documentation of known constraints
  Indication of possible ranges
  Indication of confidence level
  Project Risks influencing the estimates

## Slide 53: 6.4.3 ESTIMATE ACTIVITY DURATION: OUTPUTS
Project Document Updates:
  duration estimates need to be entered on all relevant documents such as
    Activity Attributes
    Assumption Log
    Lessons Learned Resister

## Slide 54: SITUATIONAL QUESTIONS & REAL WORLD APPLICATION
The main problems to arise from the area of activity duration estimating are schedule and cost overruns resulting from inaccurate estimates. Erroneous estimates can cause time slippage, which then results into cost overruns.

## Slide 55
6.5 DEVELOP SCHEDULE
Adopted from PMI’s (PMBOK® Guide)
6.2
Define
Activities
6.4
Estimate
Activity
Duration
6.6
Control
Schedule
6.5
Develop
Schedule
6.0
Project Schedule Management
6.1
Plan Schedule
Management
6.3
Sequence
Activities

## Slide 56: 6.5 Develop Schedule
Determining start and finish dates for project activities
If the start and finish dates are not realistic, the project is unlikely to succeed
The process must often go through multiple iterations (along with the reviews and revisions of duration estimates and resource estimates) prior to determination of the project schedule
The assigned staff needs to confirm that the activity dates do not conflict with recourse calendars. The schedule is then analyzed to identify and resolve any conflicts with logical relationships, or if resource leveling is required, before the schedule is approved and baselined.
Adopted from PMI’s (PMBOK® Guide)

## Slide 57: 6.5 DEVELOP SCHEDULE DATA FLOW DIAGRAM

## Slide 58: 6.5 Develop Schedule
1 Project Baseline
2 Project Schedule
3 Schedule Data
4 Project Calendars
5 Change requests
6 Project Mgmt. plan
updates
Schedule Mgmt. Plan
Cost baseline
.7 Project Doc updates
Activity attributes
Assumption log
Duration estimates
Lessons learned reg.
Resource requirement
Risk register
1 Schedule Network
Analysis
2 CPM
3 Resource Optimization
4 Data Analysis
What-if scenario analysis
Simulation
5 Leads and Lags
6 Schedule Compression
7 PMIS
8 Agile release planning
1Project Mgmt. Plan
Schedule Mgmt. Plan
Scope Baseline
2 Project Documents
Activity Attributes
Activity List
Assumption Log
Basis of Estimates
lessons Learned Reg
Milestone List
Network Diagram
Team Asgmt.
Resource Calendar
Resource Req.
Risk Register
3 Agreements
4 Entr. Env. Factors
5 Org. Process Assets
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools &
Techniques
Outputs

## Slide 59: 6.5.1 DEVELOP SCHEDULE: INPUTS
.1 Project Management Plan
Schedule management plan identifies the scheduling method and tools, and how to calculate the schedule
Scope baseline provides deliverable details.
2 Project Documents
Activity Attributes • Milestone list
Activity List • Project Schedule network Diag.
Assumption log • Project Team Assignment
Basis of estimates • Resource Calendars
Duration estimates • Resource Requirements
Lessons Learned • Risk Register
.3 Agreements
Details provided by vendors about how will they perform contract work for the project

## Slide 60: 6.5.1 DEVELOP SCHEDULE: INPUTS
.4 Enterprise Environmental Factors
Government or industry standards
Communication Channels
.5 Organizational Process Assets
Scheduling methodologies, policies for schedule model development and maintenance
Project calendars
Two major categories which must be taken into
consideration during the development of the schedule:
    Imposed Dates which determine when a deliverable is required by the sponsor; i.e. a market window on a technology project, a court mandated completion date on an environmental project , etc.
    Key Events or Major Milestone may be requested by the sponsor, the customer or other project stakeholders, once scheduled these dates can be very difficult to move or modify

## Slide 61: 6.5.2 DEVELOP SCHEDULE: TOOLS & TECHNIQUES
.1 Schedule Network Analysis
  Involves calculating theoretical early / late start and finish dates for all project activities without regard for any resource pool limitations
  The resulting dates are not the schedule, but indicate the time periods within which the activity should be scheduled given resource limits and other known constraints
  Additional analysis includes:
    Assessing the need to aggregate schedule reserves to reduce the probability of schedule slippage when multiple activities converge to, or diverge from a single point.
    Identifying high-risk or long-lead activities on the critical path and using schedule reserves if necessary, or implementation of risk responses to mitigate risk on the critical path
  Schedule network analysis is an iterative process that is employed until a viable schedule is developed.

## Slide 62: Schedule Network Diagram and Determination of Critical Path

## Slide 63: 6.5.2 DEVELOP SCHEDULE: TOOLS & TECHNIQUES
.2 Critical Path Method (CPM)
  Calculates a single, deterministic early and late start and finish dates for each activity based on specified, sequential network logic and a single duration estimate
  The focus of CPM is on calculating float in order to determine which activities have the least scheduling flexibility
Earliest point in
time a task
can start
Earliest point
in time a
task can finish
Latest point in
time a task
can start
Latest point
in time a
task can finish

## Slide 64: Exercise

## Slide 65: PDM Exercise Answer

## Slide 66: TYPES OF FLOAT
Float: The amount of time an activity may be delayed from its early start without delaying the project finish date
  A mathematical calculation - Float can change as the project progresses and changes are made to the project plan.
Also called slack, and path float
Free Float (FF)
  The amount of time an activity can be delayed without delaying the Early Start of any immediate successor(s)
    it is designed to address the amount of pressure that one activity puts on the next
FF (x) = Successors’ Earliest ES – EF (x)
Total Float (TF)
  All potential slack time available on a path

## Slide 67: CALCULATING FLOAT
    Total Float = Late Finish - Early Finish
    Total Float = Late Start - Early Start
        Float > 0 time is available
        Float = 0 situation is critical
        Float < 0 time is behind

## Slide 68: TYPES OF FLOAT
Independent Float
  predecessors finish as late as possible
  successors start as early as possible
  very few tasks have Independent Float
Interfering Float
  difference between Total Float and Free Float

## Slide 69: THE CRITICAL PATH
In a project network diagram, the series of activities which determines the earliest completion of the project
The critical path will generally change from time to time as activities are completed ahead or behind schedule
Although normally calculated for the entire project, the critical path can be determined for a milestone or sub-project
The critical path is usually defined as those activities with float less than or equal to a specific value, often 0

## Slide 70: 6.5.2 DEVELOP SCHEDULE: TOOLS & TECHNIQUES
.3 Resource Optimization
Used to adjust the number of planned resource use to be equal to or less than the available resources.
Resource Leveling Adjusts the start and finish dates of activities to balance the demand for resources with the available supply. Leveling can be used when shared or critical resources are available only at certain times with limited quantities, or when resources are overloaded. Resource leveling may delay completion time.
Resource Smoothing Adjusts activities of a schedule model such that the requirements for resources on the project do not exceed certain predetermined resource limit. Activities are delayed only within their total and free floats. Hence the completion date is not effected.

## Slide 71: Resource Leveling Example
Before Leveling
After Leveling
Adopted from PMI’s (PMBOK® Guide)

## Slide 72: 6.5.2 DEVELOP SCHEDULE: TOOLS & TECHNIQUES
.4 Data Analysis
What-if Scenario Analysis
    The analysis is based on evaluating different scenarios, by varying the estimated durations, and introducing external factors, and analyzing the impact on the project completion.
  Simulation
  Developing models to simulate the combined effect of individual project risks to evaluate their impact on achieving project objectives. The most common method is Monte Carlo Simulation, in which risks are used to calculate possible schedule outcomes for the project. The technique is based on probability destructions for risks, and great number of trials, using random numbers to show the probability of achieving a certain target date.

## Slide 73: EXAMPLE PROBABILITY DISTRIBUTION OF A TARGET MILESTONE
In this example, there is 10% probability that the project will finish on or before the target date of May 13, 2017, while there is 90% probability of completing the project by May 28, 2017
Adopted from PMI’s (PMBOK® Guide)

## Slide 74: 6.5.2 DEVELOP SCHEDULE: TOOLS & TECHNIQUES
.5 Leads and Lags
  Are refinements applied during network analysis to develop a viable schedule, by adjusting the start time of the successor activities.
  .6 Schedule Compression
  A technique used to shorten or accelerate the schedule duration to meet imposed dates, without impacting the project scope.
  Crashing A technique used to shorten the schedule duration for the least additional cost, by adding resources, working overtime, expediting delivery for activities on the critical path. The trade-off in crashing is more money for shorter schedule
  Fast Tracking performed by modifying the sequencing of activities or phases to be done in parallel, totally or partially, instead of their normal serial sequence. The trade-off in fast-tracking is more risk for shorter schedule

## Slide 75: SCHEDULE COMPRESSION TECHNIQUES
Adopted from PMI’s (PMBOK® Guide)

## Slide 76: 6.5.2 DEVELOP SCHEDULE: TOOLS & TECHNIQUES
.7 Project Management Information Systems (PMIS)
Scheduling software programs that expedite development and revision of project schedules.
.8 Agile Release Planning
Provides a high-level time-line for the project’s releasable product, based on the vision of the product’s evolution.
The planning also determines the number of iterations in each release, and allows the team decide the development effort, and how long it will take, based on the business goals, dependencies and impediments.
The timeline provides a more easily understood project schedule, by defining which features will be completed at the end of each iteration

## Slide 77: AGILE RELEASE PLANNING
Adopted from PMI’s (PMBOK® Guide)

## Slide 78: 6.5.3 DEVELOP SCHEDULE: OUTPUTS
.1 Schedule Baseline
  Is an approved version of the project schedule model, displaying sequenced activities, start and finish dates, resources.
  The schedule baseline is a component of the Project Management Plan.
  Supporting detail provides the logic behind the decisions that created the schedule.
  The schedule baseline can be changed only through formal change control procedures, and is used as a basis for comparison to actual results.

## Slide 79: 6.5.3 DEVELOP SCHEDULE: OUTPUTS
.2 Project Schedule
Presents linked activities with planned dates, durations, milestones, and resources.
The project schedule remains preliminary, until resource assignments have been confirmed and scheduled start and finish dates established. Then the schedule is baselined.
The project schedule can be presented in several formats:
  Bar Charts Also known as Gantt Chart
  Milestone Chart identify the scheduled start or completion of major deliverables.
  Project Schedule Network Diagram commonly presented in activity-on-node (AON) format, showing activities and relationships without a time scale. When presented in time-scaled, the diagram is called logic bar chart.

## Slide 80: 6.5.3 DEVELOP SCHEDULE: OUTPUTS
Design
Code
Entries
Code
Update
Code
Query
Unit
Test
Unit
Test
Unit
Test
System
Test
Write
Manuals
6-1 6-15
6-16 7-15
6-16 6-30
6-16 6-23
6-16 7-15
7-16 7-31
7-1 7-15
6-24 7-30
8-1 8-15
Network Diagram with Scheduled Dates
Adopted from PMI’s (PMBOK® Guide)

## Slide 81: 6.5.3 DEVELOP SCHEDULE: OUTPUTS
Bar (Gantt) Chart:
Change Tire
Stop Car
Change Tire
Drive Away
M1 M7 M13 M17 M25
Legend
M - Minute
Adopted from PMI’s (PMBOK® Guide)

## Slide 82: 6.5.3 DEVELOP SCHEDULE: OUTPUTS
Change Tire
Stop Car
Change Tire
Drive Away
M1 M7 M13 M17 M25
Legend
M - Minute
Milestone Gantt
Data
Date
Adopted from PMI’s (PMBOK® Guide)

## Slide 83: 6.5.3 DEVELOP SCHEDULE: OUTPUTS
14
Time Scaled Network Diagram
1
2
1
3
5
7
6
11
9
15
A
12
13
B
D
C
E
G
F
H
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14
Adopted from PMI’s (PMBOK® Guide)

## Slide 84: 6.5.3 DEVELOP SCHEDULE: OUTPUTS
.3 Schedule Data
Collection of information for describing and controlling the schedule. The Schedule Data includes:
The schedule milestones, activities, activity attributes, assumptions and constraints.
documentation of all identified resource requirements
alternative schedules (best case/worst case)
Schedule contingency reserves or schedule risk assessments
4 Project Calendars
Identifies working days and shifts available for scheduled activities.
Identifies times when resources are not available for work.
5 Change Requests
Modifications requested to scope baseline or other components of the project plan to eliminate or reduce the probability of negative schedule variances, when approved through the integrated change control process.

## Slide 85: 6.5.3 DEVELOP SCHEDULE: OUTPUTS
.6 Project Management Plan Updates
Project Management Plan components that may require a change request include:
Schedule Management Plan to reflect changes the way the schedule was developed and will be managed
Cost Baseline approved changes to scope and resources may require updating the cost baseline
.7 Project Document Updates
The following documents may be updated
  Activity Attributes may need updating due to revised resource requirements or other revisions
  Assumption Log may need updating with changes to assumptions
  Duration Estimates updated to reflect changes in resource availability
  Lessons Learned Register updated to reflect effective schedule models
  Resource Requirement updated to reflect changes due to resource levelling
  Risk register updated to reflect risks perceived due to scheduling assumptions.

## Slide 86: SITUATIONAL QUESTIONS & REAL WORLD APPLICATION
Trying to complete a project without a an appropriate schedule often results in not knowing how far into the project activities truly are. If resources are not addressed appropriately, issues could emerge from not knowing who should do what. If duration estimates are significantly out of alignment with actual durations, problems, associated with schedule slippage would occur. Inaccurately sequencing activities can cause stoppage of work because certain activities are not completed and dependent activities cannot start.

## Slide 87
6.6 CONTROL SCHEDULE
Adopted from PMI’s (PMBOK® Guide)
6.2
Define
Activities
6.4
Estimate
Activity
Duration
6.6
Control
Schedule
6.5
Develop
Schedule
6.0
Project Schedule Management
6.1
Plan Schedule
Management
6.3
Sequence
Activities

## Slide 88: 6.6 CONTROL Schedule
Adopted from PMI’s (PMBOK® Guide)
The process is used to monitor, update and manage changes to the schedule baseline, throughout the project.
The schedule is updated to reflect the actual performance to date. Changes to the schedule baseline can be only approved through the Integrated Change Control process, which is concerned with:
  Determining current status of the schedule
  Influencing the factors that create schedule change
  Reconsidering schedule reserve
  Determining that the schedule has changed
  Managing actual changes as they occur
In Agile approach, the process is concerned with
  Comparing total delivered and accepted work against estimates of work for
  the elapsed time cycle
  Conducting retrospective reviews to correct and improve processes
  Determining the velocity of producing, validating and accepting work, per
  iteration
  Determining that the project schedule has changed
  Managing actual changes as they occur

## Slide 89: 6.6 CONTROL SCHEDULE – DATA FLOW DIAGRAM
Adopted from PMI’s (PMBOK® Guide)

## Slide 90: 6.6 CONTROL SCHEDULE
1 Work performance
Information
2 Schedule forecasts
3 Change requests
4 Project Mgmt. plan
Updates
Schedule Mgmt. plan
Schedule baseline
Cost baseline
Perf. Measurement
baseline
5 Project document
updates
Assumption log
Basis of estimates
Lessons learned Reg.
Project Schedule
Resource Calendar
Risk register
Schedule Data
1 Data Analysis
EVA
Iteration Burndown
Performance reviews
Trend analysis
Variance analysis
What – if analysis
2 CPM
.3 PMIS
4 Leads & Lags
Schedule compression
1 Project Mgmt. Plan
Schedule Mgmt. Plan
Schedule Baseline
Scope Baseline
Performance
Measurement Baseline
2 Project Documents
Lessons Learned Reg.
Project Calendars
Project Schedule
Resource Calendars
Schedule Data
3 Work Performance
Data
4 Org Process Assets
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools &
Techniques
Outputs

## Slide 91: 6.6.1 CONTROL SCHEDULE: INPUTS
.1 Project Management Plan
  Components of the overall project plan include
    Schedule Management Plan explains how the schedule will be updated, controlled and how reserve will be used.
    Schedule Baseline used as a reference to compare with actual results and determine if any corrective action is necessary
    Scope Baseline considered when monitoring and controlling schedule baseline.
    Performance Measurement Baseline compared to actual results with using Earned Value Analysis
.2 Project Documents
  Lessons learned Register to improve schedule control
  Project Calendars to show different work periods for some activities
  Project Schedule up to date display of completed and in-progress work
  Resource Calendars shows availability of teams and material
  Schedule Data reviewed and updated as a result of control process

## Slide 92: 6.6.1 CONTROL SCHEDULE: INPUTS
.3 Work Performance Data
Contains data about project activities, such as date started, actual progress, duration, percentage complete, finished dates.
.4 Organizational Process Assets
Existing schedule control policies
Schedule Control Tools
Monitoring and control methods used

## Slide 93: 6.6.2 CONTROL SCHEDULE: TOOLS & TECHNIQUES
.1 Data Analysis
Earned Value Analysis Schedule Variance SV, and Schedule Performance Index SPI are used to measure variations from baseline
Iteration Burndown Charts used to track the remaining work to complete in the backlog, after each iteration.
Adopted from PMI’s (PMBOK® Guide)

## Slide 94: 6.6.2 CONTROL SCHEDULE: TOOLS & TECHNIQUES
Performance Reviews provide information on schedule performance such as whether or not scheduled dates are being met. May also alert the project team to issues which may cause problems in the future
Trend Analysis A graphical analysis technique that examines project performance over time to determine an improving or deteriorating trend. May be also used for forecast.
Variance Analysis comparing target schedule dates with the actual/forecast dates provides useful information for corrective action
What-if-scenario analysis used to assess various scenarios guided by the output from Project Risk Management processes to align the schedule model with the approved plan

## Slide 95: 6.6.2 CONTROL SCHEDULE: TOOLS & TECHNIQUES
.2 Critical Path Method
Helps determine the schedule status, by comparing actual progress with the schedule baseline. Variances on the critical path will impact the project completion date.
.3 PMIS
Allows tracking actual dates vs. planned dates
.4 Resource Optimization
Scheduling of activities based on available resources and project time.
.5 Leads & Lags
Used during network analysis to bring the bring delayed project activities in line with the plan.
.6 Schedule Compression
Crashing and fast tracking to bring project activities that are behind, in line with the plan.

## Slide 96: 6.6.3 CONTROL SCHEDULE: OUTPUTS
.1 Work Performance Measurements
  Calculated schedule variance (SV) and Schedule Performance Index (SPI), are documented and reported for each work package
  .2 Schedule Forecasts
  Based on Earned Value performance indicators and knowledge available at the time of the forecast of expected future performance estimates (EAC) are calculated. Forecasts, are updated and issued as the project is executed.
  .3 Change Requests
As warranted by schedule variance analysis, changes would be requested to take corrective or preventive action or recommendations to reduce the probability of negative variances.

## Slide 97: 6.6.3 CONTROL SCHEDULE: OUTPUTS
.4 Project Management Plan Updates
  Changes to the schedule results into updating components of the Project Plan
  Schedule Management Plan reflect changes in schedule mgmt.
  Schedule Baseline updated for changes due to schedule compression
  Cost Baseline updated to incorporate response to approved changes
  Performance Measurement Baseline updated for approved changes
.5 Project Document Updates
  Changes to the schedule results into updating components of the Project Document:
    Assumption Log review sequencing, duration and productivity
    Basis of estimates Review of estimates may be needed
    Lessons learned register updated to document effective techniques
    Project schedule updated to reflect changes
    Resource Calendar to reflect changes to resource utilization
    Risk Register to reflect risks due to schedule compression
    Schedule Data to reflect approved modifications

## Slide 98: SITUATIONAL QUESTIONS & REAL WORLD APPLICATION
Issues that can arise in Control Schedule could be the existence of several versions of the “official” project schedule!.
Another issue could be that old data is being communicated to the team from an outdated schedule, when the team should be working to the new information.
Any schedule that should be revised or updated could be a predictor for potential issues.