## Slide 1: PMP® Exam Preparation PMP 250
Session # 3
Project Scope Management
Project Management Professional, (PMP), is a registered mark of the Project Management Institute , Inc.

## Slide 2
The contents of this lesson are based on:
A Guide to Project Management Body of Knowledge (PMBOK® Guide) Sixth Edition
Published and Owned by
Project Management Institute, PMI®
PMBOK, PMP, CAPM and PMI are registered trade marks of Project Management Institute, Inc.

## Slide 3: Learning Objectives
By the end of this session you should understand:
  How Project Scope Management Processes relate to the 5 project management process groups in a project life-cycle
  The inputs, tools and techniques and outputs for managing Project Scope processes as outlined in PMBOK® Guide

## Slide 4: “Must Knows” for Scope Management
Key Inputs, Tools & Techniques and Outputs for:
  Plan Scope Management
  Collect Requirements
  Define Scope
  Create WBS
  Validate Scope
  Control Scope
How to define and decompose scope
Importance & Characteristics of Project Scope Statement
Principles, characteristics and importance of WBS

## Slide 5: Project Scope Management
Adopted from PMI’s (PMBOK® Guide)
5.3
Define
Scope
5.4
Create
WBS
5.6
Control
Scope
5.5
Verify
Scope
5.0
Project Scope Management
5.2
Collect
Requirements
5.1
Plan Scope
Management

## Slide 6: Project Scope Management
The processes is required to ensure that the project includes all of the work required, and only the work required, to complete the project successfully
anything not explicitly included is implicitly excluded
Reference
- Kim Heldman’s book – P.44

## Slide 7: Concepts for Project Scope Management
In the Project context, scope may refer to:
Product scope - features and functions of product/service
Project scope - work that must be done to deliver a product
Important
Completion of the project scope is measured against the project plan; while
Completion of the product scope is measured against the product requirements
Completed project deliverables are formally accepted by “Validate Scope” process, with the verified deliverable from “Control Quality” as an input.
Control Quality
Validate Scope
Verified Deliverables
Completed Deliverables
Acceptance of Completed deliverables are formally signed-off and approved by an authorized stakeholder. Therefore, this stakeholder needs to get involved early in the project; i.e., during planning to provide inputs about the quality of deliverables to be used as a reference for assessing and managing the changes.
Accepted Deliverables

## Slide 8: Concepts for Project Scope Management

## Slide 9: Topics in Project Scope Management
Trends and Emerging Practices
Recognition by project managers of Business Analysts role to elicit, document and manage stakeholders’ requirements; project will have a higher likelihood of being successful if the PM and the BA collaborate to:
- Determine problems and identify
business needs
- Identify and recommend viable solutions for those needs
- Elicit, document and manage
stakeholder requirements to meet
business and project objectives
- Facilitate the successful implementation of the project result
2. Tailoring Considerations
The project manager needs to tailor the Scope Management Processes to the organizational capabilities in areas of:
  Knowledge and Requirements Management
  Validation and Control
  Development Approach
  Stability Requirements
  Governance

## Slide 10: Considerations for Agile/Adaptive Environments
In many projects, particularly in Information Technology area, the scope is not fully understood at the beginning, because requirements evolve during the project.
Adaptive (Agile) methods deliberately minimize scope definition in the early stages of the project, and focus on establishing the process progressively discovering and refining scope.
Agile methods purposefully build and review prototypes and release versions in order to refine requirements. As a results Scope is defined and refined throughout the project incrementally.

## Slide 11: 5.1 - PLAN SCOPE MANAGEMENT
Adopted from PMI’s (PMBOK® Guide)
5.3
Define
Scope
5.4
Create
WBS
5.6
Control
Scope
5.5
Verify
Scope
5.0
Project Scope Management
5.2
Collect
Requirements
5.1
Plan Scope
Management

## Slide 12: 5.1 - PLAN SCOPE MANAGEMENT
Involves the process for creating the Scope Management Plan, which is a part of the project management plan. It describes how the project scope will be defined, developed, monitored, controlled and validated. The scope management plan may identify
the tools and techniques and approaches that will be used to define the scope statement such as system engineering, value engineering,
the templates for the WBS, and
the techniques that will be used to verify scope

## Slide 13: 5.1 - PLAN SCOPE MANAGEMENT
Outputs
Scope Mgt. Plan
2. Requirements
Management Plan
Tools &
Techniques
.1 Expert Judgment
.2 Data Analysis
.2 Meetings
Inputs
.1 Project Charter
.2 Project Mgt. Plan
Quality Mgmt. Plan
Project Life Cycle
Description
Development approach
.3 Enterprise Env. Factors
.4 Organizational Process
Assets
Adopted from PMI’s (PMBOK® Guide)

## Slide 14: 5.1.1 - PLAN SCOPE MANAGEMENT: INPUTS
.1 Project Charter
The charter describes the project purpose a high level project descriptions, assumptions and requirements; needed to develop the Scope Management Plan
.2 Project Management Plan
Approved components of the Project Management Plan are used
as inputs to create the Scope Management Plan:
- Quality Management Plan: describes organization’s quality policies,
methodologies, standards, that influence how Scope will be managed.
Project Life Cycle Description: describes the series of project phases
Development Approach: specifies whether a predictive or an adaptive approach will be used.
.3 Enterprise Environmental Factors
Several environmental factors influence the creation of the Scope
Management Plan, these include but are not limited to:
Organizational Culture  Market conditions
Infrastructure  Personnel administration

## Slide 15: 5.1.1 - PLAN SCOPE MANAGEMENT: INPUTS
5 Organizational Process Assets
Organizational Process Assets that can influence this process, include:
Organizational policies and procedures
Historical information
Lessons Learned Repositories

## Slide 16: 5.1.2 - PLAN SCOPE MANAGEMENT: Tools & Techniques
.1 Expert Judgment
Expertise provided by knowledgeable and experienced parties relevant to developing the Scope Management Plan, in the following topics:
- Previous similar projects - Industry Information, or discipline or project application area
.2 Data Analysis
- Alternative Analysis - Ways of collecting requirements
- Elaborating the project - Creating & Validating the scope
and Product Scope - Controlling the scope
.3 Meetings
Attended by the project manager, the team, the sponsor, selected stakeholders to develop the scope management plan.

## Slide 17: 5.1.3 - PLAN SCOPE MANAGEMENT: OUTPUTS
.1 Scope Management Plan
Describes how the scope will be defined, developed, monitored, controlled and verified. The scope management plan is a major component of the project management plan, and includes details about the processes of:
Preparing the Scope Statement
Creating the WBS from the Scope Statement
Establishing how the baseline will be approved and maintained
Performing the formal acceptance of the project

## Slide 18: 5.1.3 - PLAN SCOPE MANAGEMENT: OUTPUTS
.2 Requirements Management Plan
This plan describes how requirements will be analyzed, documented and managed. Included as a components of the Project Management Plan, comprises as a minimum, the following components:
How the activities to achieve the requirements will be planned, tracked and reported
How Configuration Management (it is about the product) Activities will be planned, tracked and monitored, such as, how changes will be initiated, analyzed, traced, tracked, and reported; as well as authorization levels required to approve these changes.
Requirement prioritization process
Metrics that will be used and the rationale for using them
Traceability structure to reflect which requirement attributes will be captured in the traceability matrix.

## Slide 19: 5.2 - Collect Requirement
This process is for determining, documenting and managing stakeholder needs and expectations. It provides the basis for defining the product and the project scope.
The success of the project is directly impacted by an active stakeholder involvement in decomposing of needs into project and product requirements, and subsequently determining, documenting and managing the requirements.

## Slide 20: 5.2 - COLLECT REQUIREMENTS
Adopted from PMI’s (PMBOK® Guide)
5.3
Define
Scope
5.4
Create
WBS
5.6
Control
Scope
5.5
Verify
Scope
5.0
Project Scope Management
5.2
Collect
Requirements
5.1
Plan Scope
Management

## Slide 21: 5.2 - Collect Requirement
Outputs
Requirements
Documentation
2. Requirements
Traceability matrix
.1 Expert Judgment
.2 Data Gathering
Brainstorming
Interviews
Focus Groups
Questionnaires & Surveys
Benchmarking
3 Data Analysis
Document Analysis
4 Decision Making
Voting
Multi-criteria Decision
analysis
.5 Data Representation
Affinity Diagrams
Mind mapping
6 Interpersonal & Team skills
Nominal Grp Techniques
Observations/conversations
Facilitation
7 Context Diagram
8 Prototype
.1 Project Charter
.2 Project Mgmt. Plan
Scope Mgmt. Plan
Req. Mgmt. Plan
Stakeholder Mgmt. Plan
.3 Project Documents
Assumptions log
Lessons learned Reg.
Stakeholder Reg.
4 Business Documents
Business Case
5 Enterprise Env. Factors
6 Org. Process Assets
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools &
Techniques

## Slide 22: Situational Question & REAL WORLD APPLICATION
The biggest issue that arises from performing Collect Requirements inadequately is identifying incomplete or incorrect requirements. The requirements are the basis for all planning, so failure in this area leads to failure in planning . Failure in planning can results in consequences that range from budget issues to project failure.

## Slide 23: 5.2.1 - Collect Requirements : Inputs
.1 Project Charter
Describes high-level requirements that help develop detailed requirements
.2 Project Management Plan
Relevant components of the plan include:
Scope Management Plan: provides details of contents and way of development
Requirements Mgmt. Plan: information on how to collect, analyze and document requirements
Stakeholder Engagement Plan: Specifies stakeholder communication requirements and the level of stakeholder engagement in the requirements activities in order to assess and adapt the level of stakeholder participation.
.3 Project Documents
Assumption Log: identified assumption that influence requirements
Lessons Learned Register: provides information on effective requirements collection techniques, especially for projects using adaptive development methodology
Stakeholder Register: capture stakeholders’ expectations and identifies stakeholders who can provide information on requirements.

## Slide 24: 5.2.1 - Collect Requirements : Inputs
.4 Business Documents
  Business Case: describes required, desired and optional requirements for meeting business needs.
.5 Agreements contain project and product requirements
.6 Enterprise Environmental Factors
- Organizational Culture - Infrastructure
- Personnel Administration - Marketplace conditions
.7 Organizational Process Assets
- Policies and procedures
- Historical information and lessons learned repository

## Slide 25: 5.2.2 - COLLECT REQUIREMENTS: TOOLS & TECHNIQUES
.1 Expert Judgment
Expertise in the following areas is required for the process:
Business Analysis - Requirements Collection - Requirements Analysis
Documentation - Req. in previous projects - Diagraming techniques
Facilitation - Conflict Management
.2 Data Gathering
Techniques used for the process include:
Brainstorming: generate and collect multiple ideas about project requirements
Interviews: directly eliciting requirements from stakeholders
Focus Groups: moderated brainstorming of prequalified stakeholders or SME’s to learn about their expectations and attitudes about a proposed product or service.
Questionnaires and Surveys: most appropriate for a quick turnaround of replies to preset questions distributed to varied audiences.
Benchmarking: comparing actual or planned products/services to those of comparable organizations, to identify best practices, generate improvement ideas

## Slide 26: 5.2.2 - COLLECT REQUIREMENTS: TOOLS & TECHNIQUES
.3 Data Analysis
Document Analysis is used to elicit requirements by analyzing existing documentation and identifying information relevant to requirements. These documents include:
- Agreements - Business Plans - Business rules repositories
- Business Processes - Current process flows - Marketing Literature
- Problem/Issue logs - Policies & Procedures - Regulatory documentation
- Requests for Proposals - Use Cases
.4 Decision Making
Voting: Used to generate, classify, and prioritize requirements. The technique includes: Unanimity, Majority, and Plurality voting.
Autocratic Decision Making: an individual decides for the group
Multi-criteria decision Analysis: uses a matrix to establish multiple criteria
.5 Data Presentation
Affinity Diagrams: Classifies large number of ideas into groups for analysis
Mind Mapping: consolidates ideas created through individual brainstorming sessions into a single map to reflect commonality and differences to understand and generate new ideas

## Slide 27: 5.2.2 - COLLECT REQUIREMENTS: TOOLS & TECHNIQUES
.6 Interpersonal and Team Skills
The skills that can be used for the process include:
Nominal Group Techniques: Involves brainstorming with a voting process used to rank useful ideas for further brainstorming or prioritization.
Observation/Conversation involves viewing individuals as they perform their tasks, or carry out processes. The procedure is helpful when requirements cannot be articulated in detail.
Facilitation: using focused sessions that involve key stakeholders to define product requirements. Workshops can be used to quickly define cross-functional requirements and reconcile differences due to their interactive nature. Facilitation is used in the following situations:
- Joint application design /development (JAD) ; sessions bring business SME’s and software development team together to collect requirements and improve the development process.
- Quality Function Requirement (QFD): the process collects customer needs, objectively sorts and prioritizes them, and sets goals for achieving them
- User Stories: short textual descriptions of required functionality, that specify the stakeholder’s role, (1) who benefits from the feature (role), (2) what the stakeholder needs to accomplish (goal), (3) the benefits to the stakeholder (motivation)

## Slide 28: 5.2.2 - COLLECT REQUIREMENTS: TOOLS & TECHNIQUES
.7 Context Diagram
Visually depict the product scope, by showing the business system, and
how other systems (or people) interact with it.
PMBOK® Guide 6th Fig 5-6

## Slide 29: 5.2.2 - COLLECT REQUIREMENTS: TOOLS & TECHNIQUES
.8 Prototypes
Prototype is a model of an actual product before building it.
Allows experimentation with a mock-up product instead of discussions and abstract presentations of the requirements.
Prototyping supports the concept of progressive elaboration. In each iteration, users experiment the model of the product and provide feedback that is taken to revise and improve the prototype. When the product requirements are sufficiently understood, the design or build the final product is undertaken.
Storyboarding is a prototyping technique used in variety of projects. In Agile software development projects, storyboards use mock-ups to show navigation paths through web pages, screens and other user interfaces.

## Slide 30: 5.2.3 COLLECT REQUIREMENTS: OUTPUTS
.1 Requirements Documentation:
Describes how individual requirements meet the business needs for the project. Requirements progressively become more detailed as more information is known.
Baselined requirements need to be unambiguous, measurable, traceable, complete, consistent and acceptable to stakeholders.
Requirements can include, but are not limited to:
Business requirements: high-level organizational needs, Project justification
Stakeholder requirements: reporting and communication requirements
Solution requirements: functional, technological, support, training, quality, and reporting requirements
Transition and readiness requirements data conversion, Training
Project Requirements: actions, processes, conditions the project is to meet
Quality requirements: conditions or criteria needed to validate the successful completion of the project

## Slide 31: 5.2.3 COLLECT REQUIREMENTS: OUTPUTS
.2 Requirements Traceability Matrix
This tool, relates product requirements from their origin to the deliverables that fulfill them. The tool helps ensure that each requirement adds value to the business and project objectives.
The tool also helps track the requirements and their associated attributes, throughout the project life cycle, to ensure that requirements approved in the requirements documentation are actually delivered at the end of the project.
An example of the matrix and its contents is shown in the figure below*.
*PMBOK® Guide 6th Fig 5-7

## Slide 32: 5.3 DEFINE SCOPE
Adopted from PMI’s (PMBOK® Guide)
5.3
Define
Scope
5.4
Create
WBS
5.6
Control
Scope
5.5
Verify
Scope
5.0
Project Scope Management
5.2
Collect
Requirements
5.1
Plan Scope
Management

## Slide 33
In this process a detailed description of the project and product is developed.
The process also defines the boundaries of the product, or service or the result, along with the acceptance criteria.
The final project requirements are selected from the Requirements Documentation developed during the Collect Requirements process.
The Scope Statement is created by this process. This document is defined and described in greater details as more information is known about the project.
Define Scope can be a highly iterative process. In adaptive methodologies, only a high-level vision is initially developed for the overall project. But the detail scope is progressively elaborated one iteration at a time, and the detailed planning for the next iteration is carried out as the work progresses on the current project scope and deliverables.
5.3 Define Scope
Adopted from PMI’s (PMBOK® Guide)

## Slide 34: 5.3 Define Scope – DATA FLOW DIAGRAM
Adopted from PMI’s (PMBOK® Guide)

## Slide 35
5.3 - DEFINE SCOPE
Outputs
.1 Project scope
Statement
.2 Project document
updates
Assumption Log
Requirements Doc.
Req. Traceability
matrix
Stakeholder Reg.
.1 Expert Judgment
.2 Data Analysis
Alternative Analysis
.3 Decision Making
Multi-criteria decision
analysis
.4 Interpersonal & Team
Skills
Facilitation
.5 Product Analysis
Inputs
.1 Project charter
.2 Project Mgmt. Plan
Scope Mgmt. Plan
.3 Project Documents
Assumption Log
Req. Documentation
Risk Register
.4 Enterprise Env. Factors
.5 Organizational process
assets
Adopted from PMI’s (PMBOK® Guide)
Tools &
Techniques

## Slide 36: 5.3.1 - DEFINE SCOPE: INPUTS
.1 Project Charter
Provides a high level project description and characteristics of its deliverables. The charter also contains project approval requirements, and is used as a basis for the detailed project scope statement.
.2 Project Management Plan
Includes the Project Scope Statement, which describes how the scope will be defined, validated and controlled.
.3 Project Documents
Documents that can be considered as inputs to this process:
Assumption Log identifies all assumptions and constraints about the project.
Requirements Documentation requirements that will be included in the scope
Risk Register may indicate how the product or project scope may mitigate risk
.4 Enterprise Environmental Factors
Organizational Culture - Infrastructure
- Personnel Administration - Marketplace conditions
.5 Organizational Process Assets
Policies, procedures, and templates for Scope Statement
Previous project files
Lessons learned from previous projects or phases

## Slide 37: 5.3.2 - DEFINE SCOPE: TOOLS AND TECHNIQUES
.1 Expert Judgement
  Each application area expert develops portions of the detailed project scope statement.
.2 Data Analysis
Alternatives Analysis is a tool used to evaluate ways to meet requirements
.3 Decision Making
Multi-criteria decision making technique uses a matrix to provide systematic analytical approach for establishing criteria, such as requirements, schedule, budget, and resources, in order to refine the scope.
.4 Interpersonal and Team Skills
Facilitation is a tool used to reach a common understanding with a cross-section of stakeholders, about project deliverables and boundaries.

## Slide 38: 5.3.2 - DEFINE SCOPE: TOOLS AND TECHNIQUES
.5 Product analysis
  Developing a better understanding of the project product that helps translate project goals into realistic deliverables. The process uses techniques such as:
        Product Breakdown
        Requirements Analysis
        System Engineering
        System Analysis
        Value Analysis
        Value Engineering

## Slide 39: 5.3.3 - DEFINE SCOPE: OUTPUTS
.1 Project Scope Statement
This document describes in detail the project scope, major deliverables, assumptions and constraints, for the purpose of providing a common understanding among the stakeholders. I also contains explicit exclusions that can assist in managing stakeholder expectations.
The Scope Statement enables the project team perform detailed planning, guides execution work, and provides the baseline for evaluating whether change requests or additional work are within the project boundaries.
The document directly or by reference to other documents provides details of:
  Product Scope Description The characteristics of the product or service are progressively elaborated in this description
  Deliverables are unique and verifiable products or services or a capability along with their ancillary results or documentation that are required to be produced by the project
  Acceptance Criteria a set of conditions to be met for acceptance of deliverables
  Product Exclusions Explicit statements of out-of-scope products or services.

## Slide 40: 5.2.3 - DEFINE SCOPE: OUTPUTS
*PMBOK® Guide 6th Table 5-1

## Slide 41: 5.3.3 - DEFINE SCOPE: OUTPUTS
.1 Scope statement includes: (cont’d)
    Product acceptance criteria
    Project constraints
    Project assumptions
    Initial project organization
    Initial defined risks
    Schedule milestones
    Fund limitations
    Cost estimate
    Configuration management requirements
    Project specification
    Approved requirements

## Slide 42: 5.3.3 - DEFINE SCOPE: OUTPUTS
.2 Project Document Updates
    Changes to the Project Management Plan or its component plans must be reflected in the Project Documents by updating all relevant documents, such as:
      Assumption Log
      Requirements Documentation
      Stakeholder Register
      Requirements Traceability Matrix

## Slide 43: SITUATIONAL QUESTION & REAL WORLD APPLICATION
The primary potential problem in Define Scope is the later discovery of needed items that were not known or mentioned in the Scope Statement. Planning and therefore accounting for these items, would be missed. This problem can cause serious variances with scope, schedule, or cost.

## Slide 44: 5.4 - CREATE WBS
Adopted from PMI’s (PMBOK® Guide)
5.3
Define
Scope
5.4
Create
WBS
5.6
Control
Scope
5.5
Verify
Scope
5.0
Project Scope Management
5.2
Collect
Requirements
5.1
Plan Scope
Management

## Slide 45: 5.4 - Create WBS
Dividing the major project deliverables into smaller, more manageable components in order to:
  improve accuracy of cost, time, and resource estimates
  define a baseline for performance measurement and control
  facilitate clear responsibility assignments
The lowest level of WBS is the work package, used to group activities where work is scheduled and estimated monitored and controlled.
Adopted from PMI’s (PMBOK® Guide)

## Slide 46: 5.4 - Create WBS
Outputs
.1 Scope baseline
.2 Project documents
updates
Assumption Log
Requirements
Documentation
Tools &
Techniques
.1 Expert Judgment
.2 Decomposition
Input
.1 Project Mgmt. Plan
Scope Mgt. Plan
.2 Project Documents
Project Scope
Statement
Requirements
Documentation
.3 Enterprise Env.
Factors
.4 Organizational
process assets
Adopted from PMI’s (PMBOK® Guide)

## Slide 47: 5.4.1 - CREATE WBS: INPUTS
.1 Project Management Plan:
Includes the Scope Management Plan which specifies how to create, approve and maintain the WBS
.2 Project Documents:
Project Scope Statement describes the work that will be performed by the project, and the work that is excluded.
Requirements Documentation describes how individual requirements meet the business needs.
.3 Enterprise Environmental Factors
Industry-specific WBS standards relevant to the nature of the project, may serve as references.
.4 Organizational Process Assets
Policies, procedures and WBS Templates
Previous project files and lessons learned.

## Slide 48: 5.4.2 - CREATE WBS: TOOLS AND TECHNIQUES
.1 Expert Judgment
Expertise of individuals or groups in the process should be considered
.2 Decomposition
The technique of dividing and subdividing the project and deliverables into smaller parts for better management. The work package is the lowest level of the WBS, for which cost and duration could be estimated and managed. Decomposition involves the following steps:
Identifying and analyzing deliverables and related work
Structuring the WBS
Decomposing the WBS’s upper levels into lower level components
Assigning identification codes to each WBS component
Verifying the appropriateness of the deliverables’ decomposition

## Slide 49: 5.4.2 - CREATE WBS: TOOLS AND TECHNIQUES
The WBS can be represented in a number of ways, such as:
Using phases of the project life cycle as the 2nd level, with the project
and product deliverables at the 3rd level
Major deliverables at the 2nd level
Incorporating subcomponents which may be developed outside the
providers

## Slide 50: 5.4.2 CREATE WBS: TOOLS AND TECHNIQUES
Decomposition of each work deliverable, requires subdividing the upper-levels into its most fundamental components.
  In Agile approach, epics can be decomposed into
user stories, and user stories into tasks.
The correctness of the decomposition is verified
when the lower-levels of the WBS components
are those that are necessary and sufficient to
complete the corresponding higher-level
deliverables.
The WBS represents all product and project work
including project management work. The total
of the work at the lowest levels should roll up
to the higher levels, so that nothing is left out
and no extra work is performed.
Epic
Epic
Feature
Feature
Feature
User Story
User Story
User Story
Task 1
Task 2
REQUIREMENTS HIERARCHY

## Slide 51: 5.4.2 - CREATE WBS: TOOLS & TECHNIQUES
A Control Account is a management control point where scope, budget and schedule are integrated and compared to the earned value of performance. A control account has two or more work packages.
A Planning Package is a WBS component, below the control account, and above the work package, with known work content but without schedule activities.
Adopted from PMI’s PMBOK® Guide

## Slide 52: 5.4.2 - CREATE WBS: Tools & Techniques
Decomposition steps
    a) Identify the major elements of the project - define in terms of how the project will actually be managed
    b) Decide if adequate cost and duration estimates can be developed at this level of detail for each element - based on tangible, verifiable results that facilitate performance measurement
    c) If NOT adequate - identify constituent elements, then retest for adequacy (step b.)
    d) If adequate - verify the correctness of the decomposition:
      items necessary and sufficient for completion?
      each item clearly and completely defined?
      each item can be scheduled? Budgeted? Assigned?
    If not correct, redefine/revise, then re-verify

## Slide 53: 5.4.3 - CREATE WBS: OUTPUTS
.1 Scope Baseline
The approved scope baseline, is a component of project management plan that provides details of the planned scope for the project. It can be changed only through formal change control procedures. The scope baseline includes:
  Project Scope Statement includes the description of the project scope, the major deliverables, assumptions, and constraints
  WBS a hierarchical decomposition of the total scope of work, to be performed to accomplish the project objectives and create the required deliverables.
  Work Package the lowest level of the WBS with a unique identifier. These identifiers provide a structure for rolling up costs, schedules, and resource information to the control account level.
  Planning Package A WBS component below a control account and above a work package.

## Slide 54: 5.4.3 - CREATE WBS: OUTPUT
WBS Dictionary
  The WBS dictionary provides supporting detail that is not practical to include in the graphical format of the WBS. It can include items such as:
  Code of account identifier + Quality requirements
  Scheduled milestones + Contract information
  Cost estimates + Responsible organization
  Technical references + Resources required
  description of work + Acceptance criteria
  Associated schedule activities + Agreement Information
  .2 Project Document Update
  Assumption Log updated with additional assumptions
  Requirements Documentation to include approved changes

## Slide 55: SITUATIONAL QUESTION & REAL WORLD APPLICATION
A common mistake many project managers make is failing to conduct appropriate decomposition of the project. This mistake typically leads to scope creep and estimating inaccuracies. A project management plan can not be better than its WBS decomposition

## Slide 56: 5.5 - VALIDATE SCOPE
Adopted from PMI’s (PMBOK® Guide)
5.3
Define
Scope
5.4
Create
WBS
5.6
Control
Scope
5.5
Validate
Scope
5.0
Project Scope Management
5.2
Collect
Requirements
5.1
Plan Scope
Management

## Slide 57: 5.5 - VALIDATE SCOPE
Outputs
.1 Accepted
Deliverables
.2 Changes requests
.3Work performance
Information
.4 Project document
updates
Tools &
Techniques
.1 Inspection
.2 Group decision
making techniques
Inputs
.1 Project Mgmt Plan
.2 Requirements
documentation
.3 Requirements
traceability matrix
.4 Verified deliverables
.5 Work Performance Data
Adopted from PMI’s (PMBOK® Guide)

## Slide 58: 5.5 - VALIDATE SCOPE
The main goal of Validate Scope is to secure formal acceptance of the project scope at logical intervals during the project and/or when the entire project is completed.
Scope Validation is primarily concerned with the acceptance of the deliverables, while quality control is primarily concerned with the correctness of the deliverables and meeting the quality specifications.
The verified deliverables obtained from Control Quality are reviewed with the customer to ensure they are satisfactorily completed, and have received formal acceptance by the customer. The scope baseline, as well as work performance data are the basis for performing the validation and the final acceptance.
Scope Validation should be performed even if the project is
canceled to document the degree to which the project was completed
Adopted from PMI’s (PMBOK® Guide)

## Slide 59: 5.5 VLIDATE SCOPE – DATA FLOW DIAGRAM
Adopted from PMI’s (PMBOK® Guide)

## Slide 60: 5.5.1 – VALIDATE SCOPE: INPUTS
.1 Project Management Plan
The components of the plan that influence this process include:
Scope Management Plan specifies how the final acceptance will be done
Requirements Management Plan describes how the requirements are validated
Scope Baseline is compared with the actual results to determine if the deliverables are acceptable or a change, corrective action or preventive action is necessary
  .2 Project Documents
  Documents that influence this process include:
  Lessons Learned Register may provide information on how to improve validation
  Quality Reports are reviewed before prior to product acceptance, to identify quality assurance issues managed or escalated, improvements, findings from Control Quality
  Requirements Traceability Matrix
  Used to align requirements to stakeholders needs, as the requirements are validated for completion and acceptance
.3 Verified Deliverables
  Project deliverables that are completed and checked for correctness through the Control Quality process
  .4 Work Performance Data
  Shows the degree of compliance with requirements, number and severity of non-conformances, or the number of validation cycles performed

## Slide 61: 5.5.2 - VALIDATE SCOPE: TOOLS & TECHNIQUES
.1 Inspection
  activities such as measuring, examining, testing undertaken to determine whether results conform to requirements and the product acceptance criteria
  variously called reviews, product reviews, audits, walk – through
.2 Decision Making
Used to reach a conclusion after the validation is performed. Voting is commonly used.

## Slide 62: 5.5.3 - VALIDATE SCOPE: OUTPUTS
.1 Accepted Deliverables
Products, services or results that meet the acceptance criteria are formally signed off and approved by the customer or sponsor.
documentation that the client /sponsor has accepted the product of the project or phase.
.2 Work Performance Information
Includes information about project progress, provides percentages completed for project deliverables, or those which have been accepted.
.3 Change Requests
Change requests are documents issued for repairing defects of completed deliverables that have nor been formally accepted. The request should also describe the reasons for non-acceptance.

## Slide 63: 5.5.3 - VALIDATE SCOPE: OUTPUTS
.4 Project Documents Update
Validating Scope may require updates to the following documents:
Lessons Learned Register to capture challenges encountered, how they could have been avoided, as well as what worked well.
Requirements Documentation to capture actual validation results, especially when the actuals are better than the original requirements.
Requirement Traceability Matrix to capture the methods used.

## Slide 64: SITUATIONAL QUESTION & REAL WORLD APPLICATION
If scope validation is not successfully completed, the project manager can encounter difficulties in obtaining client signoff on deliverables and possibly the entire project.

## Slide 65: 5.6 - CONTROL SCOPE
Adopted from PMI’s (PMBOK® Guide)
5.3
Define
Scope
5.4
Create
WBS
5.6
Control
Scope
5.5
Validate
Scope
5.0
Project Scope Management
5.2
Collect
Requirements
5.1
Plan Scope
Management

## Slide 66: 5.6 - CONTROL SCOPE
This process is concerned with:
Monitoring the status of the project and product scope and managing changes to the scope baseline, as a result of inevitable changes to the project and product
Ensures that the requested changes and recommended corrective actions are processed through the integrated change control. The process is also used to manage actual changes as they occur.
Uncontrolled expansion to product or project scope without adjustment to time, cost and resources is refereed to as Scope Creep
Adopted from PMI’s (PMBOK® Guide)

## Slide 67: 5.6 - CONTROL SCOPE - DATA FLOW DIAGRAM
Adopted from PMI’s (PMBOK® Guide)

## Slide 68: 5.6 - CONTROL SCOPE
Outputs
.1 Work performance
Information
.2 Change requests
.3 Project management
plan updates
Scope Mgmt. Plan
Scope Baseline
Schedule Baseline
Cost Baseline
Performance
Measurement Baseline
.4 Project documents
updates
Lessons Learned Register
Requirements Doc.
Req. Traceability Matrix
Tools &
Techniques
.1 Data Analysis
Variance Analysis
Trend Analysis
.1 Project Mgmt. Plan
Scope Management Plan
Requirements Mgmt. Plan
Change Mgmt. Plan
Configuration Mgmt. Plan
Scope Baseline
Performance Measurement
Baseline
.2 Project Documents
Lessons Learned Register
Requirement Docs.
Req. Traceability Matrix
.3 Work performance Data
.4 Organizational process
assets
Adopted from PMI’s (PMBOK® Guide)
Inputs

## Slide 69: 5.6.1 - CONTROL SCOPE: INPUTS
.1 Project Management Plan
The following information contained in the components of the plan, are inputs to control scope:
  Scope Management Plan: to determine how the scope will be managed and controlled
  Requirements Management Plan: describes how the project requirements will be managed.
  Change Management Plan: defines the process of managing change.
  Configuration Management Plan: defines those item that are configurable, those items that require change control, and the processes for controlling changes to such items.
  Scope Baseline provides the reference to determine if actual results need corrective or preventive actions
  Performance measurement Baseline Actual results are compared to performance measurement baseline, in earned value management, to determine if a change, corrective or preventive action is necessary.

## Slide 70: 5.6.1 - CONTROL SCOPE: INPUTS
.2 Project Documents
Lessons Learned register helps apply lessons learned in earlier
phases, to later phases of the project
Requirements Documentation: is used to compare and identify variances between the work performed and other project results to planned requirement.
Requirement Traceability Matrix: is used to see how requirements meet or need to be adjusted to align with stakeholders’ needs and expectations.
.3 Work Performance Data
Includes the number of change requests received, accepted, number of deliverables verified, validated and completed
.4 Organizational Process Assets
describes existing formal and informal policies, procedures and guidelines for scope control
Motoring and reporting methods and templates

## Slide 71: 5.6.2 - CONTROL SCOPE: TOOLS & TECHNIQUES
.1 Data Analysis
Variance Analysis
  To assess the magnitude of variations with baselines
  To identify cause of variance
  And decide if corrective action is necessary
Trend Analysis examines project performance over time to determine if performance is improving or deteriorating.

## Slide 72: 5.6.3 - CONTROL SCOPE: OUTPUTS
.1 Work Performance Information
are created to provide to stakeholder measurement data and project information related to work actually done and intended to be done versus the scope management plan. Includes categories of changes received, variances and their causes.
.2 Change Requests
Analysis of project performance may result into change requests; Results can include preventive or corrective action or defect repair as needed.
.3 Project Management Plan Updates
Scope changes impact the following components of project management plan
- Scope Management Plan - Cost Baseline
- Scope Baseline - Performance Measurement - Schedule Baseline Baseline
.4 Project Documents Update
- Lessons Learned Register - Requirements Documentation
- Requirements Traceability Matrix