## Slide 1: PMP® Exam Preparation PMP250
Session # 9
Project Risk Management
Project Management Professional, (PMP), is a registered mark of the Project Management Institute , Inc.

## Slide 2
The contents of this lesson are based on:
A Guide to Project Management Body of Knowledge (PMBOK® Guide) Sixth Edition
Published and Owned by
Project Management Institute, PMI®
PMBOK, PMP, CAPM and PMI are registered trade marks of Project Management Institute, Inc.

## Slide 3: Learning Objectives
By the end of this session, you should understand:
  The processes of planning risk management identification, analysis, planning implementation and monitoring of risk responses.
  The objective of the knowledge area is to increase the probability and/or impact of positive risks, and to decrease the probability and/or impact of negative risks, by deploying the seven risk management processes described in the PMBOK® Guide, 6th Edition

## Slide 4: PROJECT RISK MANAGEMENT
11.0
Project Risk
Management
11.1
Plan Risk
Management
11.2
Identify
Risks
11.3
Perform
Qualitative
Risk Analysis
11.4
Perform
Quantitative
Risk Analysis
11.5
Plan Risk
Responses
11.7
Monitor
Risks
11.6
Implement
Risk
Responses
.

## Slide 5: RISK MANAGEMENT PROCESS INTERACTION

## Slide 6: KEY CONCEPTS FOR PROJECT RISK MANAGEMENT
All projects are risky. Organizations undertaking various projects, intentionally take-on project risk in order to create greater benefits, by understanding, controlling and mitigating the negative impacts of risk.
There are two levels of risks in projects:
  Individual Project risks: an uncertain event that, that if occurs, has a positive or negative effect on one or more objectives of the project.
  Overall Project Risk: arises from all sources of uncertainty, including individual risks, that impact the project as a whole.
Both types of risks can be positive (opportunities) or negative (threats). Project risk management aims to exploit opportunities, and avoid threats.
Risk management processes should be performed iteratively, as risks will continue to emerge throughout the project life-cycle.
To manage risks effectively, the project team must know what level of risk exposure is acceptable to the organization.

## Slide 7: TRENDS & EMERGING PRACTICES
Trends and emerging practices for a broad approach to Project Risk Management include considering:
  Non-Event Risks. There are two main types. Usually addressed by Monte Carlo simulation techniques.
    Variability risk: uncertainty about some key characteristic of a planned event; e.g., productivity being above or below target.
    Ambiguity: uncertainty about what might happen in the future; e.g., imperfect knowledge or understanding of requirements might impact project’s objectives.
  Project Resilience. Developed to tackle emergent risks (unknown – unknown risks that are recognized only after they occur). Resilience requires each project to have:
    Right level of contingency for emergent risks
    Process flexibility and strong change management
    Empowered and trusted project team with clear objectives
    Frequent reviews
    Clear inputs from stakeholders regarding acceptable adjustments to project scope or strategy.
  Integrated Risk Management. A coordinated approach to enterprise-wide risk management ensures risks are managed at all levels; (i.e., portfolio – program – project levels).

## Slide 8: TAILORING CONSIDERATIONS
Based on the unique attributes of a project, the Risk Management approach is required to be tailored for:
  Project Size; i.e., budget, duration, scope, team size.
  Project Complexity; level of innovation, new technology, commercial arrangements, external dependencies.
  Project Importance; strategic importance because the project aims to produce breakthrough opportunities, or addresses major innovations.
  Development Approach. Sequential risk management processes for waterfall projects; Incremental risk management (each iteration) fro adaptive projects.
CONSIDERATIONS FOR AGILE
Adaptive (Agile) approaches to project management, consider risk when selecting the contents of each iteration, by identifying, analyzing and managing processes performed during each iteration.

## Slide 9: PROJECT RISK MANAGEMENT “MUST KNOWS”
Key Inputs, Tools & Techniques, Outputs for Plan Risk Management, Identify Risks, Perform Qualitative Analysis, Perform Quantitative Analysis, Plan Risk Responses, Implement Risk Response, Monitor Risks.
Risk Breakdown Structure and risk categorization
Concepts and differences of project risk and business risk
Benefits and risks of contracting
Characteristics of a Risk Seeker, Risk Averse Person and a risk - neutral person
Risk Register, its purpose and what it contains
Risk reviews and risk triggers
Probability as it relates to risk management
How to calculate EMV
Monte Carlo Simulation in relation to risk management
Management Reserves and Contingency Reserves
What are workarounds in relation to risk response management
Characteristics of risk response plan and related strategies

## Slide 10: 11.1 PLAN Risk Management
Adopted from PMI’s (PMBOK® Guide)
11.0
Project Risk
Management
11.1
Plan Risk
Management
11.2
Identify
Risks
11.3
Perform
Qualitative
Risk Analysis
11.4
Perform
Quantitative
Risk Analysis
11.5
Plan Risk
Responses
11.7
Monitor
Risks
11.6
Implement
Risk
Responses
.

## Slide 11: 11.1 - Plan Risk Management
Deciding how to approach and conduct the risk management activities for a project.
The plan ensures that the degree, type and visibility of risk management are commensurate with the risks and the importance of the project to the organization and stakeholders.
The Risk Management Plan should be completed early in the project, and revisited at each phase, or whenever a significant change in the scope occurs.
The plan requires modification, should a subsequent review indicates that that the risk management plan is ineffective.
Adopted from PMI’s (PMBOK® Guide)

## Slide 12: 11.1 PLAN RISK MANAGEMENT DATA FLOW DIAGRAM
Adopted from PMBOK® 6th Edition, Fig 11.3 page 402

## Slide 13: 11.1 – Plan Risk Management
1 Risk management plan
1 Expert Judgment
2 Data Analysis
Stakeholder Analysis
3 Meetings
1 Project Charter
2 Project Mgmt. Plan
All components
3 Project Documents
Stakeholder Register
4 Enterprise Env. Factors
5 Org Process Assets
Inputs
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 14: 11.1 PLAN RISK MANAGEMENT: INPUTS
.1 Project Charter
  Provides various inputs relevant to risk management, such as high-level project uncertainties, decryptions, requirements
.2 Project Management Plan
  Provides the baseline or the current state of other areas including scope, schedule, and cost, that the Risk Management plan needs to be consistent with.
.3 Project Documents
Stakeholder Register. Contains details relevant to project stakeholders, their roles and attitudes towards risk.

## Slide 15: 11.1 PLAN RISK MANAGEMENT: INPUTS
.4 Enterprise Environmental Factors
  Attitudes and tolerance towards risk
  Different organizations and different individuals have different tolerances for risk.:
    $500,000 is negligible for some or livelihood for others
    Possible 15% cost overrun is high risk for one and low risk for another
    The decision maker can be risk seeking, risk neutral or risk averse
.5 Organizational Process Assets
  Predefined approaches to risk analysis and response
  Risk categories
  Common definitions, terms, templates, roles & responsibilities and authority levels
  Lessons learned
  Stakeholder registers

## Slide 16: 11.1.2 PLAN RISK MANAGEMENT: TOOLS & TECHNIQUES
.1 Expert Judgment
Judgment and expertise in organization’s approach to risk management, tailoring the approach to a project’s need, and identification of risks likely to be encountered in the project.
.2 Data Analysis
Analytical Techniques
Used to define the overall risk context of the project in terms of stakeholder risk attitudes and project complexity.
The assessment is helps the project team allocate appropriate resources and focus the risk management activities
.3 Meetings
  Meetings to develop the risk management plan should include:
    Project manager and team, Anyone in the organization responsible for managing risk planning and execution activities Other key stakeholders, Others as needed
  These meetings should define:
    Risk cost elements and schedule activities for inclusion in budget
    Risk contingency reserve application approaches
    Risk management responsibilities
    Establish risk categories and risk levels,
    Establish probability and impact matrix for the project

## Slide 17: 11.1.3 PLAN RISK MANAGEMENT: OUTPUTS
.1 Risk Management Plan
  Strategy:
  Describes how the approach will be structured and performed during the project life cycle:
    Risk identification
    Qualitative risk analysis
    Quantitative risk analysis
    Risk response planning
    Implementing Risk Responses
    Monitoring Risk
  Methodology:
    Defines the approaches, tools and data sources that may be used
    Different types of assessments can depend upon the project stage, amount of information available, and flexibility remaining in risk management

## Slide 18: 11.1.3 PLAN RISK MANAGEMENT: OUTPUTS
.1 Risk management plan (continued)
  Roles and Responsibilities:
    Defines the roles & responsibilities for the risk plan activities:
      Team lead
      Team support
      Team Membership
  Funding:
    Establishes the funds needed risk management, including contingency and management reserves.
  Timing:
    Defines when the risk management process will be performed throughout the project life cycle

## Slide 19: 11.1.3 PLAN RISK MANAGEMENT: OUTPUTS
.1 Risk Management Plan (continued)
  Risk Categories
    Risk Breakdown Structure (RBS): A hierarchical display of risk categories, identifying risk to a consistent level of detail.
Risk Management Planning
Adopted from PMI’s PMBOK® Guide

## Slide 20
PMBOK® 6th Edition Fig. 11.4 page 406

## Slide 21: 11.1.3 PLAN Risk Management: outputs
.1 Risk management plan (continued)
  Stakeholder risk appetite
    The risk appetite of each key stakeholder, for project risks, should be recorded in The Risk Management Plan.
    Risk appetites, expressed in measureable thresholds around each project objective (i.e., cost, schedule, scope, quality), determine the acceptable level of overall project risk exposure, and define the probability and impacts rubric, to be used when assessing individual project risks.
  Definition of Risk Probability and Impact:
    Provides a scale for risk levels based on probability and impact definitions.
    The definitions reflect the risk appetite of the organization and key stakeholders of the project.
    The number of levels is determined by the degree of detail required by the risk management processes. Varies between three to five levels.

## Slide 22: PROBABILITY-IMPACT DEFINITION EXAMPLE
PMBOK® 6th Edition Table. 1114 page 407

## Slide 23: 11.1.3 Plan Risk Management: outputs
.1 Risk Management Plan (continued)
  Probability and impact matrix
    A relative scale representing relative probability values like 0.1, 0.3, 0.5,0.7,0.9
    The impact scale reflects the significance of risk impact, on each project objective if a risk occurs.
    Risks or opportunities are prioritized according to their potential implications for meeting the project’s objectives
    See the probability and Impact matrix

## Slide 24: Probability/Impact Matrix
Adopted from PMI’s PMBOK® 6th Edition Fig. 11.5 Page 408

## Slide 25: 11.1.3 Plan Risk Management: outputs
.1 Risk management plan (continued)
  Reporting Formats:
    Describes content and format of the risk register and the risk report.
  Tracking:
    Documents how risk activities will be recorded for:
      Risk Management Processes
      Auditing

## Slide 26: 11.2 - IDENTIFY RISKS
Adopted from PMI’s (PMBOK® Guide)
11.0
Project Risk
Management
11.1
Plan Risk
Management
11.2
Identify
Risks
11.3
Perform
Qualitative
Risk Analysis
11.4
Perform
Quantitative
Risk Analysis
11.5
Plan Risk
Responses
11.7
Monitor
Risks
11.6
Implement
Risk
Responses
.

## Slide 27: 11.2 – IDENTIFY RISKS
Risk identification involves:
  Determining which risks might affect the project and documenting their characteristics
  Participants in risk identification include:
    Project team
    Risk management team
    Subject matter experts from within the company
    End users
    Customers
    Other project managers
    Stakeholders
    Outside experts
Risk identification:
    Is an iterative process
    May be performed with different participants at different times
    Analyses may be performed with persons not involved in the project to achieve an unbiased analysis.

## Slide 28: 11.2 - IDENTIFY RISKS DATA FLOW DIAGRAM
Adopted from PMI’s PMBOK® Guide 6th Edition Fig.11.7 page410

## Slide 29: 11.2 – Identify RISKS
1 Risk Register
2 Risk Report
3 Project Documents
Update
Assumption log
Issue Log
Lessons learned register
1 Expert Judgment
2 Data Gathering
Brainstorming
Checklists
Interviews
3 Data Analysis
Root cause analysis
Assumptions & Constraints Analysis
SWOT Analysis
Document Analysis
4 Interpersonal & Team Skills
Facilitation
5 Prompt Lists
6 Meetings
1 Project Mgmt. Plan
Requirement Mgmt. plan
Schedule Mgmt. plan
Cost Mgmt. plan
Quality Mgmt. Plan
Resource Mgmt. plan
Risk Mgmt. plan
Scope Baseline
Schedule Baseline
Cost Baseline
.2 Project Documents
Assumption log
Cost Estimates
Duration Estimates
Issue log
Lessons learned Register
Requirements documents
Resource requirements
Stakeholder register
3 Agreements
4 Procurement Documents
5 Ent. Env. Factors
6 Org. Proc. Assets
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)
INPUTS

## Slide 30: 11.2.1 IDENTIFY RISKS: INPUTS
.1 Project Management Plan
Requirements Management Plan. May indicate risky project objectives
Schedule Management Plan. May identify risky areas
Cost Management Plan. May identify risky areas
Quality Management Plan. May identify risky areas, or assumptions made that may give rise to risks.
Resource Management Plan. May identify risky areas, or assumptions made that may give rise to risks.
Risk Management Plan. Provides information on risk related roles & responsibilities, contingency reserves in the budget and the schedule, expressed in the RBS.
Scope Baseline. Includes the WBS that may be used for risk identification.
Schedule Baseline. May be reviewed to identify uncertain activities or risky assumptions
Cost Baseline. May be reviewed to identify uncertain costs of funding, or risky assumptions

## Slide 31: 11.2.1 IDENTIFY RISKS: INPUTS
.2 Project Documents
Assumption Log. Assumption and constraints may give rise to project risks.
Cost Estimates. Current cost estimates may be insufficient to perform the activities, hence could pose a project risk
Duration Estimates. Current duration estimates may be insufficient to perform the activities, hence pose a project risk
Issue Log. Recoded issues may give rise to project risks.
Lessons Learned Register. Risks identified in previous projects may recur in the current project.
Requirements Documentation. Some requirements may give rise to project risks
Resource Requirements. Current estimates may be insufficient for the project, hence could pose a risk.
Stakeholder Register. Indicates participants in risk identification process, and those available to act as risk owners.

## Slide 32: 11.2.1 IDENTIFY RISKS: INPUTS
.3 Agreements
Agreements to procure goods and services may pose some threads to the project in terms of: milestone dates, contract type, acceptance criteria, wards and penalties.
.4 Procurement Documents
Procured goods and services from outside sources may carry ambiguities. As these documents are updated throughout the project, they should be reviewed for risks.
.5 Enterprise Environmental Factors
Commercial risk databases - Academic studies
Benchmarking results - Industry studies of projects
.6 Organizational Process Assets
Actual project data - Org. control processes
Risk statement formats - Checklists

## Slide 33: 11.2.2 - IDENTIFY RISKS: TOOLS AND TECHNIQUES
.1 Expert Judgment
Experts with relevant experience with similar projects should be consulted and requested to suggest possible risks based on their previous experience. Inputs from experts should be taken into consideration.
.2 Document Gathering
  Brainstorming:
    Facilitator states ground rules, participants identify risks (e.g. round-robin) and facilitator pad-boards them
    Facilitator distributes list of unique risks for review and validation with team/other risk management participants
    Iterative process until a thoroughly exhaustive list of project risks is obtained.
    Delphi Technique:
      Method of reaching consensus of opinion among experts:
      Panel of project risk experts are identified
      Anonymous participation
      Facilitator uses a structured questionnaire to solicit ideas about project risk from panel
      Responses are consolidated and submitted to panel for further comments
      Process repeated until consensus reached

## Slide 34: 11.2.2 - IDENTIFY RISKS: TOOLS AND TECHNIQUES
Checklists
Based on historical information, acquired knowledge of the team and other sources (Example below)
Risk Description | Technical | Scope | Time | Cost | Quality | Org. | External
New, unproven technology R&D work | x |  | x | x |  |  | 
Existing manufacturing process capability is borderline for the product of the project | x |  |  |  | x |  | 
Customer requirements not clearly defined |  | x | x | x | x |  | 
Environmental concerns, lobbyists |  |  |  |  |  |  | x
Conflicts with other projects for resources |  |  | x |  |  | x | 
Adopted from PMI’s PMBOK® Guide

## Slide 35: 11.2.2 - IDENTIFY RISKS: TOOLS AND TECHNIQUES
.2 Data Gathering (continued)
Interviews
    Interviews with subject matter experts
    Interviews with experienced project managers
    Interviewees identify risks based on their experience
    Project information provided by the PM (e.g. scope statement, WBS, assumptions, constraints, etc.)
    Other sources they find useful
.3 Data Analysis
  Root Cause Analysis
A technique used to identify a problem, uncover the underlying causes, and develop a preventive action.
  Assumptions and constraints analysis
  All projects are based on assumptions/ hypotheses, scenarios
    Identify and list assumptions and constraints
    Explore the validity of assumption and constraints to identify those that pose a risk
    Inaccurate, inconsistent, and incomplete assumption may pose a risk.
    Removed or relaxed constraints, may give rise to opportunities.

## Slide 36: 11.2.2 - IDENTIFY RISKS: TOOLS AND TECHNIQUES
.3 Data Analysis (continued)
SWOT Analysis
    The technique examines the project from Strengths, Weaknesses,
    (of the organization), Opportunities and Threats perspective.
    Identifies any opportunities for the project that may arise from strengths, and any threats resulting from weaknesses.
  Document Analysis
A structured review of project plans, assumptions, constraints, previous project files, contracts, agreements, and technical documents. Uncertainty, ambiguity or inconsistency in these documents may be indicators of project risk.
.4 Interpersonal and Team Skills
    Facilitation improves the effectiveness of risk identification techniques, by helping participants to remain focused, follow procedures, overcome bias, and resolve disagreements.

## Slide 37: 11.2.2 IDENTIFY RISKS Tools and Techniques
.5 Prompt Lists
    The list provides a directory of predetermined risk categories, to be used as a framework to aid the team generate ideas.
    The lowest level of RBS can be used as a prompt level for individual risks.
    Some strategic frameworks are more suitable for identifying overall project risk, such as:
      PESTLE (Political, Economic, Social, Technological, Legal,
      Environmental)
      TECOP (Technical, Environmental, Commercial, Political)
      VUCA (Volatility, Uncertainty, Complexity, Ambiguity)
.6 Meetings
    Often called risk workshops, facilitated by an experienced facilitator, and the participation of the right stakeholders, to perform some form of brainstorming for identifying project risks.

## Slide 38: Risk Techniques applicable to Project Phases
G = Good Relatively strong application F = Fair Average Application
P = Poor Average application N = None Not applicable
Adopted from PMI’s PMBOK® Guide

## Slide 39: Risk Techniques applicable to Project Phases
G = Good Relatively strong application F = Fair Average Application
P = Poor Average application N = None Not applicable
Adopted from PMI’s PMBOK® Guide

## Slide 40: 11.2.2 - IDENTIFY RISKS: Tools and Techniques
System or Process Flow Chart
Adopted from PMI’s PMBOK® Guide

## Slide 41: 11.2.2 - IDENTIFY RISKS: Tools and Techniques
Cause-and-Effect Diagram
Time
Personnel
Measurement
Machine
Energy
Environment
Method
Material
Risk
Effect
Cause
Adopted from PMI’s PMBOK® Guide

## Slide 42: 11.2.2 - IDENTIFY RISKS: Tools and Techniques
Influence Diagram
Product
Price
Market
Size
Market
Share
Unit Sales
Revenues
Costs
Marketing
Budget
Profit
Adopted from PMI’s PMBOK® Guide

## Slide 43: 11.2.3 - IDENTIFY RISKS: OUTPUTS
.1 Risk Register
  Records the details of identified individual risks.
  The results of qualitative risk Analysis, planning and implementing risk responses, and monitoring risks, are progressively recorded in the risk register, as these processes are conducted throughout the project.
  Upon completion of Identify Risks process, the register may include:
    List of identified risks as individual risks, given unique identifiers, leading to effects.
    Potential Risk Owners. To be confirmed during Qualitative risk analysis process.
    List of Potential Risk Responses. To be confirmed during Plan Risk Responses process.
    Additional data for each risk may be recorded, such as:
    - Risk Title - Risk Category - Current Status
    - Cause(s) - Effect(s) - Triggers
    - WBS Ref. - Timing - Deadline for action

## Slide 44: 11.2.3 - IDENTIFY RISKS: OUTPUTS
.1 Risk Report
  Provides information about the overall project risk, along with a summary of identifies individual risks.
  The report is completed progressively as the risk management processes are conducted throughout the project. Information included in the report may contain:
    Sources of overall project risk, with indication of most important drivers.
    Summary information of identified individual risks, with information regarding the number of threats and opportunities, categories, metrics, trends, etc.
.2 Project Documents Updates
Assumption Log. Updated to reflect new assumption made and constraints identified during the process.
Issue Log. Updated to reflect new issues identified.
Lessons Learned Register. Updated to capture information or techniques that were effective during the Identify Risks process.

## Slide 45: 11.3 - PERFORM Qualitative Risk Analysis
Adopted from PMI’s (PMBOK® Guide)
11.0
Project Risk
Management
11.1
Plan Risk
Management
11.2
Identify
Risks
11.3
Perform
Qualitative
Risk Analysis
11.4
Perform
Quantitative
Risk Analysis
11.5
Plan Risk
Responses
11.7
Monitor
Risks
11.6
Implement
Risk
Responses
.

## Slide 46: 11.3 – PERFORM QUALITATIVE RISK ANALYSIS
Qualitative risk analysis is the process of prioritizing individual project risks by assessing the impact and likelihood of identified risks.
  Prioritizes risks according to their impact on project objectives
  Determines the importance of addressing and planning responses for individual risks, and their time-criticality
  Evaluates the quality of the risk information available
  Ensures that the probability and consequences of the risks are evaluated using available information and established qualitative-analysis methods and tools.
  Trends in repeated qualitative analysis can indicate the need for more (or less) risk management actions.
  Should be revisited throughout the project life cycle to stay current with changes in the project’s risks
  Can lead to further analysis in quantitative risk analysis or directly to risk response planning.
  Preferably, an experienced facilitator should be used to support the process, to reduce subjective assessments based on the team’s perception of risk.
  In Agile approaches, the Perform Qualitative Risk Analysis process is conducted before the start of each iteration.
Adopted from PMI’s (PMBOK® Guide)

## Slide 47: 11.3 PERFOEM QAULITATIVE RISK ANALYSIS DATA FLOW DIAGRAM
Adopted from PMBOK® Guide 6th Edition Fig.11.9 page 420

## Slide 48: 11.3 – PERFORM QUALITATIVE RISK ANALYSIS
1 Risk Register Updates
Assumption Log
Issue Log
Risk Register
Risk Report
1 Expert Judgment
2 Data Gathering
Interviews
3 Data Analysis
Risk Data Quality Assessment
Risk Prob. Impact Assessment
Assessment of other risk parameters
4 Interpersonal & Team Skills
Facilitation
5 Risk Categorization
6 Data Representation
Probability/Impact Matrix
Hierarchical Charts
7 Meetings
1Project Mgmt. Plan
Risk Mgmt Plan
2Project Documents
Assumption Log
Risk Register
Stakeholder Reg.
3 Ent. Env. Factors
4 Org. Proc. Assets
Inputs
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 49: 11.3.1 – PERFORM QUALITATIVE RISK ANALYSIS INPUTS
.1 Project Management Plan
Risk Management Plan. Is the rulebook for risk management.
  Provides information about how to perform qualitative risk analysis, roles & responsibilities for conducting risk management, budgets, schedule of activities for risk management, risk categories, definitions of probability and impact matrix, stakeholders’ risk tolerances.
.2 Project Documents
Assumption Log. Used to inform the priority of assessing individual risks based on their impact on the project.
Risk Register. Contains information about individual risks, potential responses, root causes, and risk categorization.
Stakeholder Register. Includes stakeholder details, who may assume risk owner roles.
.3 Enterprise Environmental Factors
Industry studies, publications and databases addressing risks of similar projects
.4 Organizational Process Assets
Information from similar projects

## Slide 50: 11.3.2 – PERFORM QUALITATIVE ANALYSIS: TOOLS & TECHNIQUES
.1 Expert Judgment
  Knowledge and training in qualities risk analysis experience in previous projects.
  Obtained through facilitated workshops or interviews.
  .2 Data Gathering
  Formal or semi-formal interviews conducted in with confidentiality and trust, can be used to gather information from knowledgeable people to assess the probability and impact if individual risks.
.3 Data Analysis
Risk Data Quality Assessment. May be assessed via questionnaires to measure stakeholders’ perceptions about the completeness, objectivity and relevancy and timeliness of the data.
Risk Probability and Impact Assessment. Can be assessed in interviews or meetings with knowledgeable persons.

## Slide 51: 11.3.2 – PERFORM QUALITATIVE ANALYSIS: TOOLS & TECHNIQUES
.3 Data Analysis (cont’d)
Assessment of other risk parameters.
  Urgency - Proximity of impact - Dormancy (delay) of impact
  Manageability - Controllability - Detectability
  Connectivity - Strategic impact - Propinquity (significance)
.4 Interpersonal and Team Skills
  Skilled facilitation can help participants focus on the task of risk analysis, follow the methods and techniques, to reach consensus on assessment of individual risk probability, impact, and identification of responses.
  .5 Risk Categorization
  Risks categorization helps development of more effective responses, by addressing groups of related risks.
  Categorization could be by source, or impacted area of the project or other areas such as budget, project phase, common root causes.

## Slide 52: 11.3.2 – PERFORM QUALITATIVE ANALYSIS: TOOLS & TECHNIQUES
.3 Data Analysis (cont’d)
Assessment of other risk parameters.
  Urgency - Proximity of impact - Dormancy (delay) of impact
  Manageability - Controllability - Detectability
  Connectivity - Strategic impact - Propinquity (significance)
.4 Interpersonal and Team Skills
  Skilled facilitation can help participants focus on the task of risk analysis, follow the methods and techniques, to reach consensus on assessment of individual risk probability, impact, and identification of responses.
  .5 Risk Categorization
  Risks categorization helps development of more effective responses, by addressing groups of related risks.
  Categorization could be by source, or impacted area of the project or other areas such as budget, project phase, common root causes.

## Slide 53: 11.3.2 – PERFORM QUALITATIVE RISK ANALYSIS TOOLS & TECHNIQUES
Probability/Impact Matrix:
  Risk probability scales:
    A scale ranging from 0.0 (no probability) to 1.0 (certain).
    Assessing risk probability may be difficult as expert judgment is used, often without the benefit of historical data
    Ordinal scales, representing probability values from very unlikely to almost certain may be used
    Cardinal scales, assigning specific probabilities (such as, .1 / .3 / .5 / .7 / .9) may also be used.
  Risk impact scales:
    Reflect the severity of the risk on project objectives
    Impact scales can be either cardinal or ordinal:
      Ordinal – very low, low, medium, high, very high impact
      Cardinal – scales assigning specific values or weights to the impact, and may be linear or non-linear:
        An example of a linear scale is .1 / .3 / .5 / .7 / or .9
        An example of a non-linear scale is .05 / .1 / .2 / .4 / .8

## Slide 54: Probability/Impact Matrix
 |  | Impact |  |  |  | 
 |  | Trivial | Minor | Moderate | Major | Extreme
Probability | Rare | Low | Low | Low | Medium | Medium
 | Unlikely | Low | Low | Medium | Medium | Medium
 | Moderate | Low | Medium | Medium | Medium | High
 | Likely | Medium | Medium | Medium | High | High
 | Very Likely | Medium | Medium | High | High | High

## Slide 55: Probability/Impact Matrix
Adopted from PMI’s PMBOK® Guide

## Slide 56: 11.3.2 – PERFORM QUALITATIVE RISK ANALYSIS TOOLS & TECHNIQUES
.7 Meetings
Dedicated risk workshops to discuss identified individual risks, in terms of previously assessed occurrence probability, impact, categorization and prioritization.
A risk owner responsible for planning the appropriate response and report progress, is allocated to each individual risk.
The meeting confirms previously assessed probabilities and impacts, an may also identify additional risks during the discussions.

## Slide 57: 11.3.3 PERFORM QUALITATIVE RISK ANALYSIS: OUTPUTS
.1 Project Documents Updates
    Assumption Log. Updated to record new assumptions made or new constraints identified, or existing ones changed, by the Qualitative Risk Analysis process
    Issue Log. Updated to record new issues encountered
    Risk Register. Updated with new information generated during the process, regarding probability, impact, priority level, owner, urgency, category of individual risks.
    Risk report. Updated to reflect the most important individual risks, as well as a summary conclusion and a prioritized list of all identified risks

## Slide 58: 11.4 - PERFORM Quantitative Risk Analysis
Adopted from PMI’s (PMBOK® Guide)
11.0
Project Risk
Management
11.1
Plan Risk
Management
11.2
Identify
Risks
11.3
Perform
Qualitative
Risk Analysis
11.4
Perform
Quantitative
Risk Analysis
11.5
Plan Risk
Responses
11.7
Monitor
Risks
11.6
Implement
Risk
Responses
.

## Slide 59: 11.4 – PERFORM QUANTITATIVE RISK ANALYSIS
The quantitative risk analysis process aims to numerically analyze the probability of each risk’s occurrence and consequences on project objectives, as well as the analysis of overall project risk.
Risks that are higher in probability and impact are more likely to be evaluated by quantitative analysis
Quantitative risk analysis uses simulation and decision analysis to:
  Determine the probability of achieving a specific project objective
  Quantify the risk exposure for the entire project
  Determine the amount of cost and schedule contingency reserves that may be needed to ensure project completion
  Identify risks requiring the most attention, Identify realistic and achievable costs, schedule or scope targets.
Adopted from PMI’s (PMBOK® Guide)

## Slide 60: 11.4 PERFORM QUANTITATIVE RISK ANALYSIS DATA FLOW DIAGRAM
PMBOK® 6th Ed. Fig 11.12 page 429

## Slide 61: 11.4 – PERFORM QUANTITATIVE RISK ANALYSIS
1 Project Documents updates
  Risk Report
1 Expert Judgment
2 Data Gathering
Interviews
3 Interpersonal & Team
Skills
Facilitation
4 Representation of
Uncertainty
5 Data Analysis
Simulations
Sensitivity Analysis
Decision Tree Analysis
Influence Diagrams
1 Risk Mgmt. Plan
Risk Mgmt. Plan
Scope Baseline
Schedule Baseline
Cost Baseline
2 Project Documents
Assumption Log
Basis of Estimates
Cost Estimates
Cost forecasts
Duration Estimates
Milestone list
Resource requirements
Risk Register
Risk report
Schedule forecasts
3 Ent. Env. Factors
4 Org. Proc. Assets
Inputs
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 62: 11.4.1 – PERFORM QUANTITATIVE RISK ANALYSIS: INPUTS
.1 Project Management Plan
  Risk Management Plan. Provides information regarding the methodology for performing Quantitative Risk Analysis, if considered necessary, for the complexity of the project.
  Scope Baseline. A starting point from which the impact of the individual risks are evaluated.
  Schedule Baseline. A starting point from which the impact of the individual risks are evaluated.
  Cost Baseline. A starting point from which the impact of the individual risks are evaluated.
  .2 Project Documents
  Assumption Log. Assumptions may pose a source of risk to project objectives. The effect of constraints may also be analyzed during the process.
  Basis of Estimates. Provides information on the estimates assumed accuracy, classification, methodology and source, which may pose risks.
  Cost Estimates. Provide information on cost variability.
  Cost forecasts. Estimates for ETC, BAC, TCPI, may be compared to the results of quantitative cost risk analysis to determine the confidence level associated with achieving these targets.
  Duration Estimates. Starting point to evaluate schedule variability.
.

## Slide 63: 11.4.1 – PERFORM QUANTITATIVE RISK ANALYSIS: INPUTS
.2 Project Documents (cont`d)
  Milestone List. Provides a reference against which the quantitative risk analysis results are compared.
  Resource Requirements. Starting point to evaluate variability
  Risk Register. Provides individual risks as inputs to the process.
  Risk Report. Describes sources and the status of overall project risks
  Schedule Forecasts. Quantitative risk analysis results are compared with estimated forecasts, to determine the confidence level of attaining these forecasts.
  .3 Enterprise Environmental Factors
  The factors that can influence the process include, industry studies of similar projects, published material, commercial risk databases, and checklists.
  .4 Organizational Process Assets
  Information from similar projects.
.

## Slide 64: 11.4.2 - PERFORM QUANTITATIVE RISK ANALYSIS: TOOLS & TECHNIQUES
.1 Expert Judgment
The process requires expertise in the areas of:
Creating the numerical inputs to the process from risk information
Risk modeling techniques, and selecting the appropriate tools
Interpreting the results of the analysis
.2 Data Gathering
Interviews with experts may be used to analyze individual risks.
.3 Interpersonal and Team Skills
Facilitation of dedicated workshops for risk analysis.
.4 Representation of Uncertainty
The uncertainty in project duration, cost, or resource requirements, can be analyzed using appropriate probability distributions, or alternatively, risks may be included in a probabilistic model as branches.

## Slide 65: 11.4.2 - PERFORM QUANTITATIVE RISK ANALYSIS: TOOLS & TECHNIQUES
.4 Representation of Uncertainty (cont`d)
Simulation A quantitative risk analysis model that simulates the combined effect of individual project risks to evaluate their potential impact on achieving the project objectives.
The technique most often used is the Monte Carlo simulation, using computer software.
When running the model for cost risk, the input to the model would be the distribution of the cost estimates; while schedule risk simulation would input the distribution of duration estimates, and use the network diagram to calculate the project completion time. An integrated quantitative cost-schedule risk analysis would use both inputs.
The model uses the values of the input variable, chosen randomly within a specified probability distribution, and the output is calculated. This is repeated for several thousand times, to generate a histogram presenting the number of times a particular outcome results. A cumulative probability distribution (S-curve) could also be generated.
It is also possible to conduct a criticality analysis by calculating a criticality index, that determines which elements of the risk model have the greatest effect on the project

## Slide 66: 11.4.2 - PERFORM QUANTITATIVE RISK ANALYSIS: TOOLS & TECHNIQUES
Monte Carlo Simulation (cont’d)
Consider an estimate of a project using three-point estimate as follows:
  Best-case estimate – 110 days
  Most likely estimate – 150 days
  Worst-case estimate – 205 days
Using Monte Carlo Simulation, the chances of completing project in 110 days is 1% and the chances of completing in 170 days is 55%
  Given the data, it looks much more likely that the project will end up taking anywhere between 190 and 230 days
Adopted from PMI’s (PMBOK® Guide 6th Ed. Fig 11.14)
Project Duration | % of Simulation Runs | Project Duration | % of Simulation Runs | Project Duration | % of Simulation Runs
110 | 1% | 140 | 18% | 170 | 55%
190 | 88% | 210 | 98% | 230 | 100%

## Slide 67: 11.4.2 - PERFORM QUANTITATIVE RISK ANALYSIS: TOOLS & TECHNIQUES
Sensitivity Analysis
Is a technique to analyze and compare the potential impacts of identified risks
One typical display of sensitivity analysis is “Tornado” diagram, in which risks are represented by horizontal bars; the longest and uppermost bar represents the greatest risk, and progressively shorter bars represent lower risks
Adopted from PMI’s (PMBOK® Guide 6th Ed. Fig 11.14)

## Slide 68: 11.4.2 - Perform Quantitative Risk Analysis: Tools & Techniques
.2 Quantitative Risk Analysis & Modeling Techniques
  Sensitivity Analysis
    Helps determine which risks have the most potential impact on the project
    Examines the extent to which the uncertainty of each project element affects the objective being examined, when all other uncertain elements are held at their baseline values.
    Tornado charts are often used to visually depict the above sensitivities.
  Expected Monetary Value Analysis
    The expected value of a risk = Risk probability x Risk value
      Risk probability = Estimate of the probability (%) that a risk event will occur
      Risk value = Estimate of the gain or loss ($) that will be incurred if the risk event does occur

## Slide 69: 11.4.2 - Perform Quantitative Risk Analysis: Tools & Techniques
  Decision Tree Analysis
    It incorporates probabilities of risks and the costs or rewards of each logical path.
    A decision tree is a diagram that describes a decision under consideration, along with the implications of choosing one or another of the available alternatives
    Solving the decision tree indicates which decision yields the greatest expected value.
    The decision to upgrade an existing plant to produce a new product line is expected to cost the company $50M. To build a new plan will cost $120M. There is a 60% probability that the demand for the product will be strong and a 40% probability that it will be weak. If a new plant is built and demand is strong the payoff is estimated to be $200 M. If the demand is weak, the payoff is estimated to be $90 million. If the plant is upgraded and demand is strong the payoff is estimated to be $120M. If demand is weak, demand is estimated to be $60M. What is the best decision?

## Slide 70: Decision Tree Analysis

## Slide 71: 11.4.2 - PERFORM QUANTITATIVE RISK ANALYSIS: TOOLS & TECHNIQUES
.4 Representation of Uncertainty (cont`d)
Influence Diagrams. A decision making model that represents a project or situations within the project as a set of entities, outcomes or influences, along with the relationships and effects between them.
Uncertain elements in the model are represented by their probability distributions.
The influence diagram is evaluated using a simulation technique such as Monte Carlo, to indicate the element with the greatest influence on the outcome.

## Slide 72: 11.4.3 PERFORM QUANTITATIVE ANALYSIS OUTPUTS
.1 Project Documents Updates
  Assessment of overall project risk exposure. Reflected by:
    The probability of the project success, given identified individual risks
    The range of possible project outcomes based on the degree of variability remaining within the project.
  Detailed Probabilistic Analysis of the project. The key outputs of the quantitative analysis may include
    The amount of contingency reserve needed for a desired confidence level
    Identification of the individual risks with the greatest effect on the critical path of the project
    Major drivers of overall project risk with the greatest influence.
  Prioritized list of individual project risks
    The risks that pose the greatest threat or opportunity to the project
  Trends in quantitative risk analysis results
    As the analysis is repeated during the project life cycle, a trend of results may become apparent.
  Recommended Risk Response. These will form inputs to plan risk responses process.

## Slide 73: 11.5 - Plan Risk Responses
Adopted from PMI’s (PMBOK® Guide)
11.0
Project Risk
Management
11.1
Plan Risk
Management
11.2
Identify
Risks
11.3
Perform
Qualitative
Risk Analysis
11.4
Perform
Quantitative
Risk Analysis
11.5
Plan Risk
Responses
11.7
Monitor
Risks
11.6
Implement
Risk
Responses
.

## Slide 74: 11.5 - Plan Risk Responses
Developing options, selecting strategies and agreeing on actions to:
  Enhance opportunities
  Reduce threats to project objectives.
It includes identification and assignment of individuals or groups to take responsibility for implementing each agreed upon risk response
Ensures that identified risks are properly addressed.
Risk response planning must be:
  Appropriate to the severity of the risk
  Cost effective
  Timely
  Realistic within the project context.

## Slide 75: 11.5 - Plan Risk Responses
A risk may be:
  Unrecognized, unmanaged or ignored (by default)
  Recognized but no action taken
  Avoided by taking appropriate steps
  Reduced by an alternative approach
  Shared with others, e.g. joint venture
  Transferred to others through contract or insurance
  Retained and absorbed by prudent allowances
  Handled by a combination of the above
Adopted from PMI’s (PMBOK® Guide)

## Slide 76: 11.5 PLAN RISK RESPONSES DATA FLOW DIAGRAM
Adopted from PMI’s (PMBOK® Guide 6th Ed. Fig 11.17 Page 438)

## Slide 77: 11.5 - Plan Risk Responses
1Change Requests
2Project Mgmt Plan Updates
Schedule Mgmt. Plan
Cost Mgmt. Plan
Quality Mgmt. plan
Resource Mgmt. Plan
Procurement Mgmt. plan
Scope Baseline
Schedule Baseline
Cost Baseline
3 Project Document Updates
Assumption log
Cost forecasts
Lessons learned reg.
Project Schedule
Project Team Assignmt.
Risk Register
Risk report
1 Expert judgment
2 Data Gathering
Interviews
3 Interpersonal &
team skills
Facilitation
4 Strategies for Threats
5 Strategies for
Opportunities
6 Contingent response
strategies
7Strategies for overall
project risk
8 Data Analysis
Alternative analysis
Cost/Benefit Analysis
9 Decision Making
Multi-criteria decision analysis
1Project Mgmt. Plan
Resource Mgmt. Plan
Risk Mgmt. Plan
Cost Baseline
2Project Documents
Lessons Learned Reg.
Project Schedule
Project team assign's
Resource Calendars
Risk register
Risk report
Stakeholder register
3Ent. Env. Facotrs
4Org. Proc. Assets
Inputs
Tools &
Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 78: 11.5.1 - PLAN RISK RESPONSES: INPUTS
.1 Project Management Plan
  Resource Management Plan. Needed to coordinate response owners with other resources.
  Risk Management Plan. Provides information about risk thresholds and roles & responsibilities.
  Cost Baseline. Provides information about contingency funds.
  .2 Project Documents
  Lessons learned register. Describes effective risk responses learned earlier.
  Project Schedule. Helps determine scheduling risk response activities.
  Project Team Assignments. Shows resources that can be assigned to risk response activities.
  Resource Calendars. Provides resource availability information.

## Slide 79: 11.5.1 - PLAN RISK RESPONSES: INPUTS
.2 Project Documents (cont’d)
Risk Register
  List of prioritized risks (from qualitative risk analysis)
  Risk ranking of the project (qualitative risk analysis)
  Prioritized list of quantified risks (quantitative risk analysis)
  Probabilistic analysis of the project (quantitative risk analysis – simulations)
  Probability of achieving cost and time objectives (quantitative risk analysis – simulations)
  List of potential responses
      Potential response actions identified during the risk identification process
  Risk thresholds
    - Level of risk acceptable to the organization influences risk response planning (risk management planning)
  Risk owners
      List of stakeholder-owners of risk responses
  Common risk causes
    Multiple risks may be driven by a common cause
    Opportunity to mitigate multiple risks with one generic response
  Trends in qualitative and quantitative risk analysis
      Such trends can make risk response or further analysis more or less urgent

## Slide 80: 11.5.1 - PLAN RISK RESPONSES: INPUTS
.2 Project Documents (cont’d)
Risk Report. Helps select the response strategy by describing the current overall risk exposure of the project. Also lists individual risks in order of their severity and distribution.
Stakeholder register. Identifies potential, risk owners.
.3 Enterprise Environmental Factors
The main factor that influences response planning is stakeholders’ threshold and appetite for risk.
.4 Organizational Process Assets
The assets that may influence risk response planning include:
Response Planning Templates, previous risk registers and reports
Historical databases
Lessons learned from previous projects

## Slide 81: 11.5.2 -PLAN RISK RESPONSES: TOOLS & TECHNIQUES
.1 Expert Judgment
Expertise is required to develop strategies for threats, opportunities, contingencies and overall risk response.
.2 Data Gathering
Structured or semi-structured interviews with risk owners and other stakeholders.
.3 Interpersonal and Team Skills
A skilled facilitator can effectively help risk owners understand, identify, compare alternative possible risk responses, and choose appropriate risk response strategies.
.4 Strategies for Threats
Five strategies may be considered for dealing with threats:
Escalate
Avoid
Transfer
Mitigate
Accept

## Slide 82
Escalate
When a threat is outside the scope of the project or exceed the authority of the project manager, the most appropriate response is to escalate it above the project to a program or portfolio level that matches the level of impacted objectives, should the threat occur.
Avoid
  The threat would be eliminated by changing the project plan, thus protecting project objectives from the risk’s impact
  Examples of risk avoidance may require:
    Clarifying requirements
    Obtaining additional information
    Improving communication
    Scope reduction to avoid high risk activities
    Adding resources or time
    Adopting a familiar approach rather than an innovative one
    Avoiding the use of an unfamiliar subcontractor

## Slide 83: 11.5.2 -PLAN RISK RESPONSES: TOOLS & TECHNIQUES
  Transfer
    Shifting ownership of the consequence of a risk and risk response to a third party
    Makes another party responsible for the risk, but does not eliminate it
    Examples:
      Insurance
        Direct property (Resulting from auto collision, to equipment in transit, materials theft, contractor’s property)
        Indirect property (Cost of removing debris, equipment replacement, rental income loss, business interruption, liquidated damages)
      Performance bonds
      Warranties / guarantees
      Contracts / Procurement

## Slide 84: Insurable Risks
  Insurable Risk can be further divided into:
    Direct property
    Destruction of property (fire, flood, storm)
    Indirect property
    Expenses incurred following a damage or destruction (renting temporary accommodation, loss due to business interruption)
    Liability
    Lawsuit for bodily injury, personal injury or property damage
    Personnel
    Injuries to employees
    Legal liability
    Public bodily harm, property damage or personal injury from negligence of others, damage to project due to design errors, execution error, lack of performance
    Personnel-related
      Employee injury, cost to replace employee, business loss

## Slide 85: 11.5.2 -PLAN RISK RESPONSES: TOOLS & TECHNIQUES
Transfer (Continued)
  Procurement Examples
    Acquiring goods & services from outside the project organization to avoid production risks
    Sub-contracting new technology to more experienced organization
  Contract Examples
    Fixed price transfer(s) risky for the vendor
    Cost-reimbursable, leaves more risk with the purchaser.
      The selection of the right form of contract requires:
        The identification of specific risks,
        Determination of how they should be shared between the contracting parties, and
        The insertion of clear language in the contract documents

## Slide 86: 11.5.2 -PLAN RISK RESPONSES: TOOLS & TECHNIQUES
  Mitigate
    Reduces the probability and/or impact of an adverse risk event to an acceptable threshold.
    Mitigation costs should be appropriate to the probability and impact of the risk.
    Early risk mitigation action is more effective than as remedial action after the fact.
    Includes adopting new courses of action to reduce problems, such as:
      Adopting simpler processes
      Additional testing
      Prototyping
      Choosing a more stable vendor/sub-contractor
      Adding additional resources, time or funding
      Designing redundancy into a system/sub-system
  Accept
    When it is not possible to eliminate the risk from the project
    When there is no possible change to the project plan to deal with the risk
    No other suitable response strategy is feasible
    Most common positive response is to: establish a contingency reserve: time, money, resources

## Slide 87: 11.5.2 -PLAN RISK RESPONSES: TOOLS & TECHNIQUES
.5 Strategies for Positive Risks or Opportunities
  Escalate
  When an opportunity is outside the scope of the project or exceed the authority of the project manager, the most appropriate response is to escalate it above the project to a program or portfolio level that matches the level of effected objectives.
  Exploit
    Seeks to eliminate uncertainty associated with upside uncertainty by making the opportunity happen
    Assigning more talented resources to reduce completion time
    Provide better quality than originally planned
  Share
    Allocating ownership to a 3rd party, best suited to capture the opportunity for the benefit of the project
    Examples: risk-sharing partnerships, teams, joint ventures etc. established for the purpose of managing the opportunity
  Enhance
    Increase the “size” of an opportunity by increasing the probability or positive impact
  Accept
    Willingness to take advantage of it if it occurs, but not actively pursuing it

## Slide 88: 11.5.2 -PLAN RISK RESPONSES: TOOLS & TECHNIQUES
.6 Contingent Response Strategies
  Designed for use only under certain predefined conditions
    examples: missing intermediate milestones, gaining higher priority with a supplier
    Such pre-defined conditions should be tracked
    .7 Strategies for Overall Project Risk
    Responses should be developed to address overall project risks:
    Avoid. An appropriate strategy when the overall project risk is significantly negative and outside the project’s present risk threshold
    Examples: reducing or removing a high risk element from the scope, or, cancelling the entire project.
    Exploit. Appropriate when an opportunity is significantly positive for the overall project. Examples: addition of high-benefit elements to the project, or, modifying the risk threshold of the project to embrace the opportunity.

## Slide 89: 11.5.2 -PLAN RISK RESPONSES: TOOLS & TECHNIQUES
    .7 Strategies for Overall Project Risk (cont’d)
    Transfer/Share. An appropriate is to transfer a highly negative risk, alternatively, a strategy of sharing a highly positive opportunity should be considered.
    Mitigate/Enhance. These strategies are used to optimize the chances of achieving the project’s objectives. Mitigation is used for negative overall project risks. Enhance is used for positive opportunities effecting the overall project
    Accept. An appropriate strategy when no other response is feasible. Most common active acceptance strategy is to establish an overall contingency reserve for the project, such as funds, time, or resources. Passive acceptance involves no proactive action apart from periodic review of the overall project risk level.
    .8 Data Analysis
    Alternative Analysis. Compares responses to select the best.
    Cost-Benefit Analysis. Used to select the highest benefit.
    .9 Decision Making
    Multi-criteria decision making, uses a decision matrix to establish key decision criteria and selecting the preferred response.

## Slide 90: 11.5.3 - PLAN RISK RESPONSES: OUTPUTS
.1 Change Requests
Plan Response process may require changes to the cost and/or schedule baselines. These requests are processed through the Integrated Change Control process.
.2 Project Management Plan Updates
  Risk response activities, once agreed to, must update the appropriate component of the Project Mgmt. Plan, including:
    Schedule Management Plan
    Cost Management Plan
    Quality Management Plan
    Resource Management Plan
    Procurement Management Plan
    Scope Baseline
    Schedule Baseline
    Cost Baseline

## Slide 91: 11.5.3 - PLAN RISK RESPONSES: OUTPUTS
    .3 Project Documents Updates
    Assumption Log. Updated to reflect new assumptions made, new constraints identified, or existing ones modified.
    Cost Forecasts. Updated to reflect cost forecasts as a result of planned risk responses.
    Lessons Learned Register. Updated to reflect information that may be useful for later phases or for future projects.
    Project Schedule. Updated to add risk response activities.
    Project Team Assignment. Once response planning is completed, the project team assignment document needs to be updated with the team and resources required for the response activities
    Risk Register. Updated to add information about:
      Agreed strategies - Specific actions to implement
      Triggers & symptoms - Required budget & Schedule
      Contingency plans - Fallback plans
      Residual risks - Secondary risks
Risk Report. Updated to present agreed upon responses to the current overall project risk, together with expected changes that may result from these responses.

## Slide 92: 11.6 - IMPLEMENT RISK RESPONSES
Adopted from PMI’s (PMBOK® Guide)
11.0
Project Risk
Management
11.1
Plan Risk
Management
11.2
Identify
Risks
11.3
Perform
Qualitative
Risk Analysis
11.4
Perform
Quantitative
Risk Analysis
11.5
Plan Risk
Responses
11.7
Monitor
Risks
11.6
Implement
Risk
Responses
.

## Slide 93: 11.6 - IMPLEMENT RISK RESPONSES
This process, performed throughout the project life-cycle, is to ensure that the planned risk responses are executed to address the project’s overall risk exposure, mitigate the individual risk effects, and maximize the benefits of potential opportunities.
The overall risk exposure of the project and the individual threats and opportunities, could be proactively managed, only if the risk owners endeavor their best efforts to implement the planned responses.

## Slide 94: 11.6 - IMPLEMENT RISK RESPONSES
Adopted from PMI’s (PMBOK® Guide 6th Ed. Fig 11.19 Page 449)

## Slide 95: 11.6 - IMPLEMENT RISK RESPONSES
1 Change Requests
2 Project Docs Update
Issue log
Lessons learned Reg.
Project Team Assignments
Risk Register
Risk Report
1 Expert Judgment
2 Interpersonal & Team
Skills
Influencing
3 PMIS
1 Risk Mgmt. Plan
Risk Mgmt. Plan
2 Project Documents
Lessons Learned Reg.
Risk Register
Risk Report
4 Org. Proc. Assets
Inputs
Tools & Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 96: 11.6.1 - IMPLEMENT RISK RESPONSES INPUTS
.1 Project Management Plan
Risk Management Plan. Provides information about owners roles and responsibilities, the details of risk management methodology, the risk thresholds, key stakeholders’ risk appetite. The information helps define the acceptable target of risk response to achieve.
.2 Project Documents
Lessons Learned Register. Learnings from implementing risk responses can be applied to later phases or future projects.
Risk Register. Provides information about risk owners and planned responses for each individual risk.
Risk Report. Provides an assessment of the current overall project risk exposure, planned response strategy and owners.
.3 Organizational Process Assets
Lessons learned repository. Indicates effectiveness of particular risk responses, from previous projects.

## Slide 97: 11.6.2 - IMPLEMENT RISK RESPONSES TOOLS & TECHNIQUES
.1 Expert Judgment
Expertise to validate or modify risk responses if necessary.
.2 Interpersonal & Team Skills
Influencing. May be required to ensure implementation of risk responses owned by people outside the project team, who have competing demands.
.3 Project Management Information Systems
Software programs needed to integrate planned risk response activities with other project activities.

## Slide 98: 11.6.3 - IMPLEMENT RISK RESPONSES OUTPUTS
.1 Change Requests
Implementation of risk responses may require changes to cost and schedule baselines. These requests are processed via Integrated change control process.
.2 Project Documents Updates
Issue log. To record new issues encountered
Lessons Learned register. Updated to record new lessons learned or document effective implementation activities or how to avoid issues encountered.
Project Team Assignments. Updated to allocate the necessary resources to implement risk responses.
Risk Register. May be updated to reflect any changes to planned risk responses, owners, or strategy, subsequent to implementing responses.
Risk report. Updated to reflect necessary changes to previously planned responses, subsequent to implementing responses process.

## Slide 99: 11.7 - MONITOR RISKS
Adopted from PMI’s (PMBOK® Guide)
11.0
Project Risk
Management
11.1
Plan Risk
Management
11.2
Identify
Risks
11.3
Perform
Qualitative
Risk Analysis
11.4
Perform
Quantitative
Risk Analysis
11.5
Plan Risk
Responses
11.7
Monitor
Risks
11.6
Implement
Risk
Responses
.

## Slide 100: 11.7 – MONITOR RISKS
Risk monitoring involves:
  Keeping track of identified risks
  Determining if the overall project risk has changed
  Monitoring if individual risks have changed
  Identifying if new individual risks have arisen
  Ensuring the execution of risk plans is still appropriate
  Evaluating if assumptions are still valid
  Determining if risk management policies are being followed
  Determining if contingency reserves require modification
  Determining if project strategy is still valid.
Risk monitoring is an ongoing process for the life of the project
  Continually sensing the overall risk exposure of the project and developing strategies and fall-back positions to permit alternative lower-risk solutions.
Adopted from PMI’s (PMBOK® Guide)

## Slide 101: 11.7 – MONITOR RISKS DATA FLOW DIAGRAM
Adopted from PMI’s (PMBOK® Guide 6th Ed. Fig 11.21 Page 454)

## Slide 102: 11.7 – MONITOR RISKS
1 Work performance information
2 Change Requests
3 Project Mgt. Plan Updates
Any Component
4 Project Document Updates
Assumption Log
Issue Log
Lessons Learned Reg.
Risk Register
Risk Report
5 Organizational process assets updates
1 Data Analysis
Technical Performance
Analysis
Reserve Analysis
2 Audits
3 Meetings
1 Project Mgmt. Plan
Risk Mgmt. Plan
2 Project Documents
Issue Log
Lessons Learned Reg.
Risk Register
Risk Report
3 Work Performance Data
.4 Work Performance
reports
Inputs
Tools &
Techniques
Outputs
Adopted from PMI’s (PMBOK® Guide)

## Slide 103: 11.7.1 – MONITOR RISKS: INPUTS
.1 Project Management Plan
  Risk Management Plan. Provides information about how, when and who shall monitor risks.
.2 Project Documents
  Issue Log. Monitored to see if any issues have been updated.
  Lessons Learned Register. Records of previous learnings
  Risk Register. Provides key inputs about identified individual risks, owners, planned responses, specific implementation actions. Also describes symptoms, triggers and risk warning signs, and a watch list for low priority risks.
  Risk Report. Provides assessment of current overall risk exposure, planned response strategies, and describes residual risks, responses and owners.

## Slide 104: 11.7.1 – MONITOR RISKS: INPUTS
.3 Work Performance Data
  Approved changes need to be analyzed for any effects upon the risk register, risk response plan, or risk management plan
  All changes must be formally documented
  Work results and other project records about project performance and risk
  Report commonly used to monitor and control risk include Issues Logs, Action-Item Lists, Jeopardy Warnings, or Escalation Notice
.4 Work Performance Reports
  As project performance is measured and reported, new risks may be identified
  The seven-cycle risk processes should be repeated for these new risks

## Slide 105: 11.7.2– MONITOR RISKS: TOOLS & TECHNIQUES
.1 Data Analysis
  Technical Performance Analysis. Compares technical accomplishments against the project plan. Deviation (such as not meeting functionality at a milestone) may indicate the potential impact of threats or opportunities.
  Reserve Analysis. Some individual project risks may occur with positive or negative impacts on contingency reserves. Reserve analysis compares the remaining amount of contingency to the amount of remaining risks to determine if the remaining reserve is adequate.
  .2 Audits
  Used to determine the effectiveness of the risk management process
  The project manager should ensure the audits are performed at an appropriate frequency. Risk audits should be reviewed during project status meetings and their objectives clearly defined before the audit is conducted.

## Slide 106: 11.7.2– MONITOR RISKS: TOOLS & TECHNIQUES
  .3 Meetings
  Regularly scheduled Risk Review Meetings; should be held to:
    Examine and document the effectiveness of risk responses
    Identify new individual project risks
    Reassess current risks, close outdated risks,
    Identification of lessons learned

## Slide 107: 11.7.3– MONITOR AND CONTROL RISKS: OUTPUTS
.1 Work Performance Information
As an outcome of monitoring risks, the performance information, created by comparing actual risks that have occurred with the expectation how they would occur. The information determines the effectiveness of the risk management processes.
.2 Change Requests
  Implementing contingency plans or workarounds may require change the project plan. The change request should be issued and managed through integrated change control, and may involve:
  Recommended Corrective actions
  Recommended preventive actions

## Slide 108: 11.7.3– MONITOR AND CONTROL RISKS: OUTPUTS
.3 Project Management Plan Updates
  Updates to the project management plan occur as a consequence of approved changes during monitoring project risks, as needed.
.4 Project Document Updates
  The documents to be updated may include:
  Assumption Log. Updated to reflect new assumptions/constraints
  Issue Log. To record new issue
  Lessons Learned Register. Updated with new risk-related lessons.
  Risk Register. Updated to add new risks, updated existing risks, closing outdated risks, etc.
  Risk Report. Updated to reflect current overall risk exposure.
  .5 Organizational Process Assets Updates
  Updates may be required to Risk Management Plan templates, reports and Risk Breakdown Structure.

## Slide 109
SUPPLIMENTARY RISK MANAGEMENT INFORMATION

## Slide 110: Introduction to Project Risk
Risk and Opportunity
  Managers need to assess both the possible adverse consequences and the possible beneficial consequences.
  Risk and opportunity are mirror images of each other
  It takes two different mind sets to assess opportunity and to assess risk.
Notes: Every project has a cloud of uncertainty. Which could result is adverse consequence or beneficial consequences.

## Slide 111: Introduction to Project Risk
No
Information
Partial
Information
Complete
Information
(Unknown
Unknowns)
(Known
Unknowns)
(Knowns)
Total
Uncertainty
General to Specific
Uncertainty
Total
Certainty
Scope of Project Risk Management
The Uncertainty Spectrum

## Slide 112: Introduction to Project Risk
Total Project Life Cycle
Concept
Develop
Execute
Finish
Opportunity and Risk
Amount at stake
Period when
Highest Risks
are Incurred
TIME
R
I
S
K
$
V
A
L
U
E
Period of
Highest
Risk Impact
Adopted from PMI’s PMBOK® Guide

## Slide 113: Introduction to Project Risk
Uncertainty
  Knowns
    Items or situations containing no uncertainty (taxes)
  Known-Unknowns
    Items we know exist but we do not know how they will affect us (rework)
  Unknown-Unknowns
    Items or situations whose existence we cannot imagine (“Who knew ?”)

## Slide 114: Introduction to Project Risk
Risk Models
  A risk model provides a way of thinking about risk that helps us understand an organization in a distinct yet partial way
  Models are complementary and overlap
  It is better to use many models than only one
  Today we will focus on the PMBOK risk model
Notes: Every project has a cloud of uncertainty. Which could result is adverse consequence or beneficial consequences.

## Slide 115: 11.4.2 - Perform Quantitative Risk Analysis: Tools & Techniques
  Probability Distributions
    Information needed depends upon the type of probability distributions that will be used, e.g.:
      Triangular and PERT (Each of these distributions requires 3-point estimates: Optimistic, Most Likely and Pessimistic)
      Normal and Log normal (Each of these distributions requires means and standard deviations)
    Continuous probability distributions are usually used in quantitative risk analysis.
    Distributions represent both probability and consequences of the project component.
    Common distributions include:
      PERT / Beta
      Triangular
      Normal
      Log normal
      Uniform

## Slide 116: Statistical Terms
  Mean - the average of the values of the events
  Mode - the value which occurs most frequently
  Median - the middle value of the data ordered
  Dispersion (scatter around the mean)
  Range - difference between highest & lowest
  Variance - average of the sum of the squared deviations from the mean
  Standard deviation - the square root of the variance

## Slide 117: Statistical Terms (Continued)
  Data: 3, 2, 9, 6, 1, 5, 7, 3, 4
  Data, ordered: 1, 2, 3, 3, 4, 5, 6, 7, 9
    Mean = 4.4
    Mode = 3
    Median = 4
    Range = 1 to 9
    Variance = 6.5
    Standard deviation = 2.6

## Slide 118: Beta Curve Using PERT Estimates

## Slide 119: Beta Distribution Using PERT Estimates
PERT uses three-point estimates, “Optimistic” (O), “Most Likely” (ML) and “Pessimistic” (P)
  Mean = O + (4ML) + P
  6
  Standard Deviation = P – O
  6

## Slide 120: Triangular Distribution

## Slide 121: Triangular Distribution
The Triangular distribution (like PERT) uses three-point estimates, “Optimistic” (O), “Most Likely” (ML) and “Pessimistic” (P)
  Mean = O + ML + P
  3
  Variance = (P – O)2 + (ML – O)(ML –P)
  18
  Standard Deviation = Square Root (Variance)

## Slide 122: Normal DISTRIBUTION

## Slide 123: Normal Distribution
Normal distribution is a continuous probability distribution. Graphed, it is a symmetrical, bell-shaped curve. In the Normal distribution, observations, equidistant from the mean have the same frequency.
A standardized Normal curve has a zero mean and unit standard deviation.
  1 S.D encompasses 68.3% of the area under the curve
  2 S.D.’s encompass 95.5% of the area under the curve
  3 S.D.’s encompass 99.7% of the area under the curve
Many distributions arising in practice can be approximated by a Normal distribution. Other random variables may be transformed to Normality.

## Slide 124: Lognormal Curve

## Slide 125: Lognormal Distribution
Lognormal distribution is a continuous probability distribution. A random variable is log normally distributed if the natural log of the variable is normally distributed.
Financial data are often log normally distributed, e.g. costs, expenditures, etc.

## Slide 126: Uniform DISTRIBUTION

## Slide 127: Uniform Probability Distribution
Uniform probability distribution models either continuous or discrete random variables.
The values of a uniform random variable are uniformly distributed over an interval.
Events occurring within a specific time window, with each event having an equal probability of occurring, would follow a uniform distribution over the time interval.

## Slide 128: 11.3.2 – PERFORM QUALITATIVE RISK ANALYSIS TOOLS & TECHNIQUES
These charts represent three dimensions of data, where each risk is plotted as a bubble, an a three dimensional graph; i.e., the horizontal axis showing detectability, the vertical axis showing proximity, and the bubble size showing the impact.
.6 Probability and Impact Matrix
Hierarchical Charts
PMBOK® 6th Ed. Fig 11.10 page 426

## Slide 129: EXAMPLE PROBABILITY DISTRIBUTION RESULTS OF MONTE CARLO SIMULATION
In this example, there is 10% probability that the project on the left will finish on or before the target date of May 13, 2017. While there is 85% probability of completing the project on the right for $2.45M or less.
Adopted from PMI’s (PMBOK® Guide)

## Slide 130: 11.4.2 - PERFORM QUANTITATIVE RISK ANALYSIS: TOOLS & TECHNIQUES
.4 Representation of Uncertainty, (cont`d)
Sensitivity Analysis. The analysis correlates variations in the project outcome with variations in elements of the quantitative analysis risk model; The element that results in the highest variation in the output is the most sensitive element. The project team focusses on this element.
Adopted from PMI’s (PMBOK® Guide 6th Ed. Fig 11.14)