## Slide 1: PMP® Exam Preparation Workshop PMP250
Session # 10
Project Procurement Management
Project Management Professional, (PMP), is a registered mark of the Project Management Institute , Inc.

## Slide 2
The contents of this lesson are based on:
A Guide to Project Management Body of Knowledge (PMBOK® Guide)
Sixth Edition
Published and Owned by
Project Management Institute, PMI®
PMBOK, PMP, CAPM and PMI are registered trade marks of Project Management Institute, Inc.

## Slide 3: OBJECTIVES
By the end of this session you will understand:
  The three processes conducted to acquire products, services or results from external suppliers, by developing and administering agreements, contracts, purchase orders, memoranda of agreements (MOA) or service level agreements (SLA).
  how Project Procurement Management processes relate to the 5 project management process groups in a project phase
  the inputs, tools and techniques and outputs for managing Project Procurement processes as outlined in PMBOK® Guide

## Slide 4: PROJECT PROCUREMENT MANAGEMENT
Adopted from PMI’s (PMBOK® Guide)

## Slide 5: DEFINITIONS
Procurement
  Acquisition of goods or services from external sources
Procurement Management
  The processes required to acquire goods or services
Seller
  Contractor, Subcontractor, Vendor, Service Provider, or Supplier of products, services or results to the project
Buyer
  Project’s customer, and key stakeholder, clients, prime contractors, acquiring organization, government agencies, service requestors, purchasers

## Slide 6: KEY CONCEPTS FOR PROJECT PROCUREMENT MANAGEMENT
The Project Manager should be familiar with procurement regulations and processes to make intelligent decisions regarding contracts and avoid exposing the project to legal infractions.
Contract should clearly state the expected deliverables and results. Anything not in the contract, cannot be legally enforced. Project Managers should be mindful of cultural influences and local laws, in dealing with international contracts.
Contracts, being legally binding documents, are subjected to extensive approval process, involving the legal department, to ensure compliance with procurement rules and regulations, while making ensuring that the contract adequately describes the products, services or results that the seller is agreeing to provide.
Multiple contracts, managed simultaneously or sequentially, may be required for complex multi-phased projects, involving several levels of buyer-seller relationships.

## Slide 7: KEY CONCEPTS FOR PROJECT PROCUREMENT MANAGEMENT (cont’d)
A contract awarded to a winning bidder, may be run as a project, thus:
  The buyer becomes the customer of the subcontractor.
  The seller’s project management team, performs the delivery processes.
  The sellers manages the project to achieve The Procurement Scope of Work (SOW).
  The seller may become a buyer of lower-tiered products and services from its subcontractors.
For the Procurement Knowledge Area, the performing organization is assumed to be a buyer for an external organization, assumed to be a seller providing goods and services to the project. For larger, more complex projects the seller may become part of an integrated team after the contract award.
Often, the procurement of goods and services for a project, is conducted by the organization’s purchasing or contracting department

## Slide 8: 12.1 Plan Procurement Management
Adopted from PMI’s (PMBOK® Guide)

## Slide 9: 12.1 Plan Procurement Management
Identifying which project needs can be best met by procuring products or services
The process documents the project team’s answers of the following questions:
  whether to procure or provide internally; i.e., make/buy decision
  what and how much to procure
  who are the sellers
  what approach to take to procure
  when to procure
The roles and responsibilities related to procurement should be specified early in the project, and may include personnel from the purchasing and the legal departments of the organization.
Typical procurement steps might include:
  - Preparing the SOW - High level estimate - Advertising RFP
  - Shortlisting sellers - Issue bid document - Seller proposals
  Proposal evaluation - Cost evaluation - Select winner
  Finalize negotiations - Sign contract - Integrate schedule
Adopted from PMI’s (PMBOK® Guide)

## Slide 10: 12.1 Plan Procurement Management
1 Procurement
management plan
2 Procurement
Strategy
3 Bid documents
4 Procurement SOW
5 Source Selection
Criteria
6 Make or Buy Decisions
7 Independent Cost
Estimates
8 Change Requests
9 Project Docs Updates
Lessons learned Reg.
Milestone List
Requirements Docs.
Req. Traceability Mtrx.
Risk Register
Stakeholder Register
10 Org. Proc. Assets
Updates
1 Project Charter
2 Business Documents
Business Case
Benefits Mgmt. Plan
3 Project Mgmt. Plan
Scope Mgmt. Plan
Quality Mgmt. Plan
Resource Mgmt. Plan
Scope Baseline
4 Project Documents
Milestone List
Project Team Assgnt.
Requirements Docs
Req. Traceability Mtrx.
Resource Req.
Risk Register
5 Entr. Env. Factors
6 Org Process Assets
1 Expert Judgment
2 Data Gathering
Market Research
3 Data Analysis
Make or Buy Decision
4 Source Selection
Analysis
5 Meetings
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools and
Techniques
Outputs

## Slide 11: 12.1.1 PLAN PROCUREMENT MANAGEMENT INPUTS
.1 Project Charter
Describes the project, its objectives, milestones, and approved financial resources
.2 Business Documents
Business Case. Provides a reference for the procurement strategy alignment
Benefits Management Plan. Specifies when project benefits are expected to be available, hence, procurement dates and contract language.
.3 Project Management Plan
    Scope Management Plan: Provides SOW to be managed by project
    Quality Management Plan: Provides the applicable industrial quality standards for the RFP and the contract.
    Resource Management Plan: specifies resources to be purchased or leased and the relevant assumptions.
    Scope Baseline: used to develop the SOW and the terms of reference (TOR)

## Slide 12: 12.1.1 PLAN PROCUREMENT MANAGEMENT INPUTS
.4 Project Documents
Milestone List: Shows sellers when to deliver their results
Project Team Assignments: Shows which skills are available, and which need to be acquired and/or trained.
Requirements Documentation. May include:
  Technical requirements the sellers are required to satisfy
  Contractual Requirements; e.g., health, safety, security, performance, environmental, insurance, intellectual property rights, equal employment opportunity, licenses, permits, other non-technical requirements.
Requirements Traceability Matrix: links the origin of product requirements to the deliverables that satisfy them.
Risk Register: Identifies transferable risks
Stakeholder Register: provides details about project stakeholders, regulatory agencies, contracting and legal personnel, and their interest in the project.
.5 Enterprise Environmental Factors
Market Conditions - Market availability of required products/services
Seller information - Typical T&C for the specific industry
Unique legal requirements - Procurement legal advice
Contract Mgmt. Systems - Prequalified list of multi-tiered suppliers
Financial accounting and control systems

## Slide 13: 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS
.6 Organizational Process Assets
  Can have significant influence on planning procurement management; i.e., Information about pre-approved seller lists; formal procurement policies, procedures, and guidelines; contract templates; management systems.
Contract types fall into three main categories:
    1. Fixed Price Contracts
    2. Cost Reimbursable Contracts
    3. Time & Material Contracts
  The contract type has a big influence on the ultimate success of the procurement from a technical, cost, schedule and risk perspectives.

## Slide 14: 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS
Contract Types
Fixed Price Contracts. A fixed total price is set for a defined product, service or result to be provided. This type is appropriate when the requirements are well defined and no significant changes to the scope are expected. There are three types of fixed-price contracts:
  Firm fixed price (FFP): A common type, most favored by buyers. The fixed price set upon award, and does not change unless the scope of works changes.
  Fixed Price Incentive Fee (FPIF): the seller gets financial incentives for achieving cost, schedule or technical performance metrics. A price ceiling is set, and all costs above the price ceiling are born by the seller.
  Fixed Price with Economic Price Adjustment (FPEPA): Appropriate for contracts that span a considerable period of time, or payments made in different currencies. This type of fixed-price contract allows predefined adjustments to the contract price due to changed conditions, such as inflation effecting specific commodities.

## Slide 15: 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS
Contract Types
Cost-reimbursable Contracts. The seller is reimbursed all legitimate actual costs incurred to complete the work, plus a fee representing seller’s profit. This type of contracts are used when the scope of work is expected to change significantly during the contract term. There are three variations:
  Cost Plus Fixed Fee (CPFF): The seller is reimbursed for all allowable costs for performing the contract work, and receives a fixed fee as a percentage of the initial contract cost estimates. This changes only when the scope is changed.
  Cost Plus Incentive Fee (CPIF): The seller is reimbursed for all allowable costs for performing the contract work, and receives a predetermined incentive fee based on achieving certain performance objectives set forth in the contract. In CPIF contracts if the final costs are less or greater than the original estimated cost, then the buyer and seller share the variance based on a predefined split formula, for example 80/20
  Cost Plus Award Fee (CPAF): The seller is reimbursed for all allowable costs for performing the contract work, plus a fee based on performance undisputable criteria defined subjectively by the buyer.

## Slide 16: 12.1.1 PLAN PROCUREMENT MANAGEMENT: INPUTS
Contract Types
Time and Material Contracts (T&M): A hybrid type of contract with aspects of both fixed-price and cost-reimbursement contracts. This type of contracts are used for staff augmentation, acquisition of experts, and any outside support where precise estimates of work or SOW, cannot be prescribed.

## Slide 17
.1 Expert Judgment
Planning Procurement Management process may require personnel with expertise in the topics of procurement, purchasing, contract types, documents and regulations.
.2 Data Gathering
Market Research: Procurement teams may research and examine sellers capabilities in a specific industry, using information from variety of sources and references.
.3 Data Analysis
Make-or-Buy Analysis: Factors to consider in analyzing whether some required goods and services would be purchased from outside sources, or assigned to the project team to deliver, include:
  Organization’s current skills allocation and abilities
  Needed specialized expertise
  The desire to expand employment obligations
  The risks involved in either alternative.
  Financial criteria: ROI, IRR, NPV, B/C Analysis
12.1.2 Plan PROCUREMENT MANAGEMENT TOOLS & TECHNIQUES

## Slide 18
.4 Source Selection Analysis
A good practice for buyers is to specify proposal evaluation method and the selection criteria for bidders to know and prepare their bids accordingly. The criteria may include:
Least Cost. The lowest cost qualified bidder is awarded the contract. The method is appropriate for standard, routine well-defined outcomes, which could be executed at different costs
Qualifications Only. Used for relatively small value procurements. The contract is awarded on the basis of seller’s credibility, qualifications, expertise, and references.
Quality Based/Highest Technical Proposal Score. Bidder with the best acceptable technical proposal is invited to negotiate the price. The contract is awarded if the price is accepted.
Quality and Cost Based. Both quality and cost are selection criteria. Quality should be a priority in comparison to cost for high risk/uncertain elements.
Sole Source. The buyer asks a specific seller to prepare a technical and financial proposal. Since there is no competition, the award is based on negotiations.
Fixed Budget. The buyer specifies the available budget to invited sellers, and the highest-ranking technical bid is selected within the budget. Sellers adapt the scope of their proposal to the available budget. Appropriate when SOW is precisely defined.
12.1.2 Plan PROCUREMENT MANAGEMENT TOOLS & TECHNIQUES

## Slide 19: 12.1.3 PLAN PROCUREMENT MANAGEMENT: OUTPUTS
.1 Procurement Management Plan
  Defines procurement process in terms of
    The type of contract to be used
    Risk management issues
    Whether independent estimates will be used
    What actions should the project team in case the organization has a purchasing department
    Procurement documents needed
    Managing suppliers
    Coordinating procurement with project activities
    Constraints and assumptions
    Handling long lead time items
    Handling make-or-buy decisions and linking them to project estimating
    Setting contract schedule dates
    Identifying performance bonds to mitigate project risks
    Establishing direction to provided to sellers on developing WBS
    Establishing the format for SOW
    Identifying prequalified sellers
    Procurement metrics to manage the contract

## Slide 20: 12.1.3 PLAN PROCUREMENT MANAGEMENT: OUTPUTS
.2 Procurement Strategy
The procurement strategy determines the delivery method, type of contract, and how the procurement will progress.
Delivery Method. Two categories:
  Delivery for professional services could allow the provider to either subcontract or not to subcontract the required services, or, to set up a joint venture between buyer and services provider.
  Delivery methods for commercial construction projects could include: turnkey, Design Build (DB), Design-Bid-Build (DBB), Design-Build-Operate (DBO), or, Build-Own-Operate-Transfer(BOOT)
Contract Payment Types; i.e., Lump Sum, Firm Fixed Price, Cost Plus Award Fee, Cost Plus Incentive Fee, Time & Materials, Target Cost and others.
  Fixed-Price contracts are suitable for well defined work that is unlikely to change
  Cost Plus contracts are suitable when work is not well defined, evolving and likely to change.
  Incentives and awards may be used to align the objectives of buyers and sellers.
Procurement Phases. Information about:
  - Description, objectives and sequencing of each phases. - Performance indicators
  - Criteria for moving to next phase - Progress tracking plan
  Knowledge transfer process for use in subsequent phases

## Slide 21: 12.1.3 PLAN PROCUREMENT MANAGEMENT: OUTPUTS
.3 Bid Documents
Structured by the buyer to allow bidders complete their responses for evaluation by the buyer. Procurement SOW and other relevant contractual provisions are included in these documents
Request for Information (RFI). Used to request information from bidders. Usually followed by a RFQ or RFP
Request for Quotation (RFQ). Used to request prices from sellers for well defined product purchases.
Request for Proposal (RFP). Used to request a seller’s proposal to solve a problem and quote prices.

## Slide 22: 12.1.3 PLAN PROCUREMENT MANAGEMENT: OUTPUTS
.4 Procurement Statement of Work (SOW)
Describes the products and services to be procured, in sufficient detail to allow prospective sellers to determine if they are capable of providing the requirements.
The SOW should describe any collateral services required such as, performance reporting, post-project operational support.
Terms of Reference (TOR) is used for procuring services.
.5 Source Selection Criteria: May include
Bidder capability - Product and life-cycle cost - Delivery dates
Technical approach - Specific expertise - Adequacy of approach
Staff competence - Financial stability - Mgmt. experience
Training offered - Local content
.6 Make-or-Buy Decision
Analysis based decision as to whether particular work can be accomplished by the project team or needs to be procured from outside sources.

## Slide 23: 12.1.3 PLAN PROCUREMENT MANAGEMENT: OUTPUTS
.7 Independent Cost Estimates
These estimates are done by the buyer’s organization or third parties for the buyer. The objective is to ascertain that the seller has correctly understood the SOW, and the prices are in line with the market level for similar procurements.
.8 Change Requests
Changes to the procurement plan or to the products and services may be needed. These changes are processed via the integrated change control process.
.9 Project Documents Updates
Lessons Learned Register. Updated to reflect new regulations, data gathering and analysis, seller selection.
Milestone List. Shows expected delivery dates.
Requirements Documentation. Provides descriptions of technical and contractual requirements that the seller is expected to deliver.
Requirements Traceability Matrix.
Risk Register. Updated to reflect any uncertainties encountered with the seller.
Stakeholder Register. Updated to reflect additional information on stakeholders, regulatory agencies, contract personnel, legal personnel

## Slide 24: 12.2 CONDUCT PROCUREMENTS
Adopted from PMI’s (PMBOK® Guide)

## Slide 25: 12.2 CONDUCT PROCUREMENTS
Preparing the documents needed to support the process of soliciting proposal from sellers, selecting the seller and awarding the contract, managing the contract and implementing the legal agreement for delivery of required goods and services.
Major procurements may require more than one iteration of the this process and include negotiations.
Adopted from PMI’s (PMBOK® Guide)

## Slide 26: 12.2 CONDUCT PROCUREMENTS
1 Selected Sellers
2 Agreements
3 Change Requests
4 Project Mgmt Plan
Updates
Req. Mgmt. Plan
Quality Mgmt. plan
Comm. Mgmt. plan
Risk Mgmt. Plan
Procurn’t Mgmt. Plan
Scope Baseline
Schedule Baseline
Cost Baseline
5 Project Document
Updates
Lessons learned Reg.
Req. Documentation
Req. Traceability Mtrx
Resource Calendars
Risk Register
Stakeholder Reg.
6Org. Proc. Assets updates
1 Procurement Mgmt. Plan
Scope Mgmt. Plan
Req. Mgmt. Plan
Comm. Mgmt. Plan
Risk Mgmt. Plan
Procurement Mgmt. Plan
Configurations Mgmt. Plan
Cost Baseline
2 Project Documents
Lessons Learned Register
Project Schedule
Req. Documentation
Risk Register
Stakeholder Register
3 Procurement Docs
4 Seller Proposals
5 Ent. Env. Factors
6 Org Process Assets
1 Expert Judgment
2 Advertising
3 Bidder Conferences
4 Data Analysis
Proposal Evaluation
5 Interpersonal & Team
Skills
Negotiation
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools and
Techniques
Outputs

## Slide 27: 12.2.1 CONDUCT PROCUREMENTS: INPUTS
.1 Project Management Plan
Scope Management Plan. Describes how scope will be managed, including sellers’ scope.
Requirements Management Plan. Describes how sellers will manage the requirements they are under agreement to satisfy.
Communications Management Plan. Describes communications with sellers.
Risk Management Plan. Describes how risks will be managed.
Procurement Management Plan. Describes the procurement activities.
Configuration Management Plan. Describes how sellers will manage configuration to be consistent with buyer’s approach.
Cost Baseline. Includes the budget for the procured goods and services as well as the cost of the procurement process activities.
.2 Project Documents
Lessons Learned Register. Records of earlier procurement experience.
Project Schedule. Defines procurement activities and deliverable dates.
Requirement Documentation. Includes both technical and contractual requirements.
Risk Register. Records procurement risks, in terms of type of contract, duration, delivery method, agreed upon price.
Stakeholder Register. Provides stakeholder information

## Slide 28: 12.2.1 CONDUCT PROCUREMENTS: INPUTS
.3 Procurement Documentation
Bid Documents. Documents sent to sellers, such as RFI, RFP, RFQ
Procurement Statement of Work (SOW). Describes requirements in detail.
Independent Cost Estimates. Provide reasonableness check against seller prices
Source Selection Criteria. Describes how proposals will be evaluated.
.4 Seller Proposals
Prepared by the seller in response to buyer’s procurement documents. It is a good practice to submit the technical proposal separately from the price proposal. The proposals satisfying the technical criteria are then negotiated on the price.
.5 Enterprise Environmental Factors
Procurement local Laws and Regulations, ensuring that major procurements include local sellers.
External economic conditions influencing procurement processes; i.e., market conditions
Records of past experience with sellers
Prior agreements already in place
Contract management systems

## Slide 29: 12.2.1 CONDUCT PROCUREMENTS: INPUTS
.6 Organizational Process Assets
List of prequalified sellers
Organizational policies regarding the selection of sellers
Organizational templates or guideline regarding drafting of contracts
Financial policies and procedures, invoicing and payments

## Slide 30: 12.2.2 CONDUCT PROCUREMENTS TOOLS & TECHNIQUES
.1 Expert Judgment
  Expertise in evaluating seller proposals.
  Expertise in different disciplines; i.e., finance, engineering, design, development, supply chain management, legal, negotiations, etc.
.2 Advertising
  Used to expand the list of potential sellers
  Sometimes required on public projects
.3 Bidder Conferences
  Used to ensure that all prospective sellers have a common understanding of the procurement
.4 Data Analysis
Proposal evaluation to ensure they are complete and respond to bid documents, SOW, in accordance with the selection criteria detailed in the RFP

## Slide 31: 12.2.2 CONDUCT PROCUREMENTS TOOLS & TECHNIQUES
.5 Interpersonal and Team Skills
Negotiations
  Involves clarification and mutual agreement on the structure and requirements of the contract
  Final contract to reflect all agreements reached
  Examples of subjects covered: responsibilities & authorities, terms & conditions, applicable laws, contract financing, price, etc.
  Negotiations should be led by a member of the procurement team that has the authority to sign the agreement
  Five stages of Negotiation
  Protocol
  Probing
  Scratch bargaining
  Closure
  Agreement
  Essentially a sequential process
  Negotiators should not rush the process or attempt to leave one stage incomplete or jump to the next stage too quickly

## Slide 32: 12.2.3 CONDUCT PROCUREMENTS: OUTPUTS
.1 Selected Sellers
  Sellers judged to be competitive, based on their proposal evaluation
  Who have negotiated a draft- contract for subsequent refinement and approval
.2 Agreements
  A contract is a mutual agreement which obligates the seller to provide the specified product and obligates the buyer to pay for it
  Legal relationship subject to remedy in the courts.
  May include the following:
  - SOW - Schedule Baseline
  - Performance reporting - Period of performance
  - Roles and Responsibilities - Seller’s place of performance
  - Pricing - Payment terms
  - Place of delivery - Inspection & acceptance criteria
  - Warranty - Product support
  - Limitation of liability - Fees and retainer
  - Penalties - Incentives
  - Insurance & Performance bonds - Subcontractor approvals
  - Change request handling - Termination clauses, Alternative Dispute Resolution

## Slide 33: 12.2.3 CONDUCT PROCUREMENTS: OUTPUTS
.3 Change Requests
  The process of requesting changes to the project management plan or its subsidiary plans as necessary.
.4 Project Management Plan Updates Conducting procurements may require updates to:
Requirements Management Plan. Updated to reflect changes by seller
Quality Management Plan. Updated to reflect alternative standards
Communication Management Plan. Updated to include sellers
Risk Management Plan. Updated to reflect procurement risks
Procurement Management Plan. Updated for negotiated changes
Scope Baseline. Updated to reflect changes due to procurement
Schedule Baseline. Updated to reflect changes due to procurement
Cost Baseline. Updated to reflect changes due to procurement

## Slide 34: 12.3 CONTROL PROCUREMENTS
Adopted from PMI’s (PMBOK® Guide)

## Slide 35: 12.3 CONTROL PROCUREMENTS
Ensuring that the vendor’s performance meets contractual requirements
Managing procurement relationships, monitoring contract performance, and making changes and corrections as appropriate
Application of project management processes to the contractual relationship(s) and integration of these processes into the overall management of the project.
Performing administrative activities to:
Collection, analysis and maintaining of contract financial and performance records for evaluation and reporting.
Review and optimization of procurement plans and schedules.
Monitoring the procurement environment to ensure implementation can be facilitated; making adjustments as needed.
Monitoring, verification and payment of invoices.
Ensuring the quality of control and credibility of audits in accordance with the organization’s code of ethics, its legal counsel, anti-corruption initiatives.

## Slide 36: 12.3 CONTROL PROCUREMENTS
The project management team must be aware of the legal implications of actions when administrating any contract.
In large organizations contract administration; i.e. managing procurement relationships, monitoring contract performance and making changes and corrections to the contract, is performed by an administrative function other than the project team.
Adopted from PMI’s (PMBOK® Guide)

## Slide 37: 12.3 CONTROL PROCUREMENTS
1 Closed Procurements
2 Work performance info
3 Procurement Docs
updates
4 Change requests
5 Project Mgmt. plan
updates
Risk Mgmt. plan
Procurement Mgmt. pln
Schedule baseline
Cost baseline
6 Project docs updates
Lessons learned Reg.
Resource Req.
Req. traceability Matrix
Risk Register
Stakeholder register
7 Org. Proc Asset Update
1 Project Mgt. Plan
Req. Mgmt. plan
Risk Mgmt. plan
Procurement Mgmt. plan
Change Mgmt. plan
Schedule baseline
2 Procurement Docs.
Assumption log
Lessons Learned Reg.
Milestone List
Quality Reports
Requirements Documentation
Req. Traceability Matrix
Risk Register
Stakeholder Register
3 Agreement
4 Procurement Documents
5 Approved Change Requests
6 Work Performance Data
7 Ent. Env. Factors
8. Org. process Assets
1 Expert Judgment
2 Claims Administration
3 Data Analysis
Performance reviews
Earned Value Analysis
Trend Analysis
4 Inspection
5 Audits
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools and
Techniques
Outputs

## Slide 38: 12.3.1 CONTROL PROCUREMENTS:INPUTS
.1 Project Management Plan
  Requirements Management Plan. Describes how contracted requirements will be analyzed, documented and managed.
  Risk Management Plan. Describes how risk activities created by the seller will be structured and performed.
  Procurement Management Plan. Describes control procurement activities
  Change Management Plan. Describes how seller-created changes will be managed.
  Schedule baseline. Updated to reflect schedule slippages caused by seller.
  2 Project Documents
  Assumption Log. Documents assumption made during procurement
  Lessons Learned Register. Needed to improve contractor performance
  Milestone List. Shows seller’s delivery dates
  Quality Reports. Identifies seller performance and deliverable compliance
  Requirements Documentation. Identifies technical and contractual requirements, the seller is required to satisfy.
  Requirements Traceability Matrix. Shows how requirements are satisfied.
  Risk Register. Identifies risks associated with the seller.
  Stakeholder Register. Provides information about stakeholders involved in the procurement process

## Slide 39: 12.3.1 CONTROL PROCUREMENTS:INPUTS
.3 Agreements
Understanding between parties, serves as a baseline for the work being performed/provided by a seller to a buyer
.4 Procurement Documentation
Details how the procurement processes will be administered, provides the SOW, payment information, contractor performance information, plans, drawings and other documents.
5. Approved Change Requests
  Modifications to the terms of the contract or to the description of the product or service
  Contested changes where the seller and project management team cannot agree on compensation for the change are also called claims, disputes or appeals
.6 Work Performance Data
  Work performance information indicating which deliverables have been completed and which have not.
  Meeting quality standards
  Incurred or committed costs
  Seller Invoices

## Slide 40: 12.3.1 CONTROL PROCUREMENTS:INPUTS
.7 Enterprise Organizational Factors
Factors that influence control procurement process include:
Contract Change Control Systems
Market Conditions
Financial and Accounts payable management systems
Buyer’s code of ethics
.8 Organizational Process Assets
Procurement Policies

## Slide 41: 12.3.2 CONTROL PROCUREMENTS:TOOLS & TECHNIQUES
.1 Expert Judgment
Control procurements may require expertise in the areas of finance, engineering, design development, supply chain management, laws regulations compliance requirements and claims administration.
.2 Claims Administration
  Contested changes, claims, disputes, appeals are documented, processed, and monitored as per contact terms
  Contractual Dispute resolution procedures
  Arbitration, litigation
.3 Data Analysis
Performance Reviews. Performed to measure, compare and analyze actual performance on quality, resources, cost and schedule, against the agreement.
Earned Value Analysis (EVA). Measures variances of cost and schedule against the baselines.
Trend Analysis. Used to forecast estimates of cost at completion (EAC).

## Slide 42: 12.3.2 CONTROL PROCUREMENTS:TOOLS & TECHNIQUES
.4 Inspection
A structured review of the work performed by the seller, to determine work progress.
.5 Audits
  Required by the buyer and supported by seller as per the contract
  Conducted during execution to identify any weaknesses in seller’s deliverables.
  Audits findings must be brought to the attention of the project manager for adjustment as necessary.

## Slide 43: 12.3.3 CONTROL PROCUREMENTS: OUTPUTS
.1 Closed Procurements
Formal procurement closure requirements are described in the contract. Closure occurs when deliverables are have been provided on time, met the technical and quality specifications, and approved by the project team. There should be no outstanding claims or invoices.
.2 Work Performance Information
Provides a basis for identification of encountered or potential problems of a vendor, to support later claims, disputes or new procurements.
Reporting compliance of contracts enables tracking the completion of deliverables, supports improved forecasting, risk management and decision making
.3 Procurement Documents Updates
These documents may need updating to record any approved or unapproved changes, seller provided technical documents, performance information, invoices, payment records, inspection results.

## Slide 44: 12.3.3 CONTROL PROCUREMENTS: OUTPUTS
.4 Change Requests
  Changes to the project management plan or its subsidiaries such as Cost or Schedule baselines, or the procurement management plan may result from administer procurement.
  Change requests are processed for review and approval.
  Requested but unresolved changes may be disputed by one contract party and can lead to claims against the other party. These must be identified and documented by project correspondence.

## Slide 45: 12.3.3 CONTROL PROCUREMENTS: OUTPUTS
.5 Project Management Plan Updates
  Updates to the project management plan may be required for:
    Risk Management Plan. Updated to record significant unexpected risks identified during the execution of the contract, or update information on risks already in the plan.
    Procurement Management Plan. Updated to reflect approved changes that effect procurement management including costs and schedules
    Schedule Baseline. Updated to reflect any slippages that impact overall project performance.
    Cost Baseline. Updated to reflect changes impacting overall project costs and current cost forecasts

## Slide 46: 12.3.3 CONTROL PROCUREMENTS: OUTPUTS
.6 Project Documentation Updates
  Lessons Learned Register. Updated to record information about effective techniques used in maintaining and resolving variances encountered in scope, time and cost of contract performance.
  Resource Requirements. Updated to record changes in resources required to carry out the contract work.
  Requirements Traceability Matrix. Updated with information about completed requirements.
  Risk Register. Updated with information regarding new risks encountered during contract execution, or changes to existing risks
  Stakeholder Register. Updated to reflect any changes to suppliers or contractors.

## Slide 47: 12.3.3 CONTROL PROCUREMENTS: OUTPUTS
.7 Organizational Process Assets Updates
  Payment Schedule and Requests. Updated to reflect changes
  Seller Performance Evaluation Documentation. Updated to reflect new information regarding the sellers performance and capability to continue executing the agreement. The document helps selecting sellers in future.
  Prequalified Seller Lists Updates. Updated to record addition or removal of sellers from the list based on performance.
  Lessons Learned Repository. Updated to describe whether the project objectives were achieved and if not, provide reasons why not.
  Procurement File. Contains a complete set of indexed contract documents, including the closed contract, fro future reference.

## Slide 48: NOTES
Contract Breach
  Failure to perform a contractual obligation constitutes a breach of contract
    If the breach is caused a project manager preventing performance of the contract, without fault on the party who is willing to perform, the loss of the latter may consist of two distinct grounds of damage a) work already performed and b) lost profits that would have been realized if performance had been allowed
  Breach of contract – failure to perform a duty imposed by the contract
  Material breach – is so serious as to deprive the non-breaching party the benefit of the bargain
    Non-faulted party is discharged from any further obligations under the contract.

## Slide 49
SUPPLIMENTARY INFORMATION
RELEVANT TO
PROJECT PROCUREMENT MANAGEMENT

## Slide 50: NOTES
Contract Close-out
  Product verification
  Was all work completed correctly and satisfactorily
Administrative close-out
  Updating records to reflect final results
  Archiving of information for future use

## Slide 51: NEGOTIATON STAGES 1. Protocol Stage
Introductions
Negotiators getting to know each other
Atmosphere for the rest of the negotiation meeting is determined
2. Probing Stage
Beginning of the search process
Each party identifies their issues of concern (issues are not debated, only reviewed in an attempt to understand where the other party stands)
Identify strengths/weaknesses and possible areas of interest of the opponent
Modification of the negotiation plan to take into account any new information

## Slide 52: 3. Scratch Bargaining
The actual bargaining starts
Differences between the two parties’ approach (usually time, cost, performance) are discussed with some outcome deemed appropriate by both parties
Points of concession are identified and the gap between the two parties narrows
4. Closure Stage
The two positions are summed up and final concessions are reached
A summary of the agreements reached is documented
Arrangements for recording the results are initiated, leading into the last stage

## Slide 53: 5. Agreement Stage
Ensuring both parties have an identical understanding of the agreements reached
Differences in language and terminology can contribute to misunderstandings, therefore clarification may be necessary
Negotiations may be reopened on points previously thought settled
Development of plans for recording the agreements in a written contract

## Slide 54: Tactics for Contract Negotiation
Deadline
  Imposing a deadline for reaching an agreement
  Limits the time involved in negotiating
Surprise
  One party can take the other party by surprise
  One party may have some information (e.g. price change) and present it to the other party who was not aware
Limited authority
  One party may claim that the agreement cannot be finalized because the negotiator has limited authority
  Stalling tactic
  Know the authority of the opponent early in the negotiation meeting
Missing-man
  One party may claim that the person with final authority is absent

## Slide 55
Fair and reasonable
  Comparisons to other similar situations e.g. price is fair because that is what another company is paying
Delays
  Tactical use of delays to get back on track, to cool down when tempers begin to flare, etc.
Reasoning together
  Working out problems to the benefit of all involved
Confusing the opponent
  One party deliberately distorts issues and figures creating confusion

## Slide 56
Withdrawal
  One party makes a false attack upon an issue and then retreats
  Usually done to avert attention from a possible area of weakness
Unreasonable
  One party makes the other party appear unreasonable e.g. the buyer concedes on a number of minor issues then when a major issue comes up the buyer points out all of the areas in which they made concessions making the seller appear unreasonable

## Slide 57: SCOPE DEFINITION - RISK - CONTRACT SELECTION
Probability of
Occurrence
Cost Estimate Value
100%
95%
110%
120%
90%
140%
80%
Project A - Well defined
Project B - Fairly defined
Project C - Poorly defined
Suggested types of
contract for various
spreads
+/- 15%: FFP
+/- 25%: CPFF
+/- 50%: CPIF
> 50% : CPAF
Low
Medium
High