## Slide 1: PMP® EXAM PREPARATION PMP 250
Session # 6
Project Quality Management
Project Management Professional, (PMP), is a registered mark of the Project Management Institute , Inc.

## Slide 2
The contents of this lesson are based on:
A Guide to Project Management Body of Knowledge (PMBOK® Guide) Sixth Edition
Published and Owned by
Project Management Institute, PMI®
PMBOK, PMP, CAPM and PMI are registered trade marks of Project Management Institute, Inc.

## Slide 3: LEARNING OBJECTIVES
By the end of this session, you should understand:
How Project Quality Management processes relate to the 5 project management process groups in a project phase
The inputs, tools and techniques and outputs for managing Project Quality processes as outlined in PMBOK® Guide

## Slide 4
PROJECT QUALITY MANAGEMENT
Adopted from PMI’s (PMBOK® Guide)

## Slide 5: KEY CONCEPTS FOR PROJECT QUALITY MANAGEMENT
Quality Management addresses the processes and activities of the performing organization that determine quality policies, objectives, and responsibilities so that the project will satisfy the needs for which it was undertaken.
Project Quality Mgmt. applies to all projects, regardless of the deliverables, although the metrics and techniques used are specific to the type of the product.
Failure to meet quality requirements can have serious negative consequences for all stakeholders of the project, such as:
  decreased profits, increased risk, rework, undetected errors, employee attrition.

## Slide 6: KEY CONCEPTS FOR PROJECT QUALITY MANAGEMENT
  Quality and Grade are different concepts.
  QUALITY, as a delivered performance or result, is “the degree to which a set of inherent characteristics fulfill requirements”
  GRADE, as a design intent, is a category assigned to deliverables having the same functional use, but different technical characteristics, or features.
  Prevention is preferred over inspection. The cost of preventing mistakes is generally much lower than the cost of correcting defects found by inspection or during usage.
  The project team should distinguish between the following terms:
  PREVENTION (keeping errors out of the process)
  INSPECTION (keeping errors out of the customers’ hands)
  ATTRIBUTE SAMPLING (results either conform or do not conform)
  VARIABLE SAMPLING (conformity is measured on a continuous scale)
  TOLERANCES (range of acceptable results)
  CONTROL LIMITS (the boundaries of common variation in a statistically stable process)

## Slide 7: KEY CONCEPTS FOR PROJECT QUALITY MANAGEMENT COST OF QUALITY
Cost of Preventing nonconformance
Cost of appraising the product for conformance
Cost of nonconformance
(failure)
Internal Failure
Found by Project Team
External Failure
Found by customer

## Slide 8: KEY CONCEPTS FOR PROJECT QUALITY MANAGEMENT LEVELS OF QUALITY MGMT
External letting the customer find the defects
Costs: Warranty, recalls, rework, reputation
Internal Detect and correct defects before delivery
Costs: Quality control & inspection costs
Assurance Examine & correct process, not just defects
Costs: Quality assurance process costs
Prevention Incorporate quality into planning & design of the project and product
Culture Create a culture of quality awareness and commitment to quality throughout the organization

## Slide 9: TRENDS IN PROJECT QUALITY MANAGEMENT
The approach to quality management intends to be compatible with ISO 9000 and 10000 series of standards and guidelines. Project teams should follow the quality management plan and should have data to demonstrate compliance with the plan. Modern trends in Project Quality Management include:
  Customer Satisfaction: Understanding, evaluating and managing conformance to customer requirements and fitness for use. In Agile environments, stakeholder engagement with the team ensures maintenance of customer satisfaction.
  Continuous Improvement: Plan-Do-Check-Act cycle, in addition to initiatives such as TQM, Six Sigma, and Lean Six Sigma, may improve both the quality of Project Management and the deliverables.
  Management Responsibility: Participation of all project team members. Management retains quality responsibility and must provide suitable resources at adequate capacities
  Mutually Beneficial Partnership with Suppliers: Organizations that develop mutually beneficial long-term relationships with their suppliers, create value for each other, enhance the joint responses to customer needs and expectations and optimize costs.

## Slide 10: TAILORING CONSIDERATIONS
Project Quality Management processes should be tailored to the unique attributes of every project. In this respect appropriate responses to the following must be decided:
What Policy Compliance and auditing approaches should be applied?
What specific quality standards and regulatory compliances should be considered?
How would quality improvement should be managed?
How could a collaborative engagement be created and sustained with stakeholders and suppliers?

## Slide 11: CONSIDERATIONS FOR AGILE ENVIRONMENTS
The Agile approach has built-in quality review steps, performed frequently throughout the project rather than towards the end. These steps are:
Retrospective reviews, recurring regularly, check the effectiveness of the quality processes, look for the root causes for issues and suggest improvements.
Incremental delivery, focusses on small batches of work, hence uncovering inconsistencies and quality issues is done earlier in the project life cycle, at lower costs.

## Slide 12: PROJECT QUALITY MANAGEMENT
ISO - International Organization for Standardization
ISO 9000 - Quality Management Systems - fundamentals and vocabulary which establishes the terminology and definitions used. (revised 2000)
ISO 9001 - defines the model for a quality management system that address both the quality assurance of product and / or service and customer satisfaction (revised 2000)
ISO 9002 - defines the quality system for quality assurance in production and installation (withdrawn in revised 2000)
ISO 9003 - defines the quality system model for quality assurance in final inspection (withdrawn in revised 2000)
ISO 9004 - provides the quality guidelines for any organization wishing to develop and implement a quality system (revised 2000)
ISO10,006 - defines quality in project management
ISO14,000 - defines quality in the manufacturing processes as it relates to the environment

## Slide 13: THE INFLUENCERS
Dr. Deming
pioneered the use of statistics and sampling methods from 1927 - 1940
developed the 14 points to quality improvement
Joseph Juran
began conducting quality courses in Japan in 1954, four years after Dr. Deming
also developed the 10 Steps to Quality Improvement
Philip Crosby
developed the Four Absolutes of Quality

## Slide 14: DEMING’S 14 POINTS
1. Create constancy of purpose.
2. Adopt the new philosophy.
3. Cease dependence on inspection to achieve quality.
4. End the practice of awarding business on the basis of price tag. Instead, minimize total cost.
5. Improve constantly and forever.
Institute training on the job.
7. Institute leadership.
8. Drive out fear.
9. Break down barriers between departments.
10. Eliminate slogans, exhortations, and targets for the work force asking for zero defects and new levels of productivity.

## Slide 15: DEMING’S 14 POINTS
11. Eliminate work standards (quotas) on the factory floor.
12. Remove barriers that rob the hourly worker of his right to pride of workmanship.
13. Institute a vigorous program of education and self improvement.
14. Put everybody in the company to work to accomplish the transformation.

## Slide 16: SEVEN DEADLY DISEASES IN QUALITY MANAGEMENT
1. Lack of constancy of purpose.
2. Emphasis on short-term profits.
3. Evaluation by performance, merit
or annual review of performance.
Mobility of management.
5. Running a company on visible figures alone.
6. Excessive medical costs for employee health care, which increase the final costs of goods and services.
7. Excessive costs of warranty, fueled by lawyers who work on the basis of contingency fees.

## Slide 17
Act
Plan
Check
Do
Immediate Remedies
Future Actions
Against Objectives
How Methods Executed
Train
Execute
Objectives
Methods
THE DEMING CYCLE FOR IMPROVEMENT

## Slide 18: DR. JOSEPH JURAN
Developed the 10 Steps to Quality Improvement
Trilogy:
  Quality Improvement
  Quality Planning
  Quality Control
Stresses
  Customer View is fitness for use
  Manufacturers view is adherence to requirements

## Slide 19: DR. JOSEPH JURAN
Identified the legal implications of quality
  Criminal liability
  Civil liability
  Appropriate corporate actions
  Warranties

## Slide 20: PHILLIP CROSBY
Identified nonconformance averages 40% of operating costs in manufacturing
Developed his 14 Steps to Quality Improvement

## Slide 21: THE ABSOLUTES
Quality means conformance to requirements.
Quality comes from prevention.
Quality means that the performance standard is zero defects.
Quality is measured by the cost of nonconformance.

## Slide 22: QUALITY CHARACTERISTICS
Producibility
Usability
Reliability (Mean Time Between Failures (MTBF))
Maintainability (Mean Time to Repair ( MTTR))
Availability (MTBF and MTTR))
Operability
Flexibility
Social Acceptability
Affordability

## Slide 23: QUALITY CHARACTERISTICS
The totality of characteristics of an entity that bear on its ability to satisfy stated or implied needs
Low quality is always a problem
Low grade may not be a problem
Project manager responsible for delivering the required levels of both quality and grade

## Slide 24: QUALITY RESPONSIBILITY
The integration of all quality participants centers around the project and is the responsibility of the project manager
The PM selects the procedures and policies for the project and therefore controls quality
The PM must foster trust and cooperation among the team members for quality measures to be effective

## Slide 25
PROJECT MANAGEMENT PROCESSES
Initiating
Processes
Planning
Processes
Controlling
Processes
Executing
Processes
Closing
Processes
Quality Planning
Quality
Management
Quality Control
Adopted from PMI’s PMBOK® Guide

## Slide 26
8.1 PLAN QUALITY MANAGEMENT
Adopted from PMI’s (PMBOK® Guide)

## Slide 27: 8.1 PLAN QUALITY MANAGEMENT
Involves identifying which quality requirements/standards that are relevant to the project and determining how to satisfy them.
Is a key facilitating process during project planning and should be performed regularly and in parallel with the other project planning processes
The Scope and Procurement processes will focus more heavily on product quality, while time, cost, risk and integration processes focus more on project quality needs
Adopted from PMI’s (PMBOK® Guide)

## Slide 28: 8.1 – PLAN QUALITY MANAGEMENT
1 Quality Mgmt Plan
2 Quality Metrics
3 Project Mgmt. Plan
updates
Risk Mgmt. Plan
Scope Baseline
4 Project Doc Update
Lessons learned Reg.
Req. Traceability Matrix
Risk Register
Stakeholder Register
1 Expert Judgement
2 Data Gathering
Benchmarking
Brainstorming
Interviews
3 Data Analysis
Cost/Benefit Analysis
Cost of Quality
4 Decision Making
Multicriteria Decision
5 Data Representation
Flowcharts
Logical Data Model
Matrix Diagrams
Mind Mapping
6 Test and Inspection plng
7 Meetings
1 Project Charter
2 Project Mgmt. Plan
Req. Mgmt. Plan
Risk Mgmt. Plan
Stakeholder Mgmt. plan
Scope Baseline
3 Project Documents
Assumption Log
Requirements Doc.
Req. Traceability Matrix.
Risk Register
Stakeholder Register
4 Entr. Env. Factors
5 Org. Process Assets
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools &
Techniques
Outputs

## Slide 29: 8.1 PLAN QUALITY MANAGEMENT – DATA FLOW DIAGRAM

## Slide 30: 8.1.1 PLAN QUALITY MANAGEMENT : INPUTS
.1 Project Charter
Provides high-level project and product information, project approval requirements, objectives and success criteria that influence project quality planning.
.2 Project Management Plan
Requirements Management Plan describes the approach for identifying, analyzing and managing requirements, that the quality management plan and the quality metrics will reference.
Risk Management Plan identifies project risks that the quality management plan should consider to successfully deliver the product.
Stakeholder Engagement Plan documents stakeholders' needs and expectations that influence the Quality Management Plan
Scope Baseline identifies suitable quality standards and objectives that project deliverables and processes will be subjected to during quality review. Defines acceptance criteria, which in turn impact quality cost and therefore project costs, to successfully meet stakeholders’ needs.

## Slide 31: 8.1.1 PLAN QUALITY MANAGEMENT : INPUTS
.3 Project Documents
  Assumption Log provides quality assumptions and constraints.
  Requirements Documentation describes requirements that influence quality management plan for the team to implement
  Requirements Traceability Matrix provides overview of the tests required to verify requirements
  Risk Register provides information on risks that may impact quality requirements
  Stakeholder Register identifies stakeholders who have particular interests that impact quality.
  .4 Enterprise Environmental Factors
  Governmental regulations, rules, standards, guidelines, market conditions, working conditions, cultural perspectives, geographic distribution, and organizational structure.
  .5 Organizational Process Assets
  Quality Management Systems, policies, procedures, guidelines, templates, historical databases and lessons learned.

## Slide 32: 8.1.1 PLAN QUALITY MANAGEMENT : INPUTS
.5 Organizational Process Assets (cont’d)
  Good Quality Policies include:
    Principle stating “what”; i.e., objectives…not “how”
    Promotes consistency throughout the organization
    Explains how the organization views quality
    Provides specific guidelines
    Includes guidelines for updating and changing the policy
Good Objectives should be:
  Specific
  Measurable
  Agreed upon
  Realistic
  Timely

## Slide 33: 8.1.2 PLAN QUALITY MANAGEMENT : TOOLS & TECHNIQUES
.1 Expert Judgement
Specialized knowledge or training in Quality Management processes, including: assurance, control, measurements, improvements and systems, should be considered.
.2 Data Gathering
Benchmarking comparing planned project quality standards to those of similar projects to identify best practices, generate ideas for improvement, and provide a basis for measuring performance.
Brainstorming to creatively gather information from SME’s to develop the quality management plan that best fits the project.
Interviews with experienced project stakeholders and SME’s to identify product quality needs and expectations.

## Slide 34: 8.1.2 Plan Quality MANAGEMENT: TOOLS & TECHNIQUES
.3 Data Analysis
Benefit/cost analysis Used to estimate the strengths and weaknesses of alternatives for meeting quality requirements, and choosing the alternative that provides higher productivity, lower costs and increased stakeholder satisfaction
Cost of Quality (COQ) Cost of quality is the total expenditure on all the efforts to achieve product or service quality. This includes all the work to build a product or service that conforms to the requirements as well as all work resulting from nonconformance to requirements.
  Conformance Costs: Spent during the execution of the project to avoid failure
Nonconformance Costs: Spent during and after the project because of failure in meeting quality requirements

## Slide 35: 8.1.2 Plan Quality MANAGEMENT: TOOLS & TECHNIQUES
COQ
Cost of Conformance
Preventive Costs
Appraisal Costs
Cost of
Nonconformance
Internal Failure Costs
External Failure Costs
Training
Document
Processes
Equipment
Time to do it Right
Testing
Destructive
Testing Loss
Inspections
Rework
Scrap
Liabilities
Warranty Work
Lost Business

## Slide 36: 8.1.2 Plan Quality MANAGEMENT: TOOLS & TECHNIQUES
.4 Decision Making
Can be used to identify key issues and suitable alternatives to be prioritized as a set of decisions for implementation. Criteria are prioritized and weighted and applied to the various alternatives. A numerical score is calculated for each. The alternative with the highest score is selected.
.5 Data Presentation
Flowcharts display the sequence of steps and the possible branching alternatives for a process that transform inputs into outputs.
  Flowcharts show the activities, decision points, branching loops, parallel paths, and the overall order of processing by mapping procedural details within a horizontal chain.
  Flowcharts help understanding the COQ for a process, and estimates by using the payoffs and the probabilities of workflow branches to calculate the expected monetary values for the conformance and non-conformance work required to deliver the expected conforming output

## Slide 37: 8.1.2 Plan Quality MANAGEMENT: TOOLS & TECHNIQUES THE SIPOC Model
Adopted from PMI’s PMBOK® Guide 6th Edition fig 8.6 page 285

## Slide 38: 8.1.2 Plan Quality MANAGEMENT: TOOLS & TECHNIQUES
.5 Data Presentation (cont’d)
Logical Data Model graphical display of an organization’s data, described in a business language. Useful for identifying data integrity or other quality issues.
Notes
A logical data model or logical schema is a data model of a specific problem domain expressed independently of a particular database management product or storage technology, but in terms of data structures such as relational tables and columns, object-oriented classes, or XML tags.

## Slide 39: 8.1.2 Plan Quality MANAGEMENT: TOOLS & TECHNIQUES
.5 Data Presentation (cont’d)
Matrix Diagrams are tool that allows a team to identify the presence and strengths of relationships between two or more lists of items. It provides a compact way of representing many-to-many relationships of varying strengths.
Depending on how many factors may be compared, the diagram could be L, T, Y, X, C, or roof shaped.
The process identifies the key quality metrics that are important for the success of the project

## Slide 40: 8.1.2 Plan Quality MANAGEMENT: TOOLS & TECHNIQUES
.5 Data Presentation (cont’d)
Mind Mapping
A graphical way to represent ideas and concepts. It is a visual thinking tool that helps structuring information, helping you to better analyze, comprehend, synthesize, recall and generate new ideas. Just as in every great idea, its power lies in its simplicity.
The technique may help in rapidly gathering of project quality requirements, constraints, dependencies and relationships

## Slide 41: 8.1.2 Plan Quality MANAGEMENT: TOOLS & TECHNIQUES
.6 Test and Inspection Planning
Created to determine how the project’s product, deliverable or service will be inspected and tested, to meet the stakeholders’ needs and expectations, as well as meeting the deliverable’s performance and reliability goals.
.7 Meetings
Held by the team to develop quality management plan. Participants should include all project stakeholders who are responsible for quality management activities.

## Slide 42: 8.1.3 Plan Quality MANAGEMENT : OUTPUTS
.1 Quality Management Plan
  Is a component of the Project Management Plan, that describes:
    How the organization’s quality policies, procedures, and guidelines will be implemented to achieve the quality objectives.
    The activities and resources necessary for implementing the quality management plan
    The components of the plan:
      Quality standards and objectives
      Roles and responsibilities
      Deliverables and processes to be reviewed
      Quality control and management activities
      Procedures for dealing with nonconformance, corrective actions, and continuous Quality Improvement Plan

## Slide 43: 8.1.3 Plan Quality MANAGEMENT OUTPUTS
Process Improvement Plan
    A subsidiary of the project management plan, that details the steps for analyzing processes that will facilitate the identification of waste and non-value added activity. Includes:
    - Process description - Targets for improvement
    - Process boundaries - Improvement approach
    - Process configuration - Process flowchart
    - Process metrics
.2 Quality Metrics
  Describes “what” something is and “how” it will be measured in very specific terms
  The team must decide what quality characteristics will be measured and decide how the measurement will be taken - this is sometimes called metrics in some application areas

## Slide 44: 8.1.3 Plan Quality MANAGEMENT: OUTPUTS
  .3 Project Management Plan Updates
  The components that may need updating include, but not limited to, are:
  Risk Management Plan, Changes in the quality management approach may require changes to managing project risk.
  Scope Baseline may change due to addition of quality management activities. The WBS dictionary also needs to be updated.
  .4 Project Documents Updates
  Lessons Learned updated with information on challenges faced during the quality planning process
  Requirements Traceability Matrix updated to record processes specified by the quality management plan
  Risk Register updated to record new risks identified by the process
  Stakeholder Register updated to record new information identified by the process.

## Slide 45: 8.2 PERFORM QUALITY ASSURANCE
Adopted from PMI’s (PMBOK® Guide)

## Slide 46: 8.2 MANAGE QUALITY
Quality Management involves Quality Assurance (QA). The focus of QA is on ensuring that the project management processes are used effectively, and meet the standards to assure stakeholders that the final product will meet their needs, expectations and requirements
Manage Quality activities help to
  Implement design guidelines to address specific product features
  Build confidence that the product will meet specific requirements and expectations, when verified through QA tools and audits
  Confirm that quality processes are used and their use meets the quality objectives
  Improve the efficiency and effectiveness of quality processes
The project team uses the organization’s QA department tools and resources to implement some activities such as : failure analysis, design of experiments, quality improvement.
Managing quality is the work of everybody, with varying roles throughout the project life-cycle.
Adopted from PMI’s (PMBOK® Guide)

## Slide 47: 8.2 MANAGE QUALITY – DATA FLOW DIAGRAM
Adopted from PMI’s PMBOK® Guide 6th Edition fig 8.8 page 289

## Slide 48: 8.2 MANAGE QUALITY
1Quality Reports
2Test and Evaluation
Documents
3 Change Requests
4 Project Mgmt. Plan
Updates
Quality measurements plan
Scope Baseline
Schedule baseline
Cost baseline
5 Project Docs Updates
Issue log
Lessons learned register
Risk register
1 Project Mgmt. Plan
Quality Mgmt. Plan
2 Project Documents
Lessons Learned
Register
Quality Control
measurements
Quality metrics
Risk reports
3 Org Process Assets
1 Data Gathering
Checklists
2 Data Analysis
Alternatives Analysis
Document Analysis
Process Analysis
Root cause Analysis
3 Decision Making
Multi-criteria Decision
Analysis
4 Data Presentation
Affinity Diagrams
Cause & Effect Diag.
Flowcharts
Histograms
Matrix Diagrams
Scatter Diagrams
5 Audits
6 Design for X
7 Problem Solving
8 Quality Improvement
methods
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools and
Techniques
Outputs

## Slide 49: 8.2.1 MANGE QUALITY : INPUTS
.1 Project Management Plan
Quality Management plan
  A description of how the team will implement the quality policy
  Defines the acceptable level of project and product
  Describes how to ensure this level of quality in deliverables and processes
  It must address what to do with nonconformance and what corrective action to consider
  2 Project Documents
  Lessons Learned Register describes what has been learned from previous activities that can improve the effectiveness of quality mgmt.
  Quality Control Measurements used to analyze and evaluate and validate project/product quality with standards.
  Quality Metrics used as basis for the development of test scenarios for the project/product and as a basis for improvement initiatives
  Risk Report identifies sources of project risk and drivers of overall risk that can impact project quality objectives.

## Slide 50: 8.2.1 MANGE QUALITY : INPUTS
.3 Organizational Process Assets
Manage Quality can be influenced by organizational
Quality management policies, procedures, and guidelines
Templates for: Check Sheets, Traceability Matrix, Test Plans, Test Documents, etc.
Results from previous audits
Lessons learned from similar projects

## Slide 51: 8.2.2 MANAGE QUALITY : TOOLS & TECHNIQUES
.1 Data Gathering
Checklists a structured tool used to verify that a set of required steps have been performed, or to check that requirements have been met.
2 Data Analysis
Alternatives analysis evaluates options and selects most appropriate
Document Analysis documents produced as outputs of various project control processes can point to out of control processes
Process Analysis identifies problems, constraints, and non-value added activities, and uses the information to improve processes.
Root Cause Analysis (RCA) used to determine the underlying reasons that cause a variances, defects or risks. When root causes are removed the problem does not recur.
3 Decision Making
Multi-Criteria decision analysis

## Slide 52: 8.2.2 MANAGE QUALITY : TOOLS & TECHNIQUES
.4 Data Representation
  The following tools can be used:
  Affinity Diagrams: used to generate ideas that can be linked to organize a pattern of thought about a problem.
  Cause-and-effect diagrams (fishbone diagrams): used to break down the causes of the problem identified into discrete branches helping to identify the main root cause.
  Flowcharts: shows a series of steps that lead to defect
  Histograms: useful in showing numerical data, such as number of defects per deliverable, a ranking of the causes, the number of times each process is noncompliant.
  Matrix Diagrams: shows strength of relationships among factors, causes and goals that exists between the rows and the columns of the matrix.
  Scatter Diagrams demonstrate relationships between any element of a process, environment or activity one axis and a quality defect on the other axis.

## Slide 53: 8.2.2 MANAGE QUALITY : TOOLS & TECHNIQUES
.5 Audits
  An independent process used to determine if project activities, comply with organizational and project policies, processes, and procedures. Quality audits are usually performed by external teams. Audit objectives include:
  Identifying all good and best practices being implemented
  Identifying all nonconformities, gaps and shortcomings
  Sharing good practices identified or practiced with similar projects
  Assisting to improve implementation processes to augment productivity
  Documenting audit findings in lessons learned
  6 Design for X (DfX)
  A set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect “X” of the product. “X” could be reliability, cost, deployment, manufacturability etc. Using DfX may result into cost reduction, quality improvement or better performance for customer satisfaction

## Slide 54: 8.2.2 MANAGE QUALITY : TOOLS & TECHNIQUES
.7 Problem Solving
  Effective and systematic problem solving is a fundamental tool for Quality Assurance and Quality Improvement. The method includes:
  Defining the problem
  Identifying the root cause
  Generating possible solutions
  choosing the best solution
  implementing the solution
  verifying solution effectiveness
  6 Quality Improvement Methods
  Plan-do-check-act (PDCA) and Six Sigma are two of the most commonly used tools.
  Improvements are based on findings and recommendations from quality control processes, the findings of quality audits, or problem solving in the Manage Quality process.

## Slide 55
A Cause and Effect Diagram:
Is used to identify the cause of defects. This tool can be helpful in identifying the variable(s) and their sub-variables that can cause problems or defects in the deliverable.

## Slide 56
PROCESS FLOWCHART

## Slide 57
Check sheets or Tally Sheets:
are used to collect frequency data such as the number of times a defect occurs because of a specified variable. The information from check sheets can be used to create a Pareto Diagram to identify and prioritize causes of defects.

## Slide 58
Histograms:
are bar charts that are usually shaped like a bell curve to display a discrete statistical distribution. The histogram below shows the number of calls into the help desk based on the hour of the da. The data can be used for staffing the desk to ensure the required service quality level.
Chart: 
| 0.29166666666666669 | 0.33333333333333298 | 0.375 | 0.41666666666666702 | 0.45833333333333298 | 0.5 | 0.54166666666666696 | 0.58333333333333304 | 0.625 | 0.66666666666666696
 | 16 | 24 | 34 | 47 | 45 | 38 | 36 | 34 | 18 | 12
Number of calls
Time of the day

## Slide 59
Pareto Charts:
Are bar charts that are used to identify the most frequent causes of an event.
# of occurrences
These charts are useful
throughout the project.
In the beginning, to identify
problems and later on to
narrow the problems
down to the “Vital Few”
Problems being measured
Cumulative
Percentage

## Slide 60
Control Charts
  A graphic display of results of a process, over time
  Used to determine if a process is ‘in control’
  May be used to monitor any type of output variable
    repetitive activities
    cost and schedule variances
    volume and frequency of scope changes
    errors in project documents
  Establishes limits on Run Charts
  Identifies the allowable range of variation for a specific product characteristic
  Establishing upper and lower bounds assists in establishing conformance to standards
  Upper boundary is known as the Upper Control Limit (UCL) and lower is the Lower Control Level (LCL)

## Slide 61: Control Charts
Measurement
Time
0
UCL
LCL
Mean
Process
Average
Process Average is the mean of the averages of
samples taken over a period of time.
Adopted from PMI’s (PMBOK® Guide)

## Slide 62: Control Charts
Measurement
Time
0
UCL
LCL
Mean
Allowable
Range of
Variation
Beyond acceptable ranges
Adopted from PMI’s (PMBOK® Guide)

## Slide 63: Control Charts
Measurement
Time
0
UCL
LCL
Mean
Allowable
Range of
Variation
Possible problem - 7 points below
(or above) the mean
known as the Rule of 7
Adopted from PMI’s PMBOK® Guide

## Slide 64
Scatter Diagrams:
Plot the relationship of two variables. These variables make up the x and y axis. For example plotting the amount of budget spent on a task and the remaining duration of the task would show as a negative correlation. The duration should shrink as more budget is spent. Alternatively, if the resources added to the task were plotted against the budget spent would show a positive correlation.
Highly Negative
Highly Positive
Low to Moderate
Negative
No correlation

## Slide 65: 8.2.3 PERFORM QUALITY ASSURANCE: OUTPUTS
.1 Quality Reports
These reports may include information about quality management issues escalated by the team, improvement recommendations, correction actions recommendations, control quality process findings, to be used to meet quality expectations.
.2 Test and Evaluation Documents
These documents are created, based industry needs, and are used as to evaluate the achievement of quality objectives.
.3 Change Requests
Submitted to request approval for changes occurring during the manage quality process, that impact the project management plan or the project documents. These requests follow the Integrated Change Control process.

## Slide 66: 8.2.3 PERFORM QUALITY ASSURANCE: OUTPUTS
.4 Project Management Plan Updates
Components of the plan that may require updates include:
Quality Management Plan updated to reflect actual results
Scope Baseline updated to reflect specific quality mgmt. activities
Schedule Baseline updated to reflect specific quality mgmt. activities
Cost Baseline updated to reflect the cost of specific quality mgmt. activities
  .5 Project Documents Updates
  Documents that may require updates include:
  Issue Log to record new issues
  Lessons Learned Register updated with information on challenges encountered, how they have been avoided, or how well the resolutions worked.
  Risk Register updated to record new risks identified.

## Slide 67
8.3 CONTROL QUALITY
Adopted from PMI’s (PMBOK® Guide)

## Slide 68: 8.3 CONTROL QUALITY
Involves monitoring specific project results to determine if they comply with relevant quality standards and to identify ways to eliminate causes of unsatisfactory results
Should be performed throughout the project
Includes product results such as deliverables and project management results such as cost and schedule performance
It is often performed by the quality control department…but it does not have to be
In Agile projects, the Control Quality activities may be performed by all team members throughout the project life-cycle. In waterfall approach the process is performed at specific times, towards the end of the project, by specific team members.
A working knowledge of Statistical Quality Control is necessary for the process.

## Slide 69: 8.3 CONTROL QUALITY – DATA FLOW DIAGRAM
Adopted from PMI’s PMBOK® Guide 6th Edition fig 8.11 page 299

## Slide 70: CONTROL QUALITY TERMINOLOGY
Prevention
    keeping errors out of the process
Inspection
    keeping errors out of the hands of the customer
Attribute Sampling
    the result either conforms or it does not
Variables Sampling
    the result is rated on a continuous scale that measures the degree of conformity
  Tolerances
    Range of specified acceptable results and control limits that identify the boundaries of a statistically stable process.

## Slide 71: CONTROL QUALITY TERMINOLOGY
Random Causes (Common Causes)
  Normal process variations occurring with no assignable causes
  Typically due to a large number of small sources of variations that may result in a high level of variations or mistakes and/or defects
  Sum of the common causes determines the inherent variation of the process
  Determines a product’s limits and its capability as it currently operates
Special Causes
  Variation not part of the process all the time. Unusual event.

## Slide 72: 8.3 CONTROL QUALITY
1 Quality Control
Measurements
2 Verified Deliverables
3 Work performance
information
4 Change Requests
5 Project Management
Plan Updates
6 Project Document
Updates
Issue log
Lessons learned Reg.
Risk register
Test & Evaluation
documents
1 Project Mgmt. Plan
Quality Mgmt. plan
2 Project Documents
Lessons learned Reg.
Quality Metrics
Test & Evaluation docs
3 Approved Change
Requests
4 Deliverables
5 Work Performance
Data
6 Ent. Env. Factors
8 Org Process Assets
1 Data gathering
Checklists
Check sheets
Statistical sampling
Questionnaires
2 Data Analysis
Performance reviews
Root cause analysis
3 Inspection
4 Testing/evaluations
5 Data presentation
cause/effect diag.
control charts
Histogram
Scatter diagrams
6 Meetings
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools and
Techniques
Outputs

## Slide 73: 8.3.1 CONTROL QUALITY: INPUTS
.1 Project Management Plan
  Contains Quality Management Plan, that provides details regarding how quality control will be performed.
.2 Project Documents
Lessons Learned Register
Quality Metrics describes the process and the attributes to be met.
Test & Evaluation Documents used to evaluate achievement of quality objectives.
.3 Approved Change Requests
Used to verify the timely implementation of approved repairs, revised work methods, revised schedule, etc.
.4 Deliverables
Completed outcomes of project work to be inspected for quality.

## Slide 74: 8.3.1 CONTROL QUALITY: INPUTS
.5 Work Performance Data
  Planned vs. Actual Technical performance data
  Planned vs. Actual Cost and Schedule performance data
  Deliverables completion status
  Implementation of required corrective actions
  .6 Enterprise Environmental Factors
  PMIS; Quality Management Software to track errors and variations in process or deliverables.
  Regulations, rules, and application specific guidelines.
.7 Organizational Process Assets
Quality standards and policies
Templates, such as check sheets
Defect reporting procedures and communication policies.

## Slide 75: 8.3.2 CONTROL QUALITY: TOOLS & TECHNIQUES
.1 Data Gathering
Checklists help manage control quality activities
Check Sheets (tally sheets) facilitate the organized collection of useful data about potential quality problems.
Statistical Sampling
  Involves choosing part of a population of interest for inspection (e.g. selecting 10 engineering drawings at random from a list of 75)
  Sampling can often reduce the cost of quality control
  Is used to measure variability in a product for evaluation and corrective action
  Questionnaires and Surveys used to gather customer satisfaction data about the deployment of a product or a service.
.2 Data Analysis
Performance Reviews measure compare and analyze established quality metrics with actual results
Root Cause Analysis (RCA)

## Slide 76: 8.3.2 CONTROL QUALITY: TOOLS & TECHNIQUES
  .3 Inspection
  Includes activities such as measuring, examining and testing undertaken to determine whether results conform to requirements
  Inspections may be conducted at any level - a single activity, the final product or the project
  Inspections are variously called reviews, product reviews, walkthroughs, and audits
  .4 Testing / Product Evaluation
  Testing is an organized investigation to find errors, defects, bugs, or other non-conformances.
  Software testing may include: unit testing, integration testing, interface testing, regression testing, alpha testing, etc.
  In construction testing may include: concrete quality, soil tests etc.

## Slide 77: 8.3.2 CONTROL QUALITY: TOOLS & TECHNIQUES
.5 Data Presentation
Cause and Effect Diagrams used to identify possible causes for defects
Control Charts used to determine the stability and predictability of a process. Most frequently used to track repetitive activities, they can also be used to monitor cost and schedule variances, volume, frequency of scope changes or other management results to determine if the project management processes are in control
Histograms used to demonstrate the number of defects by source or by component
Scatter Diagrams show the planned performance on one axis and the actual performance on the other axis.
.6 Meetings
Approved change requests review to verify that approved changes were implemented as approved.
Retrospectives/Lessons Learned held to discuss successful elements in the project, identify improvements, what to incorporate in the current and future projects, what to add to the organizational process assets

## Slide 78: 8.3.3 CONTROL QUALITY : OUTPUTS
.1 Quality Control Measurements
  QC results that are fed back to QA to reevaluate and analyze the quality standards and processes of the implementing organization.
.2 Verified Deliverables
  The results of the execution of the quality control processes are verified deliverables, that become an input to Validate Scope process, for formal acceptance.
  3 Work Performance Information
  Obtained from analyzing the performance data collected from various controlling processes. Example: information about requirements fulfillment, such as causes for rejection, required rework, or the need for process adjustment.

## Slide 79: 8.3.3 CONTROL QUALITY : OUTPUTS
.4 Change Requests
  To recommended corrective or preventive actions or repairs, identified during the quality control process, should be formally requested and approved for implementation.
.5 Project Management Plan Updates
  Updates to quality management plan and process improvement plan would be required to reflect changes and adjustments
.6 Project Document Updates
  Updates would be needed to the following documents:
  Issue Log to record deliverables that fail quality requirements
  Lessons Learned Register updated with information on the source of quality defects, possible ways of avoiding them, and what worked well
  Risk Register to record new risks identified during control quality process.
  Test and evaluation documents may be updated as a result of this process for more effective testing in future projects