## Slide 1: PMP® Exam Preparation Workshop PMP250
Project Management Professional, (PMP), is a registered mark of the Project Management Institute , Inc.
Session # 7
Project Resources Management

## Slide 2
The contents of this lesson are based on:
A Guide to Project Management Body of Knowledge (PMBOK® Guide)
Sixth Edition
Published and Owned by
Project Management Institute, PMI®
PMBOK, PMP, CAPM and PMI are registered trade marks of Project Management Institute, Inc.

## Slide 3: PROJECT RESOURCE MANAGEMENT
This Knowledge Area includes the processes of Identifying, Acquiring and Managing, the Human and Physical resources needed for the successful implementation of the project
Physical Resources include equipment, materials, facilities, and infrastructure.
Human Resources are personnel of varied skill sets and competencies, that are assigned full or part-time, and may be added or removed from the project team as time progresses.
The project manager needs to master the distinct competencies needed for managing both type of resources.

## Slide 4
9.0 PROJECT RESOURCE MANAGEMENT
Adopted from PMI’s (PMBOK® Guide)

## Slide 5: KEY CONCEPTS FOR PROJECT RESOURCE MANAGEMENT
Human Resources are the individuals of the project team with assigned roles and responsibilities who work collectively to achieve the project goal.
The project manager is responsible for acquiring, managing, empowering and motivating the project team
Ideally, all team members should be involved, by adding their expertise in planning and decision making
The project manager should be aware the different aspects that influence the team, such as: team environment, geographical location, communications, change management, politics, cultural issues, etc.
The project manager, as a leader, is also responsible for developing team skills, retaining, motivating and improving team satisfaction.
The project manager should be aware of and subscribe to professional and ethical behaviour, and be a role model for the team.

## Slide 6: KEY CONCEPTS FOR PROJECT RESOURCE MANAGEMENT
Physical Resources include material, equipment, supplies, infrastructure, needed for successful completion of the project.
Managing physical resources in an effective and efficient manner requires reliable data to determine current and future demand, resource configurations will be required to meet those demands and the supply of resources.
Failing to efficiently manage and control resources, would impact successful project completion due to:
  Delays in manufacturing the final product by failing to secure critical equipment or infrastructure
  Impacting the product quality by ordering low-quality material
  Mismanaging material inventory would impact project cost, profits and customer satisfaction.

## Slide 7
9.1 PLAN RESOURCE MANAGEMENT
Adopted from PMI’s (PMBOK® Guide)

## Slide 8: 9.1 PLAN RESOURCES MANAGEMENT
The process defines how to estimate, acquire, manage and deploy human (i.e., team members) and physical resources (i.e., supplies material, equipment), sufficient for the successful completion of the project
The approach and level of management effort should be appropriate to the complexity of the project.
The required resources can be obtained from organization’s internal assets, or procured externally from supplier, in accordance with agreements.
Other projects may be competing for the same resources at the same time. This may significantly impact project costs, schedules, risks, quality and scope.
Adopted from PMI’s (PMBOK® Guide)

## Slide 9: 9.1 PLAN RESOURCES MANAGEMENT
1 Resource
Management Plan
2 Team Charter
3 Project Doc. Updates
Assumption Log
Risk Register
1 Expert Judgment
2 Data representation
Hierarchical Charts
RAM
Text Oriented formats
3 Organizational Theory
4 Meetings
1 Project Charter
2 Project Mgmt. Plan
Quality Mgmt. Plan
Scope Baseline
3 Project Documents
Project Schedule
Requirements Doc.
Risk Register
Stakeholder Register
4 Enterprise Env. Factors
5 Org. Process Assets
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools &
Techniques
Outputs

## Slide 10: 9.1.1 PLAN RESOURCES MANAGEMENT: INPUTS
.1 Project Charter
Provides high-level information about the project, stakeholders, requirements, also preapproved financial allocation that may impact resource management of the project
.2 Project Management Plan
Provides the following relevant information:
Scope Baseline
Quality Management Plan to determine quality related resources

## Slide 11: 9.1.1 PLAN RESOURCES MANAGEMENT: INPUTS
.3 Project Documents
Project Schedule
Requirements Documentation
Risk Register
Stakeholder Register
.4 Enterprise Environmental Factors
The factors that can influence Resource Management:
Organizational Culture and Structure
Existing Resources competencies and availability
Geographical Locations of facilities and resources
Market Conditions
.5 Organizational Process Assets
HR and physical Resources Policies and procedures
Safety and security policies
Templates for resource management
Historical information from similar projects

## Slide 12: 9.1.2 PLAN RESOUCE MANAGEMENT: TOOLS AND TECHNIQUES
1. Expert Judgement
Expertise in the following areas should be considered:
- Negotiation for resources - Mgmt. & personnel development - Determining needed effort - Determining reporting needs
- Procurement & market conditions - Human resources management
2. Data Representation
Various formats can be used to ensure that each work package has an unambiguous owner, and the team members’ role and responsibilities are well understood. These displays include:
Hierarchical Charts
Work Breakdown Structure
Organizational Breakdown Structure
Resource Breakdown Structure
Assignment Matrix – (RAM or RACI Chart)
Textual formats

## Slide 13: 9.1.2 PLAN RESOURCES MANAGEMENT: TOOLS & TECHNIQUES
Organizational Charts and Position Descriptions
  - Three formats for roles & responsibilities
Adopted from PMI’s PMBOK® Guide

## Slide 14: 9.1.2 PLAN RESOURCES MANAGEMENT: TOOLS & TECHNIQUES
  Matrix – Based Charts
    Responsibility Assignment Matrix (RAM), shows connection between work and people
    RACI designation.
      Responsible - Consult
      Accountable - Inform
Adopted from PMI’s PMBOK® Guide

## Slide 15: 9.1.3 PLAN RESOURCES MANAGEMENT: OUTPUTS
.1 Resource Management Plan
Provides guidance on how project resources shall be categorized, allocated managed and eventually released. The plan includes but is not limited to:
Identification of resources; Team and physical
Acquiring resources; Guidance how to acquire resources
Role and responsibilities:
        Role (who does what) and responsibilities (who decides what) must be assigned.
    Authority: The right to apply project resources, make decisions and sign approvals.
        Responsibility: the assigned work that a project team member is expected to perform to complete the project.
  Competence Skill and capacity required to complete project activities

## Slide 16: 9.1.3 PLAN RESOURCES MANAGEMENT: OUTPUTS
.1 Resource Management Plan(cont’d)
Project Organization Chart A graphic display of project team members and their reporting relationships.
Project Team Resource Management guidance on how HR should be defined, staffed, managed, and released.
Training strategies for team members
Team development methods for developing project team
Resource Control. Methods for optimizing and ensuring adequate physical resources are available as needed. Includes managing inventory, equipment and supplies throughout the project.
Recognition plan how team members would be rewarded.
.2 Team Charter
A document that establishes clear expectations regarding acceptable behavior by project team members, in accordance with team values, communication guidelines, decision making process, conflict resolution, meeting guidelines, team agreement. The charter works best when the team develops it.
.3 Project Documents Updates
Assumption Log updated regarding resource availability, logistics, location
Risk Register updated for identified resource-related risks

## Slide 17: 9.2 ESTIMATE ACTIVITY RESOURCES

## Slide 18: 9.2 ESTIMATE ACTIVITY RESOURCES
The process, performed periodically throughout the project as needed, identifies the type, quantity, and characteristics of resources required to complete the project.
Estimating for activity resources must be closely coordinated with other estimating processes, such as cost estimating, and information relevant to the activity being estimated. Examples:
  Estimating the cost of a construction activity needs familiarity with local building codes.
  Estimating the activity of automotive design needs familiarity with automated assembly techniques.

## Slide 19: 9.2 ESTIMATE ACTIVITY RESOURCES DATA FLOW DIAGRAM
Adapted from PMBOK® 6th Edition, Fig 9.6 Page 321

## Slide 20: 9.2.1 ESTIMATE ACTIVITY RESOURCES - INPUTS
.1 Project Management Plan
Resource Management Plan identifies resource sources and quantities
Scope Baseline drives the needs for team and physical resources
.2 Project Documents
Activity Attributes provides primary data needed for estimating and scheduling resources
Activity List identifies activities that need resources
Assumption Log provides productivity, availability, cost, and work approach information.
Cost Estimates may impact resource selection
Resource Calendar Specifies when and for how long resources will be available during the project.
Risk Register provides information that may impact resource selection
.3 Enterprise Environmental Factors
Information regarding resource location, availability, team skills, organizational culture, published estimation data, market conditions.
.4 Organizational Process Assets
Staffing policies, supplier procedures, historical information

## Slide 21: 9.2.2 ESTIMATE ACTIVITY RESOURCES TOOLS & TECHNIQUES
.1 Expert Judgement
Expertise in team and physical resource planning and estimating
.2 Bottom-Up Estimating
physical resources estimated at activity level, and aggregated at work package, control account and project levels.
.3 Analogous Estimating
Estimation based on similar previous projects
.4 Parametric Estimating
Based on algorithm or statistical relationship between historical data and project parameters.
.5 Data Analysis
Alternative analysis is used to evaluate different alternatives and select the best solution to perform the project activities, within the defined constraints.
.6 PMIS
Resource management software
.7 Meetings
Held with Functional managers to Estimate resources per activity. Level of Effort, skill level, and quantity of physical resources.

## Slide 22: 9.2.1 ESTIMATE ACTIVITY RESOURCES OUTPUTS
.1 Resource Requirements
A document that identifies resource types and quantities needed for each activity in the work packages, in each WBS branch which then is aggregated to determine the resources for the entire project. The document can also include assumptions made.
.2 Basis of Estimates
Explains how the estimates were derived, in terms of: methods used, tools used, assumptions made, constraints, ranges, confidence levels, and risks associated with the estimates.
.3 Resource Breakdown Structure
A hierarchical display of all team and physical resources required for projects categorized by type and category.
.4 Project Documents Updates
Activity Attributes updated with resource requirements
Assumption Log updated with estimation assumptions
Lessons Learned updated with effectives estimating techniques used.

## Slide 23: Sample Resource Breakdown Structure
Adapted from PMBOK® 6th Edition, Fig 9.7 Page 327

## Slide 24
9.3 ACQUIRE RESOURCES
Adopted from PMI’s (PMBOK® Guide)

## Slide 25: 9.3 ACQUIRE RESOURCES
Includes the process for:
  Getting the human resources, facilities, equipment materials, supplies, needed to complete the project work.
  Required resources could be acquired internally or procured externally.
  The factors to consider during acquiring project resources include:
    The PM should effectively negotiate and influence those who are in position to provide the required resources.
    Being careful to ensure that the available resources will meet project requirements, as the best are not always available.
    If the team resources are not available due to constraints or assignments to other projects, the PM should assign alternative resources, perhaps with different competencies and costs
    Failure to acquire the necessary resources may impact or project performance or even result in project cancellation
    The impact of unavailability of required resources should be documented.
Adopted from PMI’s (PMBOK® Guide)
Notes: Reality is frequently don’t get a choice!
Work with what you have!

## Slide 26
1 Physical Resource
Assignments
.2 Project Team Assignments
3 Resource Calendars
4 Change Requests
5 Project Mgmt. Plan Updates
  Resource Mgmt. Plan
  Cost Baseline
  6 Project Document Updates
  Lessons learned Register
  Project Schedule
  RBS
  Resource Requirements
  Risk Register
  Stakeholder Register
  7 Ent. Env. Factors updates
  8 Org. Process Assets updates
1 Decision Making
Multicriteria Decision
Analysis
2 Interpersonal & Team
skills
Negotiation
3 Pre-Assignment
4 Virtual Teams
.1Project Mgmt. Plan
Resource Mgmt. Plan
Procurement Mgmt. Plan
Cost Baseline
2 Project Documents
Project Schedule
Resource Calendars
Resource Requirements
Stakeholder Register
3 Enterprise Env. Factors
4 Org. Process Assets
9.3 ACQUIRE RESOURCES
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools &
Techniques
Outputs

## Slide 27: 9.3.1 ACQUIRE RESOURCES - INPUTS
.1 Project Management Plan
Resource Management Plan describes how to acquire project resources
Procurement Management Plan provides information how resources will be acquired from outside.
Cost Baseline provides the budget for project activities
.2 Project Documents
Project Schedule provides information when resources will be required
Resource Calendars. Provides information about when resources are available. Resource calendars are progressively elaborated.
Resource Requirements identifies which resources need to be acquired
Stakeholder register. Reveals stakeholder needs for specific resources
.3 Enterprise Environmental Factors
Resource availability, competence, prior experience, cost, market conditions, organizational structure, geographic locations
.4 Organizational Process Assets
Policies and procedures for acquiring, allocating and managing resources, historical information and lessons learned.

## Slide 28: 9.3.2 ACQUIRE RESOURCES TOOLS & TECHNIQUES
.1 Decision Making
Multi-criteria decision analysis, often used to select project resources. The selection weighted criteria include:
Availability, Cost, Ability
Unique selection criteria for team resources:
  Experience, Knowledge, Skills, Attitude, International factors
  .2 Interpersonal & Team Skills
  Negotiation skills are needed to negotiate with:
  Functional Managers
  Other project management teams within the organization
  External organizations and suppliers
  .3 Pre-Assignment
  Resources that are determined in advance, by being part of a competitive proposal, or project dependency on particular resources.

## Slide 29: 9.3.2 ACQUIRE RESOURCES TOOLS & TECHNIQUES
.4 Virtual Teams
Geographical spread team members with shared goals, who fulfill their roles with little or no face-to-face time spent with other members. Teams members utilize telecommunication technology to collaborate and communicate. Virtual teaming facilitates:
Members of the same organization who live in widespread areas to form teams
Add special expertise to the team from experts from different areas
Work from home
Teams to work different shifts and time zones
Inclusion of mobility challenged people
Reduction of travel expenses
Safe office space
For Virtual teams to work well, it is important to have well planned communications, set clear expectations, develop protocols, understand cultural differences and share credit in successes.

## Slide 30: 9.3.3 ACQUIRE RESOURCES - OUTPUT
.1 Physical Resource Assignments
Documentation to record material, equipment, supplies, locations, and other physical resources needed to complete the project work.
.2 Project Team Assignments
Documentation to record team members, their roles and responsibilities, team directories, organization charts.
.3 Resource Calendars
Identify working days and hours, shifts, weekends, holidays, when specific resources are available and for how ling during the project.
.4 Change Requests
Raised when changes occur as a result of Acquire Resources process, that impact the schedule, or when recommended corrective or preventive actions impact

## Slide 31: 9.3.3 ACQUIRE RESOURCES - OUTPUT
.5 Project Management Plan Updates
Resource Management Plan updated to reflect actual experience in acquiring resources, including lessons learned.
Cost Baseline may require updating as a result of actual acquisitions
.6 Project Documents Updates
Lessons Learned Register updated with information on challenges encountered, and how they could be avoided in the future.
Project Schedule updated to reflect changes resulting from availability of resources.
Resource Breakdown Structure updated to reflect actual acquisitions
Resource Requirements updated to reflect actual acquisitions
Risk Register updated to record new risks identified during the process
Stakeholder Register updated to reflect information about new stakeholders, or new information about existing ones.
.7 Enterprise Environmental Factors Updates
Updates to Available team and physical resources used
.8 Organizational Process Assets Updates
Updates to documentation related to the process, as needed.

## Slide 32: 9.4 DEVELOP TEAM
Adopted from PMI’s (PMBOK® Guide)

## Slide 33: 9.4 DEVELOP TEAM
The process of improving the competence of the team members to enhance project performance. The benefits are:
  Improved teamwork, enhanced people skills and competencies, motivated employees, reduced turnover rates.
  Project Team to function as a team
Project Managers has the primary responsibility for, and requires the skills to identify, build, motivate, lead, inspire and create an environment that facilitates project teams to achieve high teamwork and meet project objectives.
Behaviors that may achieve high-performance teams:
  Open and effective communications
  Team building opportunities
  Developing trust among members
  Constructively managing conflicts
  Encouraging collaborative problem solving and decision making
Adopted from PMI’s (PMBOK® Guide)
Notes: Team development on a project is often complicated when individual team members are accountable to both a functional manager and the project manager. This is referred to as dual reporting relationship.

## Slide 34: 9.4 DEVELOP TEAM
1 Team Performance
Assessment
2 Change Requests
3 Project Mgmt. Plan
Updates
Resource Mgmt. Plan
4 Project Doc. Updates
Lessons Learned Reg.
Project Schedule
Project Team Assign’s
Resource Calendars
Team Charter
5 Ent. Env. Factors Updates
6 Org. Process Assets
Updates
1 Colocation
2 Virtual Teams
3 Comm. Technology
4 Interpersonal & Team
Skills
Conflict Management
Influencing
Motivation
Negotiation
Team Building
5 Recognition & Rewards
6 Training
7 Individual & Team
Assessment
.8 Meetings
1 Project Mgmt. Plan
Resource Mgmt. Plan
2 Project Documents
Lessons Learned Reg.
Project Schedule
Project Team Assign's
Resource Calendars
Team Charter
3 Ent. Env. Factors
4 Org. Process Assets
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools &
Techniques
Outputs

## Slide 35: 9.4.1 DEVELOP TEAM: INPUTS
.1 Project Management plan
  The Resource Management component of the plan Provides guidance how the project should be defined, staffed, managed, controlled and released. Identifies training strategies and team development plans, also addresses such items as rewards, feedback, disciplinary actions, performance assessment etc.
.2 Project Documents
Lessons Learned Register provides team development guidance for the later stages
Project Schedule Identifies the need for variations in the team development strategies
Project Team Assignments Identifies members’ roles and responsibilities
Resource Calendars identifies members’ availability for development activities.
Team Charter describes the team operating guidelines and the structure of collaboration

## Slide 36: 9.4.1 DEVELOP TEAM: INPUTS
.3 Enterprise Environmental Factors
HR Management policies regarding hiring, termination, performance reviews, development and training records, rewards.
Member skills, competencies, specialization
Geographic distribution of team members
.4 Organizational Process Assets
Lessons Learned repository.

## Slide 37: 9.4.2 DEVELOP TEAM TOOLS & TECHNIQUES
.1 Collocation
Collocation of the team, even temporarily, enhances communication and a sense of community among the members.
.2 Virtual Teams
The benefits of using virtual teams include: can bring more skilled people, reduce costs, less travel expenses, proximity to customers or suppliers. Contemporary telecommunications technology facilities virtual working.
.3 Communication Technology
Helps better understanding among members of both collocated and virtual teams. Examples of technology include:
Shared portal websites, internet provide information sharing
Video Conferencing
Audio Conferencing
Email / Chat

## Slide 38: 9.4.2 DEVELOP TEAM TOOLS & TECHNIQUES
.4 Interpersonal & Team Skills
Project Managers use several interpersonal skills to build high-performing teams:
Conflict Management. Conflicts must be resolved in a timely and constructive manner
Influencing. Gathering critical information to address important issues
Motivation. Empowering the team to act independently and participate in decision making
Negotiation. Used to reach consensus and build trust.
Team Building. Activities that enhance team’s social relations and build cooperative working environment. Particularly essential for virtual teams.
.5 Recognition and Rewards
Developed during Plan Resources Management; Effective only when the value is appreciated by a recipient. Most project team members are motivated more by intangible rewards such as: opportunity to grow, recognition, being appreciated, and challenged to apply their professional skills to complex issues.

## Slide 39: 9.4.2 DEVELOP TEAM: TOOLS & TECHNIQUES
.6 Training
  All activities designed to enhance the competencies of the project team
  May be formal or informal
  Certain skills such as management or technical must be developed as part of the project, if lacking the project must be re-staffed.
  .7 Individual and Team Assessment
  Using various tools available, the project manager can assess the team’s and members’ preferences, strengths and weaknesses, to improve understanding, trust and communication among team members and facilitate higher productivity.
.8 Meetings
Held to address pertinent team development topics; types of meetings may include: project orientation, team development and team building meetings

## Slide 40: 9.4.3 DEVELOP TEAM: OUTPUTS
.1 Team Performance Assessments
  The project management team assesses the project team’s performance effectiveness, in terms of technical success, performance on schedule, and on budget. High performance teams are characterized by the following task/result-oriented outcomes:
  Improvement in skills
  Improvement in competencies
  Reduced staff turnover rate
  Increased team cohesiveness: members sharing information and experiences to help each other and improve project performance.
  Based on these assessments, the management team can identify specific training , mentoring, coaching assistance or changes required to improve the team’s performance.
  .2 Change Requests
Changes may required as a result of team development activities; if recommended corrective or preventive impact any component of the project management plan or project documents. Such requests are processed through integrated change control.

## Slide 41: 9.4.3 DEVELOP TEAM: OUTPUTS
.3 Project Management Plan Updates
  The component of the project management plan often updated as a result of this process is Resource Management Plan
  .4 Project Documents Updates
Updates may required to:
Lessons Learned Register. Updated with information on challenges encountered and how they could be avoided in future projects or phases.
Project Schedule. Develop Team activities may require changes to the project schedule.
Project Team Assignments. Updated to record changes in team assignments as a result of Develop Team process.
Resource Calendars. Updated to reflect changes in resource availability
Team Charter. Updated to reflect changes in operating guidelines.
.5 Enterprise Environmental Factors Updates
Updates may be needed to employee development plan records and skills assessments
.6 Organizational Process Assets Updates
Updates may be needed to training requirements and skills assessments.

## Slide 42: 9.5 MANAGE TEAM
Adopted from PMI’s (PMBOK® Guide)

## Slide 43: 9.5 - MANAGE TEAM
Involves tracking team members’ performance, providing feedback, resolving issues, and coordinating changes to enhance project performance.
These activities are performed by the project management team, and requires a variety of management and leadership skills for fostering teamwork, integrating members’ efforts to create high-performing teams.
Team management involves communication, conflict management, negotiations, and leadership.
Project managers should provide challenging assignments to team members and provide meaningful feedback for high performance, while being sensitive to both willingness and ability of team members, and providing more oversight to low-skill members.
Adopted from PMI’s (PMBOK® Guide)

## Slide 44: 9.5 MANAGE TEAM
.1 Change Requests
.2 Project Mgmt. Plan
Updates
Resource Mgmt. Plan
Schedule Baseline
Cost Baseline
.3 Project Doc. Updates
Issue Log
Lessons Learned Reg
Project Team Assign’t
.4 Ent. Env. Factors Update
.1 Interpersonal & Team
skills
Conflict Management
Decision making
Emotional Intelligence
Influencing
Leadership
2 PMIS
1 Project Mgmt. Plan
Resources Mgmt. Plan
2 Project Documents
  Issue log
  Lessons learned Reg.
  Project Team Assgm’t.
  Team Charter
  3 Work Performance Rep.
  4 Team Perf. Assessment
  5 Ent. Env. Factors
  6 Org. Process Assets
Adopted from PMI’s (PMBOK® Guide)
Inputs
Tools &
Techniques
Outputs

## Slide 45: 9.5.1 MANAGE TEAM: INPUTS
.1 Project Management Plan
Resource Management Plan. Contains information about roles & responsibilities, project organization, staffing management
.2 Project Documents
Issue Log. Used to document who is to resolve an issue and when
Lessons Learned Register. Used to provide information to be applied to managing project team at a later stage.
Project Team Assignments. Identifies team roles and responsibilities
Team Charter. Provides guidance on decision making, meetings and conflict resolution.
.3 Performance Reports
Includes control results from schedule, cost, quality, and scope validation to help generate decisions and take actions. The forecast information included in the report, assist in determining future resource requirements, negotiations, and updates the resource management flan.
.4 Team Performance Assessment
Performed continually, provides information about actions to be taken to resolve issues, modify communications, address conflicts and improve team interaction.

## Slide 46: 9.5.1 MANAGE TEAM: INPUTS
.5 Enterprise Environmental Factors
Human Resources Management Policies.
.6 Organizational Process Assets
  The project management team should utilize organization’s policies and procedures for rewarding employees during the project activities. These may include using:
  Certificates of appreciation
  Corporate apparel
  Other organizational perquisites.

## Slide 47: 9.5.2 MANAGE TEAM: TOOLS & TECHNIQUES
.1 Interpersonal & Team Skills
Conflict Management. Conflicts are inevitable in a project environment. Successful conflict management results in greater productivity, and positive working relationships. When managed properly, substantive differences in opinion (i.e., functional conflicts) can lead to increased creativity and better decision making. When personal differences become a negative factor (i.e., dysfunctional conflicts), team members are responsible for resolution. If disruptive conflicts continue, formal procedures, including disciplinary action, may be necessary. Factors that influence conflict resolution methods include:
  Intensity and importance of the conflict
  Urgency for a resolution
  Relative power of people involved in the conflict
  Importance of maintaining good relationships
  Motivation to find a long-term or short term solution

## Slide 48
There are five general techniques for resolving conflicts. Each is appropriate for a particular situation.
Withdraw / Avoid. Retreating from the situation; postponing the issue
Smooth / Accommodate. Emphasising areas of agreement, conceding one’s position to the needs of others to maintain good relationship
Compromise / Reconcile. Finding satisfactory solutions to all others, to temporarily or partially resolve the conflict.
Force / Direct. Pushing one’s opinion at the expense of others’. Usually enforced through power positions to resolve emergencies.
Collaborate / Problem Solve. Cooperatively incorporate multiple viewpoints and insights from differing perspectives. Typically leads to consensus and commitment.
Decision Making. involves ability to negotiate and influence the organization or the project management team. Guidelines:
- Focus on goals - Analyze available information - Follow process - Stimulate creativity
- Study environmental factors - Account for risk

## Slide 49: 9.5.3 MANAGE TEAM: OUTPUTS
.1 Change Requests
  Staffing changes can effect the rest of the project plan.
  A change request must be processed through the integrated change management process
.2 Project Management Plan Updates
  Updates may be required, as a result of manage team process:
  Resource Management Plan. Updated to reflect actual experience in managing the team.
  Schedule Baseline. Actual team performance may necessitate updates.
  Cost Baseline. Actual team performance may necessitate updates.
.3 Project Documents Updates
Issue Log. Updated to record new issues
Lessons Learned Register. Updated with information on challenges encountered and the best solutions.
Project Team Assignments. Updated to reflect changes.
.4 Enterprise Environmental Factors Updates
Updates may be necessary to performance appraisals, and personnel skills data

## Slide 50: 9.6 CONTROL RESOURCES

## Slide 51: 9.6 CONTROL RESOURCES
The process is to ensure that project resources are available and assigned to the project activities as planned, as well as monitoring and comparing their actual utilization with the plan, and taking corrective action as necessary.
The process is continuously performed throughout the project life-cycle, to ensure that needed resource are assigned and released at the right time, right place and right quantity. This requires data about quantities used to date and quantities still required.
Control resources is mainly concerned with:
  Monitoring resource expenditure
  Dealing with shortage/surplus in a timely manner
  Informing relevant stakeholders if any issues arise
  Influencing the factors that can change resource utilization
  Managing actual changes as they occur.

## Slide 52: 9.6 CONTROL RESOURCES
.1 Work performance info
.2 Change Requests
.3 Project Mgmt. Plan Updates
Resource Mgmt. Plan
Schedule Baseline
Cost Baseline
.4 Project Doc. Updates
Assumption Log
Issue log
Lessons Learned Register
Physical Resource Assgn’t
RBS
Risk Register
.1 Data Analysis
Alternative Analysis
Cost-Benefit Analysis
Performance Reviews
Trend Analysis
2 Problem solving
3 Interpersonal & Team
skills
Negotiation
Influencing
4 PMIS
1 Project Mgmt. Plan
Resources Mgmt. Plan
2 Project Documents
  Issue log
  Lessons learned Reg.
  Physical Resource Assgm’t.
  Project Schedule
  RBS
  Resource Requirements
  Risk Register
  3 Work Performance data
  4 Agreements
  5 Org. Process Assets
Inputs
Tools &
Techniques
Outputs

## Slide 53: 9.6.1 CONTROL RESOURCES - INPUTS
.1 Project Management Plan
Resource Management Plan, a component of the project management plan, provides guidance about how physical resources should be controlled & released.
.2 Project Documents
Issue Log. Identifies physical resource availability and quality issues.
Lessons Learned Register. Provides information on past experience.
Physical Resource Assignments. Describes expected resource utilization, type, quantity, location and source.
Project Schedule. Identifies, what when and where resources are needed
Resource Breakdown Structure. Provides resource replacement references.
Resource Requirements. Identifies needed material, equipment, supplies
Risk Register. Identifies risks that may impact physical resources.
.3 Work Performance Data
Provides data on status of resources used to date by type and quantity
.4 Agreements
Provide information on external resources, and procurement procedures
.5 Organizational Process Assets
Control and allocation policies, issue escalation procedures, lessons learned.

## Slide 54: 9.6.2 CONTROL RESOURCES TOOLS & TECHNIQUES
.1 Data Analysis
Alternative Analysis. Used to select the best alternative for correcting variances in resource utilization, in situations of trade-off between time and cost.
Cost-Benefit Analysis. Helps to determine the least cost acceptable corrective action in case of project deviations.
Performance Reviews. Used to measure, compare and analyze actual resource utilization with planned utilization.
Trend analysis. Used to determine whether performance or resource utilization is improving over time.
.2 Problem Solving
Required to solve problems such as unavailability of physical resources, or late delivery by suppliers, etc. The methodical approach to be taken, where the problem is: identified – defined – investigated – analyzed – solved and checked.

## Slide 55: 9.6.2 CONTROL RESOURCES TOOLS & TECHNIQUES
.3 Interpersonal & Team Skills
Negotiation. Used to select the best alternative for correcting variances in resource utilization, in situations of trade-off between time and cost.
Influencing. Practiced by project managers to solve problems or obtain needed resources in time.
.4 Project Management Information Systems
Software programs for resource management or scheduling to ensure the right resources are deployed in the right place at the right time.

## Slide 56: 9.6.3 CONTROL RESOURCES - OUTPUTS
.1 Work Performance Information
Helps perform gap analysis by comparing resource requirements and resource allocation across project activities. Identified gaps need to be addresses.
.2 Change Requests
The project manager needs to submit a change request as a result of Control Resources process, or corrective/preventive action that may impact any component of the project management plan. Change requests are processed for review and disposition through Perform Integrated Change Control process.

## Slide 57: 9.6.3 CONTROL RESOURCES OUTPUTS
.3 Project Management Plan Updates
Resource Management Plan. Updated to reflect actual experience in managing project resources.
Schedule Baseline. The way resources are actually being managed may require a schedule update.
Cost Baseline. The way resources are actually being managed may require a schedule update.
.4 Project Documents Updates
Assumption Log. Updated to record new assumptions regarding physical resources.
Issue Log. Updated to record new issues encountered during the process
Lessons Learned register. Updated to record new effective control techniques
Physical Resource Assignment. Updated to record inevitable changes in resource assignments and usage.
Resource Breakdown Structure. Updated to reflect changes in the way resources are being used.
Risk Register. Updated with any new risks associated with resource availability, utilization or other resource risks

## Slide 58: PROJECT RESOURCE MANAGEMENT SUPPLIMENTARY TOPICS

## Slide 59: What Is Conflict?
Caused by trouble-makers
Conflicts are Bad
Should be avoided
Must be suppressed
Inevitable between humans
Often beneficial
Natural result of change
Can and should be managed
Traditional View
Contemporary View
A clash between hostile or opposing elements or ideas
Adopted from PMI’s (PMBOK® Guide)

## Slide 60: Antecedent Conditions Leading to Conflict
1. Ambiguous jurisdictions
2. Conflict of interest
3. Communication barriers
4. Depending on one party
5. Differentiation in organization
6. Association of the parties
7. Need for consensus
8. Behavior regulations
9. Unresolved prior conflicts
Notes: 1. ambiguous jurisdictions - 2+ parties have related responsibilities and work boundaries and role definitions are unclear
2. conflict of interest - 2+ parties want to achieve different or inconsistent goals relative to each other
3. communication barriers - lack of communication which leads to blocking efforts to explain the needs, viewpoints and action of those involved in the organization
4. dependence on one party - one person’s dependent on another to provide resources/knowledge
5. differentiation in organization - different sub-units in the organization are responsible for different tasks
6. association of the parties - occurs when people must work together and make joint decisions who don’t normally
7. need for consensus - people must willingly agree among themselves, no decision maker is available
8. behaviour regulations - the individual’s behaviour must be regulated closely, as in situations involving high levels of safety and security
9. unresolved prior conflicts - build up and create an atmosphere of tension which can lead to more conflict

## Slide 61: Conflict Management Modes
1. Withdrawal/Avoid
2. Smooth/Accommodate
3. Compromise/Reconcile
4. Force/Direct
5. Collaborate/Problem Solve
Temporary only,
Fails to resolve
Provides resolutions

## Slide 62: Conflict Management Modes
Smooth/Accommodate
  De-emphasizing differences and emphasizing commonalties
Withdraw/Avoid
  Retreating from actual or potential conflict situations
Compromise/Reconcile
  Considering various issues, bargaining, and searching for solutions which attempt to bring some degree of satisfaction to the conflicting parties

## Slide 63: Conflict Management Modes
Force/Direct
  Exerting one’s viewpoint at the expense of another party
Collaborate/Problem Solve
  Problem is defined; information gathered; alternatives developed and analyzed; and the most appropriate alternative is selected

## Slide 64: Sources of Conflict by Life Cycle Phase
Conceptual
Develop/
Detail Planning
Execute
Finish
project priorities
admin procedures
schedule
manpower
cost
technical opinions
personality
project priorities
schedules
admin procedures
technical opinions
manpower
cost
personality
schedules
technical opinions
manpower
project priorities
procedures
cost
personality
schedules
manpower
personality
project priorities
cost
technical opinions
procedures
Adopted from PMI’s PMBOK® Guide

## Slide 65: Styles of Conflict Resolution
Concerns for
Personal
Goals
Relationships
Force
Smooth
Withdraw
Compromise
Problem
Solver
Win-Lose
Yield-Lose
Lose-Leave
Compromise
Integrative
High
Low
Low
Medium
High
Low
High
Low
Medium
High
Adopted from PMI’s PMBOK® Guide

## Slide 66: Model for Effective Human Resource Management
Teamwork
Leadership
Communication
Internal
Cultural
Ambiance
Effective
HR
Management
Adopted from PMI’s (PMBOK® Guide)

## Slide 67: Authority, Accountability, Responsibility and Reliability
Legitimate power (formal, authority)
  Derived from a person’s position in the organization
Coercive power
  Based on fear
Reward power
  Positive reinforcement for behavior
Expert power
  Behavior that is perceived to be desired by another person’s special knowledge or skill
Referent power
  Based on a less powerful person’s association with a more powerful person
Notes: Many different types of power
Use in different situations

## Slide 68: Leadership
The important thing is not how much you know, but how well you can apply it!
  Leadership is the process of influencing other team members towards a goal
  Leaders are people who do the right things to accomplish the missions and objectives of their teams
Notes: A leader provides for those what they cannot provide for themselves.

## Slide 69: Leadership & Management Skills over Project Life Cycle
Plan
Produce
Project Life Cycle
Visionary
Creative
Conceptualizer
Analytical
Innovator
Leader
Facilitator
Planner
Integrator
Technically strong
Team leader
Organizer
Interface manager
People and task
oriented
Controller
Team leader
Trainer
Doer
Technical writer
Compulsion to
complete
Phase 1
Phase 2
Phase 3
Phase 4
Conceptual
(C)
Execute
(E)
Finish
(F)
Develop/
Detail Plan
(D)
Adopted from PMI’s PMBOK® Guide

## Slide 70: Situational Leadership
TELLING
DELEGATING
SELLING
PARTICIPATING
Low
High
High
Relationships
Task
Adopted from PMI’s PMBOK® Guide

## Slide 71: Leadership Approaches/Theories
Traits approach
  Personal attributes are correlated to certain personality characteristics, abilities and skills
  4 Most common traits
    Intelligence (technical and organizational)
    Maturity and broad range of interest
    Inner motivation and achievement drive (goal-oriented)
    Consideration of needs and values of team members (employee-centered)

## Slide 72: Leadership Approaches/Theories
Behavioral Approach
  Focuses on what leaders do and how they do it
  Task orientation
    Initiating structure that focuses on the quality and quantity of work accomplished
  Relationship orientation
    Being supportive and considerate of team members’ efforts to achieve personal goals, settling disputes, keeping people happy, etc.

## Slide 73: Leadership Approaches/Theories
Contingency Approach
  Emphasizes the importance of the situation
  4 Key variables which interact to influence the leader’s behavior:
    Personal characteristics of team leader
    Personal characteristics of team members
    Characteristics of team itself
    Structure of team, department or organization
  All interact to influence leader’s behavior

## Slide 74: Contingency Leadership Models
Fiedler’s Contingency Model
Hersey and Blanchard’s Situational Leadership Model
House’s Path-goal Model
Vroom and Jago Leadership Model

## Slide 75: Fiedler’s Contingency Model
Relates performance to the leader’s motivational system and the degree to which the leader controls and influences the situation
3 Contingency variables:
  Group atmosphere
  Task structure
  Leader’s position power
Notes: Emphasizes the importance of understanding the nature of the situation and then matching the correct leadership style to that situation
1. group atmosphere - leader’s acceptance by the team
2. task structure - extent to which a task performed by the team is routine or non-routine (e.g.. R&D vs. standard development)
3. leader’s position power - the extent to which the leader has reward, coercive and legitimate power

## Slide 76: Fiedler’s Contingency Model
Least preferred co-worker (LPC) scale measures leadership style
  All leaders have a motivational system that indicates the combinations of situations where they will be most effective
  Leaders can only be task-oriented or relationship-oriented in this model
  Does not consider that leaders can influence task structure and group atmosphere because of their knowledge of the situation
Notes: e.g. task-oriented leaders will do better with a group of low achievers
relationship orientation will be more effective with high achievers
organizations can affect the leader’s performance by changing the leader’s reward system

## Slide 77: Hersey and Blanchard’s Situational Leadership Model
Based on the amount of relationship and task behavior that a leader provides in a situation
Amount of either behavior is based on the readiness or development levels of team members
Notes: relationship behaviour is supportive
task behaviour is directive

## Slide 78: Hersey and Blanchard’s Situational Leadership Model
Directive behavior (task orientation)
  The extent in which the leader engages in one-way communication; e.g. telling people what, how, when to do tasks
  Focuses on structure, control and supervision
Supportive behavior (relationship orientation)
  The extent in which the leader engages in two-way communication; e.g. listens, provides support and encouragement
  Focuses on active listening, genuine praise and sincere facilitation
Notes: 3 key words for Directive behaviour
  structure
  control
  supervision

## Slide 79: Hersey and Blanchard’s Situational Leadership Model
Development level (readiness)
  The ability and willingness of the team members to perform tasks
  Refers to:
    Competence - task relevant knowledge and skills as well as transferable skills
    Commitment - motivation and self-confidence
    Attitude - attitude towards others and interpersonal skills
Notes: the appropriate style of leadership must match the readiness level of team members
team members not ready to perform their tasks and have low competence but high commitment - use directive
as readiness level of team members increases, leader’s style should change to be more participative

## Slide 80: House’s Path-Goal Model
  Based on expectancy theory of motivation
  A leader should try to enhance employees’ satisfaction with their jobs and increase their performance level
  Leadership behaviour is contingent upon the characteristics of team members and the nature of the tasks
  Leader’s goal is to reduce the barriers that may hinder team members from meeting their objectives
Notes: e.g.
for a clear, routine task, a participative style that is more considerate of employees will likely contribute to satisfaction and performance for highly independent team embers
for ambiguous, ego-involving tasks (e.g. making presentations to clients and top management), participative leadership will have positive effects on performance and job satisfaction regardless of an employee’s need for self-esteem or achievement

## Slide 81: Vroom and Jago Leadership Model
Focuses on role played by leaders making decisions
Provides a set of rules to help identify which leadership styles to avoid in a given situation

## Slide 82: Vroom and Jago Leadership Model
Leadership can choose any of five leadership styles of decision making:
  Autocratic
  Autocratic with some information
  One-to-one consultation style
  Consultation in a group
  Consensus
Notes: Autocratic - leader makes decisions without gathering information from team members
Autocratic with some information - leader requests certain information from others
One-to-one Consultation style - makes decisions after consultation with relevant parties or team members
Consultation in a group - project manager invites ideas and suggestions from team members in a meeting. Team leader makes the final decision which may or may not reflect the influence of the group. May lead to loss of trust if leader does not incorporate team’s ideas
Consensus - sharing problems with team members as a group. Team leader acts as facilitator and and does not influence team or impose own ideas.

## Slide 83: Leadership Approaches/Theories
Attributional Theory of Leadership
  Based on cause and effect relationship
  Leader is influenced by what they perceive to be the cause of the employee’s behavior
  Effective leaders identify the correct cause and then act accordingly

## Slide 84: Leadership Approaches/Theories
Charismatic Leadership Theory
  Charismatic leaders concentrate on developing a common vision or creating opportunities and encouraging team members to control their own behavior
  Use dominance, self-confidence, a need for influence and a conviction of high moral standards
  Sometimes called ‘transformational’ leaders
Notes: Transformational leaders rely on their referent power - power they earned based on their personal qualities - to inspire team and heighten their motivation to achieve project goals.
Typically use the following behaviours:
  help team members recognize the need for revitalizing the organization by developing their need for change
  create a new vision and motivate team embers to gain their commitment to the objectives of the project
  institutionalize change by replacing old technical and political networks with new ones

## Slide 85: Leadership
L
E
A
D
Listen to your project team and the client (build trust among stakeholders)
Encourage the heart of team members (motivation)
Act as a real team (inspire team for high performance)
Deliver the deliverables (with emphasis on quality)

## Slide 86: Motivation
Motivation:
  Influences productivity
  Is an intrinsic and internal phenomenon or process
  Encourages people to achieve their objectives
  Involves psychological, social and economic satisfaction
  Involves the creation of an environment that helps everyone achieve work-related objectives while gaining the maximum personal satisfaction
Notes: Complications:
motives can only be inferred and cannot be seen
needs are dynamic in nature
people rank and select their motives differently
people apply different energy levels in pursuing their motives

## Slide 87: Motivation
Six core phases in the motivational process:
  1. A person’s needs are identified
  2. Drives created
  3. Select goal-directed behaviour
  4. Perform the task
  5. Receive feedback
  6. Reassess needs and goals
Notes: ID person’s needs - needs are deficiencies that act as energizers. May be expressed as psychological, physiological or social affiliation needs
Drives created - needs give rise to wants or desires that create drives
Select goal-oriented behaviour - a person selects a course of action that will achieve a goal. Goal acts as a force to make the person work harder and achieve high performance
Perform the task - successful accomplishment of desirable goals leads to a reduction in need deficiencies and the tensions or dissatisfactions created by them
Receive feedback - people are personally satisfied when they receive positive feedback and when project goals are achieved successfully
Reassess needs and goals - Once receive feedback, people reassess their need and goals and make appropriate adjustments in their strategies, actions and behaviours

## Slide 88: Content Motivational Theories
Maslow’s Hierarchy of Needs
Alderfer’s ERG Needs
Herzberg’s Motivational/Hygiene Theory
McClelland’s Achievement Motivation Theory

## Slide 89: Maslow’s Hierarchy of Needs
  Motivation springs from an unsatisfied need
  Lower-level needs must be satisfied before higher-level needs can be addressed
  Dynamic of needs are complex and several needs may impact behavior at any one time
  Higher needs can be satisfied in more ways than lower needs

## Slide 90: Maslow’s Hierarchy of Needs
Physiological needs
Safety/security needs
Social/affiliation needs
Esteem needs
Self
actualization
Maslow’s
Hierarchy
of Needs
Adopted from PMI’s PMBOK® Guide

## Slide 91: Alderfer’s ERG Needs
Basic needs:
  Existence needs
    Similar to Maslow’s physiological and safety needs
    Basic material needs i.e. food, water, shelter, working conditions
  Relatedness needs
    Similar to Maslow’s social needs
    Establishing and maintaining interpersonal relationships at work and home
  Growth needs
    Similar to Maslow’s esteem and self-actualization
    Efforts to explore opportunities for personal development and growth by contributing at work

## Slide 92: Alderfer’s ERG Needs
ERG needs suggest there are 2 processes at work
  Progression process
  Frustration-regression process
Frustration trying to satisfy growth needs will lead to regression and previous needs will re-emerge as a major motivating force
Notes: In addition to fulfillment progression process, frustration-regression process.

## Slide 93: Herzberg’s Motivator/Hygiene Theory
Two factors associated with motivation:
  Hygiene i.e. the work environment
  Motivators i.e. the work itself
Notes: One of the most controversial theories of motivation -
  some job factors lead to satisfaction
  others can only prevent dissatisfaction and are not sources of satisfaction

## Slide 94: Herzberg’s Motivator/Hygiene Theory
Hygiene factors
  May prevent dissatisfaction
  Necessary but not sufficient to provide motivation
  e.g. compensation, company policies and administration, working conditions, relationships with peers, supervisor and subordinates
  Sometimes called maintenance factors
Motivators
  Increase job satisfaction and are more permanent
  e.g. accountability/responsibility for own work, recognition, personal growth, achievement
Notes: Can also create dissatisfaction if not provided
The absence or inappropriate administration of these factors leads to unhappiness, however, their presence does not guarantee contentment.
Frequently helpful in motivating on a temporary basis

## Slide 95: McClelland’s Achievement Motivation Theory
People generally have achievement motives
Are motivated according to their strength of desire to achieve high levels of performance or to succeed in competitive situations
Need for achievement
  The drive to excel, succeed
Need for power
  Influence others to behave in a manner they would not behave otherwise
Need for affiliation or association
  Desire for friendly and close personal relationships at work

## Slide 96: Process Motivational Theories
Emphasizes the decision making processes used and the role of rewards on future performance
  McGregor’s Theory X and Theory Y
  Ouchi’s Theory Z
  Contingency Theory
  Goal-Setting Theory
  Expectancy Theory
  Reinforcement Theory
  Equity Theory

## Slide 97: McGregor’s Theory X and Theory Y
Theory X
People:
  Dislike work and will try to avoid it - inherently lazy
  Lack of ambition and little capacity for problem solving
  Want to be controlled and directed
  Are resistant to change and don’t care about organizational needs
  Are motivated by money, position and punishment
Theory Y
People:
  Are creative, ambitious and committed to organizational goals
  Can direct and control themselves
  Are highly self-motivated
  Desire responsibility
Adopted from PMI’s (PMBOK® Guide)
Notes: Theory X assumes people follow the path of least resistance and are largely motivated by money, position and punishment.
  PMs who believe in this tend to be authoritarian and suspicious
Theory Y implies a humanistic and supportive approach to managing people.
  PMs provide more freedom and the opportunity to participate in planning and decision making

## Slide 98: Ouchi’s Theory Z
  High levels of trust, confidence, and commitment to workers by management
  Workers are trustworthy and capable of working without close supervision
  Based on Japanese values of lifetime employment, slow promotions, infrequent evaluations and non-specialized career paths
Notes: Postulated that to the extent that the egalitarian assumptions of Japanese organizations could be incorporated into American organizations, the productivity of Americans could be improved.

## Slide 99: Contingency Theory
  Developed by Morse and Lorsch - based on McGregor’s Theory Y and Herzberg’s Hygiene Theory
  People have a central need to achieve competence
  Need continues to motivate people even after competence is met
Notes: Built upon McGregor’s Theory Y and Herzberg’s theory of hygiene and motivating factors
PMs should ensure that tasks assigned to members match their skill sets and that the organizational climate(degree of control, organizational structure) is conducive to help them meet their needs and achieve a sense of competence.

## Slide 100: Goal-Setting Theory
  Developed by G.P. Latham and E.A. Locke
  Motivation comes from a person’s internal drive and desire to achieve goals
Notes: Project participants must be invited to participate in setting goals and formulating plans and implementation strategies in order to gain their acceptance of and a commitment to meet those goals.

## Slide 101: Expectancy Theory
  Developed by Victor Vroom
  People think seriously about how much effort they should put into a task
  Motivation occurs if there is an expectation of a favourable outcome
  People choose behaviours they believe will lead to desired rewards or outcomes
Notes: The linkage, also called expectancy, is the belief of an individual that his or her actual effort will result in a given outcome.

## Slide 102: Reinforcement Theory
  Based on B.F. Skinner’s behavior modification theories
  Human behavior is shaped by the previous positive or negative outcomes experienced
  Desirable behavior will be repeated if rewarded
  Undesirable behavior will be discouraged if punished
Notes: Key element of this theory is reinforcement.
Managers must stay in constant contact with their teams and encourage open and informal communication with them.

## Slide 103: Equity Theory
  Developed by J. Stacy Adams
  People want to be treated equitably
  Team members compare job inputs and outputs with other team members
  Inequities can influence the degree of effort exerted
Notes: PMs must ensure all members are compensated fairly for their contribution to project success because any signs of inequity will in turn demotivate people.

## Slide 104: TEAM BUILDING
Role Clarification
Procedures
Development
Interpersonal
Concerns
Team Process Behaviour
Communicating
Leadership
Managing Conflict
Providing Support
Gaining Commitment
Making Decisions
Climate
Setting
Goal
Setting
Control
Decision
Making
Adopted from PMI’s (PMBOK® Guide)

## Slide 105: 9.3.2 - ACQUIRE RESOURCES TOOLS & TECHNIQUES
Types of Negotiation
Distributive (win-lose)
    One party’s gain is the other’s loss
    Occurs during intense conflicts over economic issues
Integrative (win-win)
    Seek solutions where both parties win
    Both parties show flexibility, trust and are motivated to solve problems
Lose-Lose
    Both parties take an extreme position

## Slide 106: 9.1.2 PLAN RESOURCES MANAGEMENT: TOOLS & TECHNIQUES
Organizational principles
  Unity of command
  Parity in authority and responsibility
  Scalar principle (chain of command)
  Span of management
  Flexibility
  Division of labor
  Departmentation
Dimensions of Organizational Structure
  The organizational structure of a project can be analyzed along several dimensions:
    Formalization
    Centralization
    Complexity
    Specialization

## Slide 107: 9.1.2 PLAN RESOURCE MANAGEMENT TOOLS & TECHNIQUES
Formalization
  The degree to which written policies, procedures, rules and job descriptions are defined
  Excessive formalization may create ‘red tape’ so be aware of the size of your project - the larger it is, the more formal it will need to be
Centralization
  The authority to make decisions is highly centralized and project teams have limited decision making authority
  Decentralized projects tend to have more authority residing within the project team
  Centralization may vary according to the project life cycle
Notes: e.g. Y2K projects need to be very formal

## Slide 108: 9.1.2 PLAN RESOURCES MANAGEMENT TOOLS & TECHNIQUES
Complexity
  Covers the number of different job titles and departments involved in the project
  The more complex, the more interface management and communication required
Specialization
  Breaking a complex task into simple functional parts
  Increases efficiency
  Often leads to boredom, unhappiness and lack of motivation
Notes: the more complex, the more admin time required, as well
PMs must have strong HR skills to manage tasks across several functional boundaries
must formulate and practice an effective communication strategy